{"text_format":"3","workbook":"xls","n_sheets":3,"sheets":["新增","调整","Sheet3"],"not_rendered":{"external_links":1,"defined_names":2},"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"新增","index":0,"n_rows":91,"n_cols":25,"rows_kept":91,"merged":[[0,0,0,24],[1,0,1,24],[2,0,4,0],[2,1,2,3],[2,4,4,4],[2,5,4,5],[2,6,4,6],[2,7,4,7],[2,8,4,8],[2,9,2,10],[2,11,4,11],[2,12,4,12],[2,13,2,15],[2,16,2,21],[2,22,4,22],[2,23,4,23],[2,24,4,24],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,9,4,9],[3,10,4,10],[3,13,4,13],[3,14,3,15],[3,16,4,16],[3,17,4,17],[3,18,4,18],[3,19,3,21],[90,0,90,4]],"flags":["formulas_cached_only"]}
["2023年度巩固拓展脱贫攻坚成果和乡村振兴项目库入库项目明细表"]
["单位：(盖章)"]
["序号","项目类别",null,null,"乡","村","项目名称","建设性质","实施地点","时间进度",null,"责任单位","建设内容及规模","资金规模和筹资方式",null,null,"受益对象",{"$nulls":5},"绩效目标","联农带农机制","备注"]
[null,"项目 类型","二级 项目 类型","项目子类型",{"$nulls":5},"计划开工时间","计划完工时间",null,null,"项目预算 总投资( 万 元)","其中",null,"受益村数(个)","受益户数(户 )","受益人口数(人)","其中"]
[{"$nulls":14},"财政资金(万 元)","其他资金(万 元)",{"$nulls":3},"受益脱贫村数 (个)","受益脱贫户数及防止返贫监测对象户数(户)","受益脱贫人口数及防止返贫监测对象人口数(人)"]
[1,"产业发展","配套设施项目","小型农田水利设施建设","云湖街道","大岭村","游冲组沟渠疏浚","整修","大岭村游冲组",2023.3,2023.4,"大岭村","沟渠清淤疏浚3000米",6,3,3,1,132,408,1,54,163,"沟渠清淤疏浚3000米，收益2500人以上","300亩农田灌溉排水安全"]
[2,"乡村建设行动","人居环境整治","村容村貌提升","云湖街道","大岭村","同德组至三湾组河道整治清淤","整修","同德组至三湾组",2024.6,"2023.11","大岭村","清理整治同德组至三湾组共十个组河道，全长4.4千米",50,50,0,1,230,1320,1,12,38,"河道整治清淤4.4千米","提高水质和人居环境适宜"]
[3,"乡村建设行动","农村基础设施","农村道路建设","云湖街道","大岭村","大岭村组级公路提质改造","新、改建","大岭村三湾组至曹家组",2023.8,"2023.10","大岭村","3.5m宽路面白改黑1500m。",120,100,20,1,86,620,1,4,12,"3.5m宽路面白改黑1500m。","改善村民安全出行条件，满足群众生活需要。"]
[4,"产业发展","生产项目","种植业示范基地","云湖街道","云湖集中安置小区","湖南省雨露星辰种养专业合作社","产业发展","飞跃社区",2023.4,2023.12,"云湖集中安置小区","蔬菜种植示范基地土地租赁、开荒平整20亩，示范基地基础建设与种植生产20亩",15,9,6,1,167,654,1,167,654,"蔬菜种植示范基地20亩，受益600人以上","巩固脱贫成果，引导安置小区脱贫人口参与产业发展，主要带动小区居民就近务工，促进安置小区脱贫人口家庭增收，降低返贫风险。"]
[5,"乡村建设行动","农村基础设施","农村供水保障设施建设","云湖街道","板桥村","新建自来水备用水源设施","新建","魏家组",2023.4,2023.7,"板桥村","修建一座蓄水水库，蓄水体积5000立方",45,5.24,39.76,1,1088,5030,1,64,211,"新建自来水备用水库一个，蓄水能力达5000立方；备用水源临时供全村用水7天以上","带动农户就业，保障农户饮水安全。"]
[6,"产业发展","生产项目","种植业基地","云湖街道","三联村","三联村葛根种植基地",null,"三联村八屋组",2023.3,"2023.12","三联村","预计种植葛根15余亩，平整土地，购买葛苗附属材料及田间管理",10.5,3,7.5,1,63,581,1,5,22,"增加村集体经济收入","种植葛根，带动农户就业发展产业，增加农户收入"]
[7,"乡村建设行动","农村基础设施","农村供水保障设施建设","白羊田","方山村","殷家组-伍上组水沟维修","改建","殷家组-伍上组",2023.4,2023.5,"白羊田镇方山村","修建水沟全长约300米",6,4,2,1,85,355,0,6,15,"完成殷家组-伍上组水沟维修，全长约约300米，保障群众农业灌溉，激发群众发展生产的积极性，促进增收。","改善农业生产条件，保障群众农业灌溉，激发群众发展生产的积极性，促进增收。"]
[8,"产业发展","配套 基础 设施 项目","小型农田水利设施建设","聂市镇","黄盖村","磨咀组山塘、余家组山塘","新建","磨咀组、余家组","2023年2 月","2023年4 月","黄盖村","山塘清淤、堵漏、埋设涵管、整修",7,5,2,1,89,235,null,6,20,"山塘整修解决了农业生产灌溉问题，提高脱贫困户和周边群众增产增收。","带动农户及脱贫户稻田灌溉及增产增收。"]
[9,"产业发展","生产项目","养殖业基地","聂市镇","黄盖村","种牛养殖基地建设","新建","杨家组","2023年02 月","2023年底","黄盖村","新建养殖厂房",93,63,30,1,713,2754,null,19,51,"种牛养殖基地建设，巩固脱贫成效，壮大集体经济，带动发展生产。","给脱贫户及农户增收。"]
[10,"产业发展","生产项目","水产养殖业发展","聂市镇","黄盖村","特种水产养殖","新建","余桥组","2023年02 月","2023年10 月","黄盖村","特种水产养殖建设",60,45,15,1,68,193,null,5,16,"特种水产养殖及水质治理建设，带动产业发展","解决脱贫户及群众就业，增收。"]
[11,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","聂市镇","沿河社区","香花组、祠畈组道路硬化","新建","沿河社区香花组、祠畈组","2023年 6月","2023年 12月","沿河社区","香花组、祠畈组道路硬化长260米，宽3.5米，厚15公分",8,6,2,1,47,136,null,5,15,"加强乡村建设，改善脱贫户及居民周边环境，巩固脱贫成果。","加强基础设施建设，改变村容村貌，巩固脱贫成果。"]
[12,"产业发展","生产项目","养殖业基地","聂市镇","官田村","肉鸽喂养","新建","原官田村小学","2023年","2023年","官田村","肉鸽喂养",30,20,10,1,200,500,1,24,56,"该项目涉及农户300户960人，其中脱贫户24户56人。","带动脱贫户及农户发展产业"]
[13,"乡村建设行动","农村基础设施","水利设施建设","聂市镇","源潭社区","源潭社区万家岭机埠恢复","新建","源潭社区万家巷","2023年05 月","2023年07 月","源潭社区","1300米长，型号35的水管安装，所有的设施更新",120,35,85,1,655,2530,null,6,15,"解决周边农户4000亩农田的灌溉问题","加强基础建设，为农业发展提供条件，巩固脱贫成果"]
[14,"乡村建设行动","农村 基础 设施","农村供水保障设施建设","聂市镇","马垅村","渔民退铺后续工程（自来水安装）","新建","马垅村渔业组","2023年 4月 7日","2023年12月底","马垅村","所有渔民自来水管全部铺设\n",12,10,2,1,162,526,1,3,8,"解决渔业组162农户526人饮水安全亩，其中脱贫户3户8人。","解决渔业组162农户526人饮水安全亩，其中脱贫户3户8人，巩固脱贫成果。"]
[15,"乡村建设行动","农村基础设施","农村道路建设","聂市镇","朱圣村","炮铺组公路处险拓宽及硬化","新建","朱圣村炮铺组","2023年 6月","2023年 10月","朱圣村","炮铺组处险公路拓宽及硬化长50米，宽1.5米",5,2,3,1,65,220,null,4,9,"加强乡村建设，改善脱贫户及居民周边环境，巩固脱贫成果。该项目涉及农户65户220人，其中脱贫户4户9人","加强基础设施建设，改变村容村貌，巩固脱贫成果。"]
[16,"乡村建设行动","农村基础设施","农村供水保障设施建设","聂市镇","朱圣村","自来饮用水安装入户","新建","朱圣村","2023年","2023年","朱圣村","自来水安装",68.2,68.2,0,1,912,3679,1,36,108,"加强乡村建设，改善脱贫户及居民钦水安全，巩固脱贫成果。","加强基础设施建设，改变村容村貌，巩固脱贫成果。"]
[17,"产业发展","配套 基础 设施 项目","小型农田水利设施建设","聂市镇","红士村","山塘整修","新建","红士村","2023年","2023年","红士村","红士村山塘整修（何家冲、和平组、下王组、塘上组、大屋组、胡门组、带沙组、张义组、毛桥组）",30,15,15,1,562,1820,1,25,78,"山塘维修（群众用水），稳固脱贫成效，方便群众发展产业。该项目涉及农户562户1820人，其中脱贫户25户78人","水利设施维修，方便群众发展生产，巩固脱贫攻坚成果。"]
[18,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","聂市镇","同德村","聂市镇同德村上下铺组桥梁建设工程","新建","同德垸","2023年3  月","2023年6 月","同德村","上下铺组桥梁建设工程桥长10米，宽5米。",10.5,8.5,2,3,156,610,null,4,9,"该项目的实施，大大改善当地村民的出行，为当地的经济社会发展提供了有力的保障，确保了我村新农村建设的快速发展。","方便群众的出行，促进经济发展。"]
[19,"产业发展","配套 基础 设施 项目","小型农田水利设施建设","聂市镇","三和村","山塘整修","新建","三和村\n茶冲组，西安组，桥桠组山塘整修。","2023年 3月","2023年 10月","三和村","山塘整修",15,10,5,1,160,358,null,11,22,"山塘维修（群众用水），稳固脱贫成效，方便群众发展产业。该项目涉及农户160户358人，其中脱贫户11户22人","水利设施维修，方便群众发展生产"]
[20,"产业发展","配套 基础 设施 项目","小型农田水利设施建设","聂市镇","新安村","杉木山塘敷修","新建","新安村杉木组","2023年 4月","2023年 11月 ","新安村","山塘清淤、堤坝加固、涵管更新",4,3,1,1,80,238,null,6,17,"山塘维修（群众用水），稳固脱贫成效，方便群众发展产业。该项目涉及农户80户238人，其中脱贫户6户17人","水利设施维修，方便群众发展生产"]
[21,"产业发展","配套 基础 设施 项目","小型农田水利设施建设","聂市镇","乘风村","引水渠及排渠护砌建设","新建","群英组","2023年","2023年","乘风村","引水渠及排渠护砌工程",15,12,3,1,103,341,null,4,14,"稳固脱贫成效，方便群众发展产业。该项目涉及农户103户341人，其中脱贫户4户14人","水利设施建设，方便群众发展生产"]
[22,"产业发展","配套 基础 设施 项目","小型农田水利设施建设","聂市镇","同合村","洞庭组山塘清淤及浆彻石","新建","洞庭组 ","2023年","2023年","同合村","洞庭组山塘清淤及浆彻石",25,20,5,1,131,405,1,16,56,"山塘清淤及浆彻石有效防止通村道路塌陷及4个组的稻田灌溉，提高贫困户增产增收。","带动农户及脱贫户稻田灌溉及增产增收。"]
[23,"乡村建设行动","农村基础设施","农村道路建设","聂市镇","同合村","村部门前道路拓宽及白改黑","2022年转2023年","同合村村部","2023年","2023年","同合村","村部门前道路拓宽及白改黑",30,25,5,1,1038,4407,1,65,227,"村部门前的道路拓宽及白改黑，可改造村部环境，便于村民进村办事。","加强基础建设，改变村容村貌，为民提供优越生活条件，巩固乡村振兴成果。"]
[24,"乡村建设行动","农村基础设施","农村供水保障设施建设","聂市镇","凤形村","自来饮用水安装入户","新建","马冲组，刘塘组，下后组","2023年","2023年","凤形村","饮用水安装",40,20,20,3,65,221,null,6,14,"解决3个组村民安全饮水问题，该项目涉及农户65户221人，其中脱贫户6户14人。","解决3个组村民安全饮水问题，增加群众幸福感。该项目涉及农户65户221人，其中脱贫户6户14人。"]
[25,"产业发展","配套 基础 设施 项目","小型农田水利设施建设","聂市镇","长源村","山塘整修","新建","郑东   郑西      塘堪   汪家   刘家山塘整修","2023年","2023年","长 源 村","山塘整修",25,20,5,1,256,725,null,18,35,"山塘维修（群众用水），稳固脱贫成效，方便群众发展产业。该项目涉及农户256户725人，其中脱贫户18户35人","水利设施维修，方便群众发展生产"]
[26,"乡村建设行动","农村基础设施","农村道路建设（通村路、通户路、小型桥梁等）\n","聂市镇","乘岭社区","乘岭社区和美乡村示范建设","新建","乘岭社区","2023年 4月","2023年 11月 ","乘岭社区","老屋组至大保组公路扩宽硬化1.5米，长2450米，三处驳岸146米；白羊组驳岸，长190米计1127立方米",150,100,50,1,181,603,null,12,39,"和美乡村示范创建，加强乡村建设，改善脱贫户及居民周边环境，巩固脱贫成果。该项目涉及农户181户603人，其中脱贫户12户39人。","方便居民出行，带动产业发展。"]
[27,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄盖镇","合兴村","合兴村胜利组道路硬化","新建","合兴村胜利组","7月","8月","黄盖镇合兴村","合兴村胜利组道路硬化约400米",18,15,3,1,14,56,0,2,"4（伍玉兴、谭国伍）","完成胜利组组级道路硬化400米左右，改善村民生产生活条件。","改善胜利组村民生产生活条件，为出行和农作提供更多便利，提高致富创收热情"]
[28,"产业发展","配套基础设施项目","小型农田水利设施建设","江南镇","灯塔村","灯塔6组到三级渠沟渠清淤","维修","灯塔6组到三级渠","9月","11月","灯塔村","灯塔6组到三级渠沟渠清淤",8.57,5,3.57,1,285,860,null,14,41,"方便村民农田耕种；使脱贫户增产；促进乡村振兴发展。","通过沟渠清淤方便农田灌溉，增加农户种养积极性，使其增产增收；方便防汛抗旱期间排渍抽水。"]
[29,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","灯塔村","孙洲七组道路拓宽","新\n建","灯塔村孙洲七组","8月","9月","灯塔村","600米",15.4406,10,5.4406,1,116,460,null,28,81,"工程：新建600米长，1.5米宽资源路。解决村民出行难的问题，村民与脱贫户农产品销售难问题，有效提高经济收入。","为脱贫户增收500元--1000元"]
[30,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","新湖村","黄沙塘组公路硬化","新建","新湖村黄沙塘组","4月","4月","新湖村","组级公路硬化400米长，3.5米宽",11.2,5,6.2,1,48,174,0,2,7,"工程：新建400米长，3.5米宽，0.2米厚资源路。改善村民出行交通条件，有效提高经济收入","为脱贫户增收500元--1000元"]
[31,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","坦渡村","西头组公路硬化","新建","坦渡村西头组","2023.5.1","2023.5.20","坦渡村","硬化公路500米,4米宽，厚20厘米",50,10,40,1,65,300,0,3,7,"工程：硬化长1000米、宽4米、厚20公分，解决村民与脱贫户出行难，方便运输，巩固脱贫成效","使脱贫户增收800元左右"]
[32,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","长岭社区","中长岭旧塘清淤整修","新建","长岭社区中长岭组","2023.4.1","2023.6.30","长岭社区","清淤7亩",14,5,9,1,1102,3151,0,21,44,"改建基础设施，有效改善脱贫户和居民水体质量，提升山塘的蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。","使脱贫户增收800元左右"]
[33,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","长岭社区","樊家组山塘清淤","新建","长岭社区樊家组","2023.4.1","2023.6.30","长岭社区","清淤5亩",6,4,2,1,1102,3151,0,21,44,"改建基础设施，有效改善脱贫户和居民水体质量，提升山塘的蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。","使脱贫户增收800元左右"]
[34,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","灯明村","畈屋组山塘维修","新建","灯明村畈屋组","2023.5.9","2023.5.30","灯明村","面积12006平方米，清淤4802.4立方，塘堤长60米、高3.2米、底宽6.5米、面宽2.5米。",6.2,5,1.2,1,68,258,0,6,20,"解决畈屋组群众及脱贫户生产生活用水问题，使群众和脱贫户生产生活用水更加方便，提高了群众及脱贫户生产生活问题。","使脱贫户增收800元左右"]
[35,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","韩桥村","全村各组35口塘整修","整修","韩桥村","4月","10月","韩桥村","35口",60,40,20,1,886,3161,0,35,92,"改建基础设施，有效改善脱贫户和居民水体质量，提升山塘的蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。","使脱贫户增收800元左右"]
[36,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","韩桥村","大坝山水库整修","整修","韩桥村大坝山","4月","10月","韩桥村","清淤26000平方，砌护坡道1000",100,70,30,1,886,3161,0,35,92,"改建基础设施，有效改善脱贫户和居民水体质量，提升山塘的蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。","使脱贫户增收800元左右"]
[37,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","韩桥村","撇红河升级改造","整修","韩桥村 ","4月","10月","韩桥村","5000米撇洪河升级改造",90,70,20,1,886,3161,0,35,92,"改建基础设施，有效改善脱贫户和居民水体质量，提升山塘的蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。","使脱贫户增收800元左右"]
[38,"产业发展","生产项目","种植业基地","桃林镇","白石村","白石组茶园改造","茶   园  改  造","白  石  组","4月","5月","白石村","30亩",15,13,2,1,32,152,1,3,6,"促进农业发展，提高茶叶生产量，改善居民的生活环境。","改善人居环境，提升居民幸福感。促进农业发展，提高茶叶生产量，改善居民的生活环境。"]
[39,"产业发展","配套基础设施","小型农田水利设施建设","桃林镇","白石村","新屋组堰坝水渠维修","堰坝水渠维修","白石村新屋组","11月","12月","白石村委会","堰坝长12米宽2米水渠长200米宽0.6米",15,13,2,1,52,192,1,7,28,"促进农业发展；改善水利设施；改善居民的生活环境。","促进农业发展；改善水利设施；改善居民的生活环境。"]
[40,"乡村建设行动","人居环境整治","下水道维修","桃林镇","清泉社区","清泉社区临湘二中至上李组下水道维修","改造","清泉社区临湘二中至上李组","4月","7月","清泉社区","临湘二中至上李组下水道维修2000米",28,12,16,1,265,1060,1,6,17,"促进农业发展，提高生态环境保护水平，改善居民的生活环境。","改善人居环境，提升居民幸福感。"]
[41,"乡村建设行动","农村基础设施建设","农村道路建设","桃林镇","清泉社区","清泉社区临湘二中至上李组公路拓宽硬化","改造","二中至清泉社区上李组","4月","7月","清泉社区","二中至清泉社区上李组公路拓宽硬化2公里",36,20,16,1,265,1060,1,6,17,"目标1：方便村民出行，目标2：促进乡村振兴的经济发展","方便村民出行，促进经济发展"]
[42,"乡村建设行动","人居环境整治","下水道维修","桃林镇","清泉社区","清泉社区下街喻家口下水道维修","改造","清泉社区下街喻家口下水道维修","7月","9月","清泉社区居委会","清泉社区下街喻家口下水道维修150米",10,10,0,1,28,72,1,6,17,"促进农业发展，提高生态环境保护水平，改善居民的生活环境。","改善人居环境，提升居民幸福感。"]
[43,"乡村建设行动","农村基础设施建设","农村道路建设","桃林镇","清泉社区","清泉社区栏河坝公路拓宽硬化","改造","清泉社区拦河坝","7月","9月","清泉社区居委会","清泉社区栏河坝公路拓宽硬化180米",22,22,0,1,30,126,1,6,17,"目标1：方便村民出行，目标2：促进乡村振兴的经济发展","方便村民出行，促进经济发展"]
[44,"乡村建设行动","人居环境整治","下水道维修","桃林镇","清泉社区","清泉社区小桥边下水道维修","改造","清泉社区小桥边","2023年9","2023年10","清泉社区居委会","清泉社区小桥边下水道维修280米",30,30,0,1,38,172,1,6,17,"促进农业发展，提高生态环境保护水平，改善居民的生活环境。","改善人居环境，提升居民幸福感。"]
[45,"产业发展","生产项目","种植业","桃林镇","治水村","百兽草种植","产业发展","梓山片区黄土、德兴、陈条组","2023.4.1","2023.5.30","治水村","百兽草种植200亩",60,30,30,1,320,820,1,39,117,"为经济发展提供保障，增加贫困户收入","改善村民就业"]
[46,"产业发展","生产项目","种植业","桃林镇","治水村","紫苏种植","产业发展","凤凰、治水片区","2023.5.2","2023.6.30","治水村","紫苏种植800亩",60,20,40,1,460,960,1,39,117,"为经济发展提供保障，增加贫困户收入","改善村民就业"]
[47,"产业发展","配套设施项目","小型农村水利建设","桃林镇","坪头村","坪头村吴家组水库堤坝维修","堤坝维修","吴家组","2023.3.17","2023.4.6","坪头村委会","长55米，宽5米",8,5,0,1,93,388,1,4,10,"促进农业发展；改善水利设施；改善居民的生活环境。","促进农业发展；改善水利设施；改善居民的生活环境。"]
[48,"产业发展","配套设施项目","小型农村水利建设","桃林镇","坪头村","王家组水库堤坝维修","堤坝维修","王家组","2023.11.10","2023.12.20","坪头村委会","长47米宽5米，高12米",8,6,0,1,52,192,1,3,6,"促进农业发展；改善水利设施；改善居民的生活环境。","促进农业发展；改善水利设施；改善居民的生活环境。"]
[49,"乡村建设行动","农村基础设施","农村道路建设","桃林镇","三合村委会","组级公路白改黑","新建","包王组","4月","5月","三合村委会","长700米，宽4米",20,6,14,1,50,300,1,1,3,"促进农业发展，提高生态环境保护水平，改善居民的生活环境。","改善人居环境，提升居民幸福感。"]
[50,"产业发展","配套设施","水利设施建设","桃林镇","苎麻社区","福寿山茶园灌溉水利建设","新建","苎麻社区福寿山","6月","7月","苎麻社区居委会","福寿山200亩茶园灌溉项目（60立方蓄水池及泵房、水管安装、水井建设等）",62.1521,50,12.1521,1,342,1840,1,16,42,"加快产业发展，发展集体经济；改善茶园水利设施，优化茶园种植条件；增加社区居民及脱贫户收入。","加快产业发展，发展集体经济；改善茶园水利设施，优化茶园种植条件；增加社区居民及脱贫户收入。"]
[51,"产业发展","配套设施","小型农村水利建设","桃林镇","坪上村","仇家组公路硬化","公路硬化","仇家组","3月","8月","坪上村","160米",7,7,0,1,28,119,1,3,9,"促进农业发展；改善水利设施；改善居民的生活环境。","促进农业发展；改善水利设施；改善居民的生活环境。"]
[52,"产业发展","配套设施","小型农村水利建设","桃林镇","坪上村","湾李组排洪渠建设及维修","排洪渠建设及维修","湾李组","3月","8月","坪上村","260米",11,11,0,1,49,255,1,3,9,"促进农业发展；改善水利设施；改善居民的生活环境。","促进农业发展；改善水利设施；改善居民的生活环境。"]
[53,"乡村建设行动","农村基础设施","农村道路建设","桃林镇","东湖村委会","东湖村骆东线公路拓宽硬化","新建","骆坪桥至东湖庙桥2公里拓宽硬化","4月","5月","东湖村村委会","长2000米，宽4米",38,21,17,1,1385,4325,1,25,89,"促进农业发展，提高生态环境保护水平，改善居民的生活环境。","改善人居环境，提升居民幸福感。"]
[54,"乡村建设行动","农村基础设施","农村道路建设","桃林镇","骆坪村村委会","骆坪村大屋组至冲屋组公路拓宽硬化","新建","大屋至冲屋拓宽硬化长600米，宽1米，厚度：0.2米","3月","4月","骆坪村村委会","大屋至冲屋拓宽硬化长600米，宽1米，厚度：0.2",10,7,3,1,97,326,1,3,9,"促进农业发展，提高生态环境保护水平，改善居民的生活环境。","改善人居环境，提升居民幸福感。"]
[55,"产业发展","生产项目","小型农田水利设施建设","桃林镇","横铺村","横铺村山塘维修","维\n修","横铺村细屋组","4月","5月","横铺村民委员会","整修、清淤、堤坝加固",7,5,2,1,31,147,1,1,2,"方便村民农田耕种；使脱贫户增产；促进乡村振兴发展。","方便村民耕种，使村民们增产"]
[56,"乡村建设行动","农村基础设施","农村道路（桥梁）建设","桃林镇","横铺村","横铺村桥梁维修加固","维\n修","横铺村细屋组","4月","5月","横铺村民委员会","维修、加固",13,8,5,1,31,147,1,1,2,"方便村民出行；促进乡村振兴的经济发展","方便村民出行，促进经济发展"]
[57,"农村基础建设","农村环境整治","配套基础设施","五里牌街道","五里牌街道","设备更新","改建","五里牌街道","2023.01","2023.12","五里牌街道","五里牌街道辖区内约1300户垃圾桶更换",10,10,0,10,1300,4109,1,28,93,"通过此项目的建设可以保证约1300户居民的生活垃圾能够得到及时清理","保障社区居民生活垃圾及时清理的需要，提高居民生活质量和幸福指数。"]
[58,"产业发展","生产项目","\n种植业基地","五里牌街道","松峰村","金盆柚基地","新建","松峰村小垅组","2023.03","2023.12","松峰村","150亩",40,10,30,1,903,4500,null,24,60,"此项目实施后可为我村集体经济增收，解决我村经济问题。","解决部分脱贫户与监测户就业问题，提高居民经济收入，达到居民满意度，提高居民的幸福指数。"]
[59,"农村基础建设","农村水利建设","配套基础设施","五里牌街道","鸿鹤社区","山塘整修","改建","鸿鹤社区","2023.05.09","2023.05.20","鸿鹤社区","两口山塘清理淤泥",5,4,1,1,43,289,null,1,3,"此项目实施后可灌溉农田46亩","山塘通过整修，能保证289人农田能够及时得到灌溉，避免因旱情缺水导致农田减产，从而提高农田产量，增加农户收入。"]
[60,"农村基础建设","农村水利建设","配套基础设施","五里牌街道","新庄社区","公路维修","维修","新庄社区次坡组","2023年8月1日","2023年9月1日","新庄社区","拓宽加固100米",5,4,1,1,86,420,1,5,9,"维修拓宽公路达到100米","保障社区居民正常通行及农业生产的需要"]
[61,"农村基础建设","农村水利建设","配套基础设施","五里牌街道","许畈村","山塘整修","改建","许畈村","2023.02","2023.03","许畈村","长塘、杨古塘清淤扩容，加固堤坝",9.2,6,3.2,1,237,648,null,38,38,"此项目实施后可灌溉农田394亩","山塘通过整修，能保证648人农田能够及时得到灌溉，避免因旱情缺水导致农田减产，从而提高农田产量，增加农户收入。"]
[62,"农村基础建设","农村道路建设","配套基础设施","五里牌街道","许畈村","公路拓宽","新建","许上组至柳前组","2023.03","2023.04","许畈村","公路拓宽硬化1.5米及部分路面整体硬化",22,10,12,1,386,1056,null,38,38,"此项目实施后可提高居民出行质量","此路改建好之后可以提高农民的出行质量，达到农民平安出行的满意度，使农民家中的农产品外出销售，从而提高农民收入。"]
[63,"产业发展","生产项目","养植业基地","羊楼司镇","尖山社区","尖山社区养殖业发展","改造","临湘市羊楼司镇尖山社区南一组丹家山","4月","5月","临湘市羊楼司镇尖山社区","承包丹家山水塘12亩，堤坝加固路面硬化60米，溢洪道清淤整修100米，安装立支管一套，鱼苗放养5000斤",8.6,8,0.6,1,1423,3986,1,56,182,"养殖鱼12亩，保障了脱贫户及监测户菜园基地的灌溉，同时发展了村集体经济","流转丹家山水库12亩，带动产业发展。"]
[64,"产业发展","生产项目","养殖业基地","羊楼司镇","双山村","双山村专业养殖","新建","临湘市羊楼司镇双山村铺上组","3月","6月","临湘市羊楼司镇双山村","新增能繁母猪55头，猪栏修缮20格，猪厂内外场地硬化120平，水电线路重装1000米",31,7,24,1,476,1796,1,14,37,"新增能繁母猪55头，出仔猪1000头/年。增加村集体经济收入","流转厂房10亩，带动产业发展和农民增收。"]
[65,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","羊楼司镇","明星村","铺上组塌方公路维修","改造","铺上组","5月","7月","临湘市羊楼司镇明星村","村道路维修35米长18米高",26,5,21,1,30,129,1,3,9,"道路维修，为脱贫户及监测户提供出行安全","道路维修，带动产业发展和农民增收"]
[66,"产业发展","生产项目","种植业基地","羊楼司镇","桃树村","稻油种植发展","基地建设","上、下铺组、坳背组","2月","5月","桃树村","农田改造、基础维护100亩",15,10,5,1,65,275,0,6,14,"种植稻油100亩，增加脱贫户收入","流转土地100亩，带动产业发展合农民增收"]
[67,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","羊楼司镇","梅池村","其家坑水库安全防护档","新建","下梅池组","2023.3.20","2023.4.20","梅池村","护栏全长370米、高1.2米",8.5,8,0.5,1,32,130,0,3,3,"安装防护栏为游客、脱贫户监测户提供游玩、出行安全","安装防护栏带动旅游发展和村民出行安全"]
[68,"产业 发展","生产项目","休闲农业与乡村旅游","羊楼司镇","尖山社区","尖山社区和美乡村示范创建一期","新建","尖山社区","7月","11月","尖山社区","旅游附属设施建设",300,100,200,1,2820,9160,1,30,84,"在社区内建设旅游附属设施，宜居宜业宜游和美乡村","有利于社区及周边居民享受和美乡村的人居环境"]
[69,"产业发展","生产项目","种植业基地","羊楼司镇","黄金村","黄金村黄精种植","新建","临湘市羊楼司镇黄金村大屋组","4月","5月","临湘市羊楼司镇黄金村","种植黄精40亩",30,10,20,1,627,3000,0,19,62,"种植黄精30亩，保障了脱贫户及监测户带动就业，同时发展了村集体经济","流转大屋组土地30亩，带动产业发展。"]
[70,"乡村建设行动","农村基础设施","产业路、资源路建设","羊楼司镇","梧桐铺社区","梧桐铺社区黄土组道路硬化","新建","黄土组","7月","9月","梧桐铺社区","道路硬化长300米，宽4米，高0.2米",11,10,1,1,52,197,0,2,5,"道路硬化，为脱贫户及监测户提供出行安全","道路硬化，带动产业发展和农民增收"]
[71,"产业发展","生产项目","养殖业基地","羊楼司镇","中洲社区","中洲社区鱼塘养殖业发展","改造","中洲社区中洲组花坡","1月","6月","中洲社区","养殖鱼，10亩",10,9,1,1,376,2076,0,5,12,"养殖鱼10亩，可以提高居民生活质量，同时发展了村集体经济","流转中洲组10亩塘，带动产业发展。"]
[72,"乡村建设行动","农村基础设施","产业路、资源路建设","羊楼司镇","柘庄村","柘庄村港南组至周家组破损公路维修","改造","港南组至周家组","6月","7月","柘庄村","村道路维修850米长3.5米宽",25,10,15,1,100,352,0,2,4,"道路维修，为脱贫户及监测户提供出行安全","道路维修，带动产业发展和农民增收"]
[73,"乡村建设行动","农村基础设施","资源路","羊楼司镇","双山村","双山村王家至塘墈道路拓宽硬化","改造","王家组至塘墈组","3月","10月","双山村","村道路拓宽硬化0.9公里",90,10,80,1,74,244,0,2,6,"道路维修，为农户产业发展提供交通便利","道路维修，带动产业发展和农民增收"]
[74,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","詹桥镇","壁山村","詹桥镇2023年壁山村红色旅游基地提质工程","新建","壁山村红色旅游基地","5月","6月","壁山村","壁山村红色旅游基地路面白改黑600米",20,3,17,1,130,620,1,25,85,"推动特色产业发展，打造自主品牌，结合乡村旅游拓展产业链，为居民致富开拓新风向","红色旅游+农户就业相结合"]
[75,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","詹桥镇","壁山村","詹桥镇2023年壁山村红色基地入口提质工程","新建","壁山村红色旅游基地","5月","6月","壁山村","壁山村红色基地入口基础设施建设（坡砌墈高6米，路面400米，宽度2米8驳墈硬化拓宽修整、白改黑、排水沟整修800米）",60,50,10,1,130,620,1,25,85,"推动特色产业发展，打造自主品牌，结合乡村旅游拓展产业链，为居民致富开拓新风向","红色旅游+农户就业相结合"]
[76,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","水泉村","詹桥镇2023年水泉村岭中片道路白改黑","新建","水泉村岭中片","5月","8月","水泉村","水泉村岭中片道路白改黑2105米，宽3.5米",61,15,46,1,134,576,1,28,84,"发展集体经济，带动群众发展产业，为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[77,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","跳石村","詹桥镇2023年跳石村杨畈桥改扩建","新建","跳石村杨畈桥","10月","12月","跳石村","石咀至杨畈组杨畈桥拆旧建新",18,4,14,1,61,234,1,4,16,"为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[78,"产业发展","生产项目","种植业基地","詹桥镇","分水村","詹桥镇2023年分水村抬头片中药材种植基地","新建","分水村抬头片","4月","12月","分水村","抬头片中药材种植30亩",12,6,6,1,123,356,1,12,37,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果","种植基地+农户就业相结合"]
[79,"乡村建设行动","农村基础设施","农村供水保障设施建设","詹桥镇","雁南村","詹桥镇2023年雁南村胡李陆片水利工程","新建","胡家组","5月","7月","雁南村","胡李陆片水利工程提质改造1000米",8,8,0,1,225,728,1,7,28,"基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[80,"乡村建设行动","农村基础设施","农村供水保障设施建设","詹桥镇","泰和社区","詹桥镇2023年泰和社区甘坵组山塘水库整修","新建","泰和社区甘坵组","3月","6月","泰和社区","泰和社区甘坵组山塘水库清淤、砌墈800㎡，山塘堤坝整修、驳墈长38米宽22米、路长215米",18,null,null,1,97,313,1,17,46,"基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[81,"产业发展","配套基础设施项目","小型农田水利设施项目","长安街道","集庄社区","长安街道集庄社区付家组山塘清淤","新建","集庄社区付家组","2023.03.20","2023.04.05","集庄社区","清淤2000方",4,2,2,1,35,185,1,2,8,"通过山塘清淤2000方，解决周边农田灌溉问题，利于增收。","通过山塘清淤，解决周边农田灌溉用水问题，有利于粮食增产，增加老百姓收入"]
[82,"就业项目","就业","技能培训","临湘市","临湘市","致富带头人培训","新建","临湘",2023.1,2023.12,"乡村振兴局","80人",35,35,null,null,80,80,null,80,80,"增强脱贫户发展产业技能，带动群众发展产业，增加群众及贫困户收入","增强脱贫户发展产业技能，带动群众发展产业，增加群众及贫困户收入"]
[83,"乡村建设行动","农村基础设施","小型农田水利设施项目","临湘市","八百村、大和村、松峰村、三港村、沙团村、杨田村、雁峰村、板桥村、汤畈村、大畈村等","小型农业水利设施建设（恢复农村小水源蓄水能力）","改建","除桃矿街道外13个乡镇","2月","12月","水利局","山塘清淤、220座",1121.06,420,701.06,106,1012,3145,11,215,688,"提高山塘蓄水能力","改善实施村灌溉条件、提高农产品种植产量"]
[84,"产业发展","生产项目","种植业基地","临湘市","临湘市","拓展产业扶贫成果重点项目","新建","临湘市","2023年","2023年","农业农村局","种植业基地",300,160,140,6,34,152,2,34,152,"通过“合作社+基地+农户”的模式，实行种植产业发展","鼓励促进脱贫户发展产业积极性，增加脱贫户产业收益防止返贫风险"]
[85,"其他","其他","其他","临湘市","临湘市","村级集体经济发展奖补资金","新建","临湘市","2023.2.8","2023.4.15","组织部","根据相关文件对村级集体经济发展成绩突出的村（社区）和相关单位进行奖补。评选出村级集体经济发展进步村（社区）5个，羊楼司镇如斯村、聂市镇长源村、长塘镇柳厂村、桃林镇苎麻社区、詹桥镇沙团村，每个村奖励3万元；集体经济发展突出村（社区）1个江南镇石岭村，奖励5万元；",600,500,100,11,1324,3819,3,89,360,"评选出村级集体经济发展进步村（社区）5个，集体经济发展突出村（社区）5个，促进集体经济发展先进单位5个，“引老乡、回故乡、建家乡”先进单位3个。希望全市各单位能以先进为榜样，进一步解放思想，创新思路，为建设“三区四市五个新格局”作出新的更大贡献！","项目总投资预算55万元，共对11个村（社区）2个镇（街道）3个企业（合作社）进行奖励。其中受益村11个，受益户数1324户，受益人口3819人。其中受益脱贫村3个，受益脱贫户数及防止返贫监测对象89户，人口360人。"]
["合   计",{"$nulls":12},4743.1227,2630.94,2089.1827,217,29015,103210,61,1781,5306]

{"sheet":"调整","index":1,"n_rows":32,"n_cols":18,"rows_kept":32,"merged":[[2,0,2,17],[3,0,3,2],[3,16,3,17],[4,0,5,0],[4,1,5,1],[4,2,5,2],[4,3,5,3],[4,4,4,6],[4,7,5,7],[4,8,4,9],[4,10,5,10],[4,11,5,11],[4,12,5,12],[4,15,5,15],[4,16,5,16],[4,17,5,17],[6,0,7,0],[6,1,7,1],[6,2,7,2],[6,3,7,3],[6,4,7,4],[6,5,7,5],[6,6,7,6],[8,0,9,0],[8,1,9,1],[8,2,9,2],[8,3,9,3],[8,4,9,4],[8,5,9,5],[8,6,9,6],[10,0,11,0],[10,1,11,1],[10,2,11,2],[10,3,11,3],[10,4,11,4],[10,5,11,5],[10,6,11,6],[12,0,13,0],[12,1,13,1],[12,2,13,2],[12,3,13,3],[12,4,13,4],[12,5,13,5],[12,6,13,6],[14,0,15,0],[14,1,15,1],[14,2,15,2],[14,3,15,3],[14,4,15,4],[14,5,15,5],[14,6,15,6],[16,0,17,0],[16,1,17,1],[16,2,17,2],[16,3,17,3],[16,4,17,4],[16,5,17,5],[16,6,17,6],[18,0,19,0],[18,1,19,1],[18,2,19,2],[18,3,19,3],[18,4,19,4],[18,5,19,5],[18,6,19,6],[20,0,21,0],[20,1,21,1],[20,2,21,2],[20,3,21,3],[20,4,21,4],[20,5,21,5],[20,6,21,6],[22,0,23,0],[22,1,23,1],[22,2,23,2],[22,3,23,3],[22,4,23,4],[22,5,23,5],[22,6,23,6],[24,0,25,0],[24,1,25,1],[24,2,25,2],[24,3,25,3],[24,4,25,4],[24,5,25,5],[24,6,25,6],[26,0,27,0],[26,1,27,1],[26,2,27,2],[26,3,27,3],[26,4,27,4],[26,5,27,5],[26,6,27,6],[28,0,29,0],[28,1,29,1],[28,2,29,2],[28,3,29,3],[28,4,29,4],[28,5,29,5],[28,6,29,6],[30,0,31,0],[30,1,31,1],[30,2,31,2],[30,3,31,3],[30,4,31,4],[30,5,31,5],[30,6,31,6]],"flags":["formulas_cached_only"]}
[]
[]
["临湘市巩固拓展脱贫攻坚成果和乡村振兴项目库动态调整项目申报表\n (入库项目关键信息调整)"]
["单位：（盖章）",{"$nulls":15},"时间：2023年3月"]
["序号","乡","村","项目名 称","项目类别",null,null,"实施地点","时间进度",null,"责任单 位","建设内容及规模","项目预算总投资( 万 元)","其中",null,"绩效目标","联农带农机制","备注"]
[{"$nulls":4},"项目类型","二级项目类型","项目子 类型",null,"计划开工时间","计划完工时间",{"$nulls":3},"财政资金(万 元)","其他资金(万 元)"]
[1,"聂市镇",null,"聂市镇公益性岗位","公益性岗位","公益性岗位","公益性岗位","聂市镇","2023年","2023年","聂市镇","建设公益性岗位110个",33,33,0,"全镇范围内实施公益性岗位，受益脱贫户及监测户脱贫户632户1869人","全镇范围内实施公益性岗位，解决脱贫人口及监测户就业难问题，巩固脱贫成果。","调整前"]
[{"$nulls":7},"聂市镇","4月","5月","聂市镇","建设公益性岗位96个",50,38.4,11.6,"全镇范围内建设公益性岗位96个","全镇范围内实施公益性岗位，解决脱贫人口及监测户就业难问题，巩固脱贫成果。","调整后"]
[2,"桃林镇","桃林镇","桃林镇160户脱贫户及30户监测户产业奖补/桃林镇2023年产业奖补","产业发 展","生产项 目","种养植业 发展","桃林镇","2023年2","2023-04-01","桃林镇","辖区18个村到户类产业发展",17,17,0,"帮助脱贫户及监测户发展产业；带动产业发展，帮助脱贫户及监测户创收。","帮助脱贫户及监测户发展产业；带动产业发展，帮助脱贫户及监测户创收。","调整前"]
[{"$nulls":7},"桃林镇","2023.4.1","2023.5.20","桃林镇","桃林镇辖区207户脱贫户及29户监测户发展种、养殖业",14.08,14.08,0,"帮助全镇207户脱贫户29户监测户发展产业，带动产业发展，帮助脱贫户及监测户创收。","帮助脱贫户及监测户发展产业；带动产业发展，帮助脱贫户及监测户创收。","调整后"]
[3,"桃林镇","桃林镇","桃林镇公益性岗位","就业项目","公益向岗位","就业帮扶","桃林镇","1月","12月","桃林镇","辖区18个村54个公益性岗位",16.2,16.2,0,"帮助桃林镇辖区脱贫户及监测户解决就业；巩固脱贫攻坚同乡村振兴有效衔接","帮助桃林镇辖区脱贫户及监测户解决就业；巩固脱贫攻坚同乡村振兴有效衔接","调整前"]
[{"$nulls":7},"桃林镇","1月","12月","桃林镇","全镇辖区40个公益性岗位",24,16,8,"帮助桃林镇辖区脱贫户及监测户解决就业；巩固脱贫攻坚同乡村振兴有效衔接","帮助桃林镇辖区脱贫户及监测户解决就业；巩固脱贫攻坚同乡村振兴有效衔接","调整后"]
[4,"坦渡镇","坦渡镇","坦渡镇公益性岗位","就业项目","公益性岗位","公益性岗位","坦渡镇","2023-01-01","2023-12-01","坦渡镇人民政府","30个公益性岗位补贴发放",9,9,0,"直接帮扶，提升脱贫户与监测户增加务工收入。","让参加公益性岗位的脱贫户和监测户务工收入增加3000元以上，从而巩固脱贫成效。","调整前"]
[{"$nulls":7},"坦渡镇","2023-01-01","2023-12-01","坦渡镇人民政府","42个公益性岗位补贴发放",39.048,16.8,22.248,"直接帮扶，提升脱贫户与监测户增加务工收入。","让参加公益性岗位的脱贫户和监测户务工收入增加4000元以上，从而巩固脱贫成效。","调整后"]
[5,"白羊田镇","白羊田镇","白羊田镇公益岗位奖补","就业项目","公益性岗位","公益性岗位奖补","白羊田镇",2023.01,2023.12,"白羊田镇","奖补脱贫户、监测户公益性岗位",16.5,16.5,0,"帮助脱贫户、监测户就近就地就业，促进受益户稳定增收，防范返贫致贫风险。","提供就业机会，促进农户自主致富，提高经济收入。","调整前"]
[{"$nulls":7},"白羊田镇",2023.01,2023.12,"白羊田镇","奖补脱贫户、监测户公益性岗位",28.4,19.2,9.2,"帮助脱贫户、监测户就近就地就业，促进受益户稳定增收，防范返贫致贫风险。","提供就业机会，促进农户自主致富，提高经济收入。","调整后"]
[6,"詹桥镇","詹桥镇","2023年詹桥镇公益岗位","就业项目","公益性岗位","公益性岗位","詹桥镇","2023-01-01","2023-12-31","詹桥镇","鼓励聘用脱贫户务工",13.5,null,null,"为群众及脱贫户提供就业机会，带动增收致富","农户就业","调整前"]
[{"$nulls":7},"詹桥镇","2023-01-01","2023-12-31","詹桥镇","鼓励聘用脱贫户务工",22.2,null,null,"为群众及脱贫户提供就业机会，带动增收致富","农户就业","调整后"]
[7,"江南镇","鸭栏村","沟渠清淤、疏浚","产业发展项目","配套基础设施项目","小型农田水利设施建设","鸭栏村",2023.03,2023.04,"鸭栏村委会\n","沟渠清淤、疏浚7.1万m³",30.5,25,5.5,"方便农田灌溉","方便农田灌溉，提高农户及脱贫户的农田种植收入。","调整前"]
[{"$nulls":7},"鸭栏村",2023.03,2023.04,"鸭栏村委会\n","沟渠清淤、疏浚2.4万m³",10.2,5,5.2,"方便农田灌溉","方便农田灌溉，提高农户及脱贫户的农田种植收入。","调整后"]
[8,"江南镇","江南村","江南村七组机耕桥维修","产业发展项目","配套基础设施项目","小型农田水利设施建设","江南村七组",2023.05,2023.06,"江南镇","宽3.5米，长6米",6,5,1,"改善村民生产出行运输安全状况；方便防汛期间排渍；方便村民农田灌溉。","改善村民生产出行运输安全状况；方便防汛期间排渍；方便村民农田灌溉，提高农户及脱贫户的农田种植收入。","调整前"]
[{"$nulls":7},"江南村七组",2023.05,2023.07,"江南镇","宽4.5米，长7米",20,6,14,"改善村民生产出行运输安全状况；方便防汛期间排渍；方便村民农田灌溉。","改善村民生产出行运输安全状况；方便防汛期间排渍；方便村民农田灌溉，提高农户及脱贫户的农田种植收入。","调整后"]
[9,"长安街道","荆竹山村","长安街道荆竹山村李家组农田灌溉渠道硬化","产业发展项目","配套基础设施项目","小型农田水利设施建设","荆竹山村李家组",2023.05,2023.06,"长安街道","清理渠道内的淤泥100方，硬化渠道内的底板",8,5,3,"方便农田灌溉","方便农田灌溉，提高农户及脱贫户的农田种植收入。","调整前"]
[{"$nulls":7},"荆竹山村李家组",2023.05,2023.06,"长安街道","清理渠道内的淤泥100方，两边驳岸砌石共300米，硬化渠道内的底板",8,3,5,"方便农田灌溉","方便农田灌溉，提高农户及脱贫户的农田种植收入。","调整后"]
[10,"长塘镇","长塘镇","长塘镇2023年公益岗位","就业项目","公益性岗位奖补","公益性岗位奖补","长塘镇","2023.01.01","2023.12.31","长塘镇政府","公益性岗位奖补",9.6,9.6,0,"提升脱贫户生活质量，巩固脱贫攻坚成果，提高脱贫户收入","用于鼓励脱贫户监测户自力更生，做保洁员等公益性岗位奖补，保证收入问题。","调整前"]
[{"$nulls":7},"长塘镇","2023.01.01","2023.12.31","长塘镇政府","公益性岗位奖补",20,11.2,8.8,"提升脱贫户生活质量，巩固脱贫攻坚成果，提高脱贫户收入","用于鼓励脱贫户监测户自力更生，做保洁员等公益性岗位奖补，保证收入问题。","调整后"]
[11,"忠防镇","忠防镇","忠防镇2023年公益岗位","就业项目","公益性岗位奖补","公益性岗位奖补","忠防镇",2023.01,2023.12,"忠防镇政府","公益性岗位奖补",9.6,9.6,0,"用于鼓励脱贫户监测户自力更生，做保洁员等公益性岗位奖补，保证收入问题。","用于鼓励脱贫户监测户自力更生，做保洁员等公益性岗位奖补，保证收入问题。","调整前"]
[{"$nulls":7},"忠防镇",2023.01,2023.12,"忠防镇政府","公益性岗位奖补",16.5,16.5,0,"用于鼓励脱贫户监测户自力更生，做保洁员等公益性岗位奖补，保证收入问题。","用于鼓励脱贫户监测户自力更生，做保洁员等公益性岗位奖补，保证收入问题。","调整后"]
[12,"羊楼司镇","石壁村","有机稻油基地扩面100亩","产业发展","生产项目","种植业基地","羊楼司镇石壁村莲花组、何家组","2023-01-01","2023-07-01","临湘市羊楼司镇石壁村","100亩稻油基地提质改造",20,18,2,"为脱贫户及监测户提供就业岗位，增加收入","流转土地39亩，带动产业发展和农民就业增收","调整前"]
[{"$nulls":7},"羊楼司镇石壁村莲花组、何家组","2023-01-01","2023-07-01","临湘市羊楼司镇石壁村","机耕道1000米，山塘修复1口，荒田改造60亩",20,18,2,"为脱贫户及监测户提供就业岗位，增加收入","流转土地39亩，带动产业发展和农民就业增收","调整后"]
[13,"羊楼司镇","三港村","生态农庄","产业发展","生产项目","种植业基地","羊楼司镇三港村细港组","2023-04-01","2023-10-01","临湘市羊楼司镇三港村","建设\n民宿及农庄",80,70,10,"建设民宿及农庄，增加集体经济收入，发展农民就业增收","建设民宿及农庄，增加集体经济收入，发展农民就业增收","调整前"]
[{"$nulls":7},"羊楼司镇三港村细港组","2023-05-01","2023-06-01","临湘市羊楼司镇三港村","农庄产业路拓宽1.5米",40,30,10,"建设农庄产业路，有利于增加集体经济收入，发展农民就业增收","建设农庄产业路，有利于增加集体经济收入，发展农民就业增收","调整后"]

{"sheet":"Sheet3","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"flags":["formulas_cached_only"]}