{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["1"],"not_rendered":{"defined_names":2},"read":"whole","date_system":"1900"}

{"sheet":"1","index":0,"n_rows":323,"n_cols":8,"rows_kept":323,"merged":[[0,0,0,7],[1,0,2,0],[1,1,2,1],[1,2,2,2],[1,3,2,3],[1,4,2,4],[1,5,1,6],[1,7,2,7],[35,0,36,0],[35,1,36,1],[35,2,36,2],[35,3,36,3],[35,5,36,5],[35,7,36,7],[322,0,322,2]]}
["临湘市2024年衔接资金项目计划完成情况公示表"]
["序号","主管单位","项目设施单位","项目名称","完成情况","资金使用情况(单位：万元）",null,"绩效目标、减贫机制实现情况"]
[{"$nulls":5},"项目总额","其中：衔接资金"]
[1,"临湘市农业农村局","临湘市农业农村局","岳阳市临湘市忠防镇等四个乡镇木形村等九个村高标准农田建设项目(二〇二四年)","已完工",{"v":1172,"d":"1172.00"},{"v":1172,"d":"1172.00"},"1：进出平衡地块耕地恢复28.87亩。\n 2：完成山塘整治11座。\n 3：完成修筑机耕路56条。"]
[2,"临湘市农业农村局","临湘市农业农村局","新型农业经营主体贷款贴息资金","已完工",{"v":231,"d":"231.00"},231,"减轻全市新型农业经营主体融资成本负担"]
[3,"临湘市农业农村局","临湘市茶业有限责任公司、湖南韩桥农业科技有限公司、临湘市马家洞油茶种植专业合作、临湘市陡岭洞茶叶专业合作社 ","2024年省帮扶产业发展重点项目","已完工",{"v":212,"d":"212.00"},212,"通过产业直接帮扶或吸纳务工就业方式计划新带动脱贫人口数量纳入项目绩效管理，企业通过直接帮扶模式、专业合作社通过直接帮扶模式带动。"]
[4,"临湘市农业农村局","临湘市农业农村局","县域经济创新进位奖","已完工",{"v":500,"d":"500.00"},200," 1:对脱贫户进行产业帮扶，提升脱贫户发展特色产业的积极性。\n2：对脱贫户开展送种苗、技术指导、保底回收、劳动务工、土地流转等帮扶措施。\n 3：增加脱贫户（监测户）的产业收益，使监测户人均增加300元/户的收入，防止返贫风险。"]
[5,"临湘市水利局","临湘市水利局","2024年忠防镇木形片区集中供水工程","已完工",{"v":400,"d":"400.00"},400,"新建供水规模960立方/天小型集中供水工程1处，受益人口月2164人。"]
[6,"临湘市水利局","临湘市水利工程建设项目管理中心","国债配套水利项目","已完工",406.03,406.03,"新增灌溉面积1.59万亩，年节水量185万立方米，粮食增产42万公斤，达到节水增产的效益"]
[7,"临湘市水利局","临湘市水利工程建设项目管理中心","“引团济龙”引调水项目前期经费","已完工",{"v":200,"d":"200.00"},200,"解决临湘市城区20万人用水安全和16.8万亩农田灌溉。"]
[8,"临湘市水利局","项目建设相关\n村（社区）","临湘市2024年小型农业水利设施建设","已完工",{"v":840,"d":"840.00"},840,"提高山塘蓄水能力"]
[9,"临湘市农业农村局","临湘市相关各镇（街道）、村（社区）、涉农小三场","临湘市保洁设施改造升级及支持村级产业发展","已完工",{"v":450,"d":"450.00"},200,"农村人居环境得到了大幅度提升，美丽乡村建设稳步推进。"]
[10,"临湘市农业农村局","各镇、街道","临湘市2024年农村厕改化粪池政府采购项目","已完工",{"v":1080,"d":"1080.00"},420,"完成户厕建设1320户，公村公厕建设6座"]
[11,"临湘市农业农村局","中山湖渔场","大湖直堤加固维修","已完工",{"v":35,"d":"35.00"},20,"大湖直堤900米进行维修，用土方加宽加固，达到不使内垸2100亩水田受淹。"]
[12,"临湘市农业农村局","横河堤养殖场","新发组道路硬化","已完工",{"v":26.5,"d":"26.50"},10,"硬化道路486米，解决320亩农田生产运输困难问题"]
[13,"临湘市农业农村局","白沙洲畜牧良种场","龙虾池平整旱地","已完工",{"v":26,"d":"26.00"},20,"内垸龙虾池50亩平整为旱地"]
[14,"临湘市农业农村局","白沙洲畜牧良种场","渠道清淤","已完工",{"v":12,"d":"12.00"},10,"垸内6条沟渠需清理"]
[15,"临湘市农业农村局","新建渔场","王家、张山两组道路硬化工程","已完工",{"v":17,"d":"17.00"},10,"对王家、张山两组道路硬化470米，宽3米，预算资金17万元，解决本场和周边村270亩农田生产运输困难问题。"]
[16,"临湘市农业农村局","种猪种鸡场","谭家桥桥梁维修","已完工",5.86,5,"谭家桥加装安全防护栏，连接桥梁路面维修"]
[17,"临湘市农业农村局","市农业农村局","雨露计划","已完工",{"v":140.2,"d":"140.20"},140.2,"脱贫户（包括监测户）的子女就读职业高等学院补助1500/学期"]
[18,"临湘市农业农村局","市农业农村局","一次性交通补贴、帮扶车间","已完工",102.86,102.86,"在外务工脱贫户一次性交通补贴，提供就业的扶贫车间补助"]
[19,"临湘市农业农村局","市农业农村局","小额信贷贴息","已完工",{"v":200,"d":"200.00"},77.2,"脱贫户（包括监测户）小额信贷贴息"]
[20,"临湘市农业农村局","聂市镇乘岭社区，桃林镇骆平村","设施农业建设","已完工",{"v":148,"d":"148.00"},111,"260亩水肥一体化喷淋滴灌网（棚外）及配套设施，新建鸡舍大棚1700平方米，蛋鸡智能化养殖设备1套"]
[21,"临湘市农业农村局","临湘市农业农村局","2024年粮食生产奖补","已完工",{"v":500,"d":"500.00"},300,"通过该项目一是稳定和增加粮食生产面积，增加粮食产量；二是新型经营主体和龙头企业发挥带动作用；三是鼓励、促进脱贫户种植的积极性，四是增加脱贫户种植收益，防止返贫风险。"]
[22,"临湘市农业农村局","临湘市长塘镇托坝社区集体经济合作社，临湘市长塘镇长塘社区集体经济合作社，临湘市万众种植专业合作社，临湘市召丰水稻种植专业合作社，绿野星辰山野菜专业合作社","临湘市农产品产地冷藏保鲜设施建设","已完工",{"v":197,"d":"197.00"},197,"建设4座不同类型冷库，带动周边群众就业"]
[23,"临湘市农业农村局","临湘市农业农村局","集中育秧设施建设","已完工",{"v":300,"d":"300.00"},100,"提供优良，高产的水稻秧苗确保粮食产量的增加，种植收益的增加"]
[24,"市组织部","各实施村","临湘市2024年发展村级集体经济项目","已完工",{"v":500,"d":"500.00"},300,"一般村集体经济收入达10万元以上，力争产业强劲村村级集体经济收入达50万元及以上。并充分带动周边群众就业增收及巩固脱贫成果。"]
[25,"市组织部","市组织部","2024年集体经济奖补","已完工",{"v":30,"d":"30.00"},30,"力争产业强劲村村级集体经济收入达50万元及以上。并充分带动周边群众就业增收及巩固脱贫成果"]
[26,"市农业农村局","市农业农村局","优势百亿产业以奖代投","已完工",{"v":30,"d":"30.00"},20,"1:对脱贫户进行产业帮扶，提升脱贫户发展百亿优势特色产业的积极性。2：增加脱贫户（监测户）的产业收益，使监测户人均增加300元/户的收入，防止返贫风险"]
[27,"临湘市农业农村局","万众种植、正阳水稻、鸭栏水稻种植、鼎顺水稻、勇敢水稻种植专业合作社","岳阳市市级示范社\n重点培育项目","已完工",{"v":19,"d":"19.00"},19,"帮助提升运营质量、强化服务带动能力，进一步促进高质量发展"]
[28,"临湘市林业局","临湘市药菇山国有林场","临湘市药菇山国有林场2024年欠发达国有林场巩固提升项目-中药著培育项目","已完工",{"v":83.6,"d":"83.60"},60,"中药材培育100亩"]
[29,"临湘市林业局","临湘市荆竹山国有林场","临湘市荆竹山国有林场2024年欠发达国有林场巩固提升资金-苗圃建设项目","已完工",{"v":120,"d":"120.00"},100,"建成具有林场特色的苗木基地，满足林场植树造林的需要，提升林场造林质量，降低苗木成本，提高造林成活率。"]
[30,"临湘市民宗局","龙窖山村、双山村、长源村、源冲村、长塘社区、柳厂村、余湾村、壁山村、长浩村9个村（社区）","临湘市茶园低氟改造边销茶原料降氟项目","已完工",{"v":250,"d":"250.00"},120,"带动周边群众就业保障、3年后丰产每后增加低氟黑毛茶原料供应67吨"]
[31,"长安街道","长安街道","长安街道2024年庭院经济产业奖补","已完工",{"v":4.2,"d":"4.20"},4.2,"65户脱贫户及监测户发展庭院经济"]
[32,"长安街道","长安街道","公益岗位","已完工",{"v":8.8,"d":"8.80"},8.8,"22人参加公益岗位"]
[33,"长安街道","杨田村","杨田村刘家组组级道路硬化","已完工",{"v":10.535,"d":"10.54"},7,"组级公路硬化350米"]
[{"$nulls":4},"已完工",null,2]
["34","长安街道","杨田村","杨田村新屋组至香木组道路维修。","已完工",{"v":3,"d":"3.00"},3,"道路维修550米"]
["35","长安街道","杨田村","杨田村灾后重建","已完工",{"v":73.3538,"d":"73.35"},70,"下山桥拓宽维修，水沟重建及驳岸，清运山体滑坡土石方。"]
["36","长安街道","荆竹山村","荆竹山村刘家组集中建房点连接路拓宽硬化","已完工",12.65,5,"路面拓宽硬化200米，路肩护坡，排水沟修建。"]
["37","长安街道","集庄社区","长安街道集庄社区堰坝整修","已完工",{"v":5,"d":"5.00"},5,"清淤1000方，驳岸300方。"]
["38","黄盖镇人民政府","黄盖镇","黄盖镇高标准蔬菜育苗大棚建设","已完工",365,365,"完成对博特利养殖场进行拆除改造，土壤重构40亩，建设立体化蔬菜与集中育秧大棚 35亩，建设道路 600米，修建沟渠 2000米改造供电设施 3000 米，修建供水机埠 1座，购置育苗大棚配套设施，带动群众发展产业。"]
["39","黄盖镇人民政府","黄盖镇","黄盖镇庭院经济奖补","已完工",4.32,4.32,"对全镇发展产业的农户按标准进行奖补，提高农户种养殖热情，增加经济收入。"]
["40","黄盖镇人民政府","团山社区","黄盖镇团山社区农产品仓储冷链物流","已完工",5.409,3,"完成41亩鲜食玉米种植"]
["41","黄盖镇人民政府","黄盖镇","黄盖镇公益岗位奖补","已完工",2.4,2.4,"为脱贫户、监测户提供就业机会，稳定增收，减少返贫致贫风险。"]
["42","黄盖镇人民政府","合兴村","黄盖镇合兴村胜利组沟渠清淤","已完工",14.31,5,"完成合兴村胜利组沟渠清淤，增强农田排灌能力，改善水利条件，提高农业综合生产能力"]
["43","黄盖镇人民政府","合兴村","黄盖镇合兴村南湖组道路硬化","已完工",24.8857,21,"完成南湖组组级道路硬化896米左右，改善村民生产生活条件。"]
["44","黄盖镇人民政府","广坪村","黄盖镇广坪村广坪组、清水潭组、红旗组、前进组沟渠清淤","已完工",20.916,7,"完成广坪村多组沟渠清淤，增强农田排灌能力，改善水利条件，提高农业综合生产能力"]
["45","黄盖镇人民政府","黄盖湖村","黄盖镇黄盖湖村将军组机耕路维修","已完工",6.834,6.5,"完成将军组组级道路硬化1680米，改善村民生产生活条件。"]
["46","黄盖镇人民政府","黄盖湖村","黄盖镇黄盖湖村友谊组机耕路维修","已完工",11.76,9.5,"完成友谊组组级道路硬化，改善村民生产生活条件。"]
["47","黄盖镇人民政府","黄盖镇","黄盖镇机埠维修及防汛抗旱管道、水泥沟恢复","已完工",25.0736,25,"通过机埠维修、防汛抗旱管道及水泥沟恢复，保证黄盖各村社区农户农田的正常生产用水"]
["48","聂市镇政府","聂市镇黄盖村","黄盖村防汛","已完工",17.93,15,"土咀垸、余桥垸、高桥垸易损地段加固及灾后修复，方便群众发展农业生产及保障群众生命财产安全。该项目改良3200亩农田灌溉条件，涉及农户368户，1154人，脱贫户12户36人"]
["49","聂市镇政府","聂市镇长源村","沟渠修复gouquxf","已完工",8,8,"改善老百姓生产条件，提高老百姓收入"]
["50","聂市镇政府","聂市镇同德村","2024年同德垸水面生态养殖项目二期","已完工",55,12,"巩固脱贫成效，壮大集体经济，吸收脱贫劳动力就业，该项目涉及农户1213户5119人，其中脱贫户52户185人。"]
["51","聂市镇政府","聂市镇马垅村","叶桥垸水面生态养殖","已完工",25,20,"巩固脱贫成效，壮大集体经济年收入约40万元，吸收脱贫劳动力就业，该项目涉及农户753户3164人，其中脱贫户40户123人。"]
["52","聂市镇政府","聂市镇官田村","旭畈组至枫林路基拓宽","已完工",4,3,"改善农村产业发展条件增加农民收入，该项目涉及农户740户2900人，其中脱贫户64户184人。"]
["53","聂市镇政府","聂市镇红士村","老冲组水毁工路驳岸","已完工",4.3,3,"方便群众出行以及发展农业生产。该项目涉及农户28户132人，其中脱贫户2户4人。"]
["54","聂市镇政府","聂市镇同合村","同合村碾槽组至胡家组通组公路硬化","已完工",55,28,"此路打通后将能有效改善聂坳片4个组交通运输环境，能有效解决村民出行方便及助力乡村振兴集体经济发展，该项目涉及农户103户，401人，其中脱贫户19户63人"]
["55","聂市镇政府","聂市镇三和村","源潭桥至三和村部公路拓宽","已完工",68,25,"便于脱贫劳动力和群众出行，方便群众发展产业。该项目涉及农户300户1150人，其中脱贫户8户27人"]
["56","聂市镇政府","聂市镇朱圣村","朱圣村杨梅组周家冲公路硬化","已完工",20,10,"方便本组及周边群众出行，发展特色产业，带动地方经济发展"]
["57","聂市镇政府","聂市镇同合村","同合村同梓岭山塘清淤、埋设涵管及浆彻石","已完工",35,10,"山塘清淤及浆彻石埋设涵管能有效防止道路塌陷及4个组的稻田灌溉，提高贫困户增产增收。"]
["58","聂市镇政府","聂市镇乘岭社区","高效农业大棚建设","已完工",{"v":160,"d":"160.00"},155,"推动社区高效农业发展，提高社区集体经济收入"]
["59","聂市镇政府","聂市镇乘风村","群英、团结组排洪沟浆砌石建设","已完工",18,9,"巩固脱贫成效，壮大集体经济该项目涉及农户110户485人，其中脱贫户9户30人"]
["60","聂市镇政府","聂市镇凤形村","四座山塘整修","已完工",10,8,"山塘维修可有效灌溉农田作物，群众用水，稳固脱贫成效。该项目涉及农户186户860人，其中脱贫户4户9人"]
["61","聂市镇政府","聂市镇官田村","官田畈至铁坳组道路拓宽硬化","已完工",63,7,"加强乡村建设，改善脱贫户及居民周边环境，巩固脱贫成果。"]
["62","聂市镇政府","聂市镇红士村","红士村曾门，上屋，下屋，谢门组组级公路维修、增加会车道。","已完工",11,5,"加强乡村建设，改善脱贫户及居民农业生产发展，巩固脱贫成果。"]
["63","聂市镇政府","聂市镇黄盖村","玉米转基因实验基地","已完工",12,4,"解决周边群众就业问题。"]
["64","聂市镇政府","聂市镇马垅村","梅树组特色产业路","已完工",25,5,"方便本组及周边群众出行，发展特色产业，带动地方经济发展"]
["65","聂市镇政府","聂市镇汤畈村","何家二组山塘驳岸清淤","已完工",30,10,"加强基础建设，为产业发展提供条件，增加群众收入。该项目涉及农户30户，145人，脱贫户3户6人，"]
["66","聂市镇政府","聂市镇沿河社区","山塘整修","已完工",7,5,"该项目涉及农户112户，379人；其中脱贫户4户15人，解决农户田地用水问题，巩固脱贫成效。"]
["67","聂市镇政府","聂市镇源潭社区","岔街道路提质改造","已完工",26,6,"方便各组及周边群众出行，带动地方经济发展。该项目涉及农户72户，350人，其中脱贫户2户6人"]
["68","聂市镇政府","聂市镇长源村","长源村新长源垸水面生态养殖项目","已完工",30,3,"解决脱贫及监测户劳动就业，增加脱贫及监测户经济收入."]
["69","聂市镇政府","聂市镇","公益性岗位","已完工",40,38.8,"全镇范围内实施公益性岗位，受益脱贫户及监测户脱贫户632户1869人"]
["70","聂市镇政府","聂市镇","2024年聂市镇产业奖补","已完工",26.52,26.52,"全镇范围内实施产业奖补，受益脱贫户及监测户脱贫户629户1864人"]
["71","聂市镇政府","聂市镇长源村","长源村防汛","已完工",{"v":22,"d":"22.00"},18,"新长源垸及九成撇洪渠、叶家桥撇洪渠易损地段加固及灾后修复，方便群众发展农业生产及保障群众生命财产安全。该项目改良4000亩农田灌溉条件，涉及农户598户，21514人，脱贫户17户36人"]
["72","聂市镇政府","聂市镇同德村","同德村防汛","已完工",{"v":70,"d":"70.00"},20,"同德垸堤垸及撇洪渠易损地段加固及灾后修复，改良下游农田灌溉条件1100亩，方便群众发展农业生产及保障群众生命财产安全。该项目涉及农户398户，1194人，脱贫户17户36人。"]
["73","聂市镇政府","聂市镇新安村","孙坳组、虎形组机耕路修建","已完工",8,7,"修建孙坳组至虎形组长3000米，宽3.5米机耕路，改善农业生产条件，稳固脱贫成效。该项目涉及农户85户325人，其中脱贫户5户10人"]
["74","聂市镇政府","聂市镇权桥村","下卢组汛期水毁桥梁修复","已完工",8,2,"水毁桥梁修复恢复可有效灌溉农田作物，稳固脱贫成效。该项目涉及农户152户690人，其中脱贫户5户16人"]
["75","聂市镇政府","聂市镇马垅村","沈上至乘石路连接路","已完工",30,3,"方便群众出行以及发展农业生产。该项目涉及农户254户951人，其中脱贫户12户42人。"]
["76","聂市镇政府","聂市镇同德村","新建组组级公路硬化工程项目","已完工",18,10,"改善农村道路基础设施建设，增加农民收入，该项目涉及农户238户1256人，其中脱贫户12户39人。"]
["77","聂市镇政府","聂市镇同德村","王家组山塘整修","已完工",3,2,"王家组山塘面积10亩，部分清淤，堤翻新加固，地管30米新做，改善灌溉面积450亩，涉及农户90户，390人，脱贫户1户2人。"]
["78","聂市镇政府","聂市镇汤畈村","临观组山塘驳岸清淤","已完工",8,5,"方便群众发展农业生产。该项目涉及农户38户152人，其中脱贫户12户4人。"]
["79","羊楼司镇","尖山社区","和美乡村示范创建二期四季果园建设","已完工",{"v":157.6,"d":"157.60"},143,"通过此项目实施发展了社区集体经济，打造了社区旅游观光景点，"]
["80","羊楼司镇","尖山社区","易地搬迁后扶羊楼司镇尖山社区竹情安置小区基础设施维护2024","已完工",{"v":37,"d":"37.00"},14,"通过此项目实施预防了因天灾带来的安全隐患和经济损失，改善了安置户的人居环境。"]
["81","羊楼司镇","三港村","中药材种植","已完工",{"v":19,"d":"19.000"},7,"三港村付家组中药材种植菖蒲10亩、黄精5亩，合计15亩，增加村集体经济，同时带动脱贫、监测户务工增收"]
["82","羊楼司镇","三港村","中药材种植后续管理","已完工",3.082,3,"三港村付家组中药材种植菖蒲10亩、黄精5亩，白芨11亩，合计26亩后续的管，增加村集体经济，同时带动脱贫、监测户务工增收"]
["83","羊楼司镇","龙窖山村","龙窖山村乡村旅游特色露营基地第一期","已完工",{"v":2.4,"d":"2.400"},2,"完善乡村旅游基础设施建设，促进产业发展，解决剩余劳力就业、增加脱贫（监测）户经济收入"]
["84","羊楼司镇","龙窖山村","山洪地质灾害水毁恢复","已完工",{"v":10,"d":"10.00"},10,"完善乡村基础设施建设，促进产业发展，解决剩余劳力就业、增加脱贫（监测）户经济收入"]
["85","羊楼司镇","如斯村","板粟园抚育施肥","已完工",{"v":9.36,"d":"9.360"},3,"4年丰产后，预计年增加村集体经济收9万元"]
["86","羊楼司镇","金鸡社区","金鸡社区八月蛋种植基地","已完工",5.218,2,"为脱贫户提供就业岗位，增加收入"]
["87","羊楼司镇","梅池村","梅池村公路拓宽","已完工",{"v":21,"d":"21.000"},5,"梅池村公路拓宽发展村集体经济，发展旅游产业，同时带动脱贫人口和群众务工增收"]
["88","羊楼司镇","文白社区","文白社区\n港渠护砌\n2024","已完工",14.473,5,"赵家组港渠护砌200米，减少洪涝灾害，确保下游居民生命财产安全。"]
["89","羊楼司镇","文白社区","文白社区挖沟清淤2024","已完工",{"v":5.12,"d":"5.120"},3,"挖沟清淤174米确保辖区部分居民方便出行，改善人居环境"]
["90","羊楼司镇","新屋村","新屋村道路整修","已完工",9.64,8,"全年完成2公里公路的维护整修，同时带动4人脱贫人口和监测群众务工增收，"]
["91","羊楼司镇","新屋村","新屋村栗楠至梁家组公路整修","已完工",{"v":6,"d":"6.00"},5,"全年完成1.5千米公路整修，路基拓宽2.5米，同时带动4人脱贫人口和监测群众务工增收"]
["92","羊楼司镇","黄沙村","黄沙村入户断头路硬化","已完工",{"v":7.92,"d":"7.920"},5,"项目总投入7.92万元，通过改善交通条件，促进农村产业的发展，增加群众收入 ，全村脱贫户6户20人受益"]
["93","羊楼司镇","黄沙村","黄沙村入户断头路硬化花屋组","已完工",{"v":12.1,"d":"12.10"},7,"项目总投入12.5万元，通过改善交通条件，促进农村产业的发展，增加群众收入 ，全村脱贫户5户18人受益"]
["94","羊楼司镇","羊楼司镇","羊楼司镇2024年庭院经济","已完工",18.08,18.08,"通过帮扶产业，增加收入。"]
["95","羊楼司镇","柘庄村","油茶种植","已完工",{"v":16,"d":"16.000"},5,"种植油茶60亩，为脱贫户及监测户提供就业岗位，增加收入。"]
["96","羊楼司镇","石壁村","石壁村稻再油示范基地建设","已完工",{"v":3.64,"d":"3.640"},3,"再生稻及油菜种植100亩增加脱贫户及村民收入"]
["97","羊楼司镇","石壁村","石壁村双季稻种植基地提质改造","已完工",{"v":17.8,"d":"17.800"},10,"保障农田生产、增产增收，为脱贫户及监测户提供就业岗位，增加收入"]
["98","羊楼司镇","石壁村","东头至水桶路基拓宽","已完工",3.998,3,"建设村庄、便利出行、\n有利资源进出、增加群\n众收入"]
["99","羊楼司镇","雅团村","粮食生产（二期","已完工",16.338,4,"为脱贫户及监测户提供就业岗位，增加收入"]
["100","羊楼司镇","雅团村","水利堰坝整修","已完工",{"v":8.08,"d":"8.080"},8,"解决村民农田灌溉问题"]
["101","羊楼司镇","友爱村","河道护堤","已完工",5,5,"河道护堤修复120米，减少洪涝灾害，确保辖区居民生命财产安全"]
["102","羊楼司镇","友爱村","柳坪路段公路塌方护砌","已完工",2,2,"柳坪路段公路塌方护砌修复50米，减少洪涝灾害，确保辖区居民生命财产安全"]
["103","羊楼司镇","双山村委会","双山村王家至塘墈道路拓宽硬化","已完工",10,10,"墩上至塘墈道路150米拓宽3米硬化、周边场坪500平方硬化。群众的出行及农产品运输带来了便利，生产和生活条件明显改善"]
["104","羊楼司镇","双山村","铁家组道路硬化","已完工",{"v":35.7,"d":"35.700"},15,"铁家组道路全长850米，宽3米硬化，为农户产业发展提供交通便利。"]
["105","羊楼司镇","明星村","种植油茶","已完工",7,7,"发展村集体经济，同时带动脱贫人口和监测群众务工增收。受益脱贫人口满意度达到100%。"]
["106","羊楼司镇","明星村","河道清淤","已完工",{"v":3.6,"d":"3.60"},3.6,"发展村集体经济，同时带动脱贫人口和监测群众务工增收，群众出行方便。"]
["107","羊楼司镇","黄金村","黄金村河道护砌","已完工",3,3,"改善河道环境，提高居住环境质量。"]
["108","羊楼司镇","三港村","三港村和美湘村建设","已完工",100,100,"发展产业能带动脱贫，监测户劳动就业增加收入，发展村集体经济"]
["109","羊楼司镇","羊楼司镇","羊楼司镇公益岗位2024","已完工",23.2,23.2,"提供岗位给脱贫户及监测户"]
["110","长塘镇人民政府","长塘镇水圳村","长塘镇袁家组沟渠整修","已完工",8,5,"解决了老百姓及脱贫户的农田灌溉、提升了脱贫户自身发展能力，有利于促进群众及脱贫户增产增收。"]
["111","长塘镇人民政府","柳厂村委会","白家陇道路新建","已完工",39,4,"可改善一般群众与脱贫户的运输与出行，生产耕种，提升经济效益"]
["112","长塘镇人民政府","古洞村","机耕路硬化","已完工",36,3,"可改善一般群众与脱贫户的运输与出行，生产耕种，提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
["113","长塘镇人民政府","古洞村","古洞村钓场维修","已完工",13,13,"可改善一般群众与脱贫户经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
["114","长塘镇人民政府","马安村委会","马安村游港河百亩棉花基地中期建设","已完工",80,40,"改善了群众及脱贫户的经济收入，提高了生产生活质量，巩固脱贫成果。"]
["115","长塘镇人民政府","马安村委会","长塘镇马安村李家组机耕路拓宽硬化","已完工",22,5,"机耕路拓宽改建，为村脱贫户以及老百姓出行方便，在耕作种田方面提供便利的通行，也改善了人居环境。"]
["116","长塘镇人民政府","何洞村","排水沟改造","已完工",10,5,"为村贫困户以及广大群众创造了更好的、更便利的生活条件，改善人居环境，群众满意度100%"]
["117","长塘镇人民政府","何洞村","李家组农田生产设施建设","已完工",6,3,"为村贫困户以及广大群众创造了更好的、更便利的生活条件，改善人居环境，群众满意度100%"]
["118","长塘镇人民政府","石田村委会","上铺组港洲驳岸","已完工",4.8,4,"完善村基础设施建设，为脱贫户提供更好的生活条件，提升脱贫户自发展的能力，"]
["119","长塘镇人民政府","石田村委会","灌溉渠道维修","已完工",5,5,"灌溉渠道，为石田村脱贫户以及广大群众灌溉用水，群众满意度100%"]
["120","长塘镇人民政府","长塘社区","长塘起淤","已完工",20,15,"完善村基础设施建设，为脱贫户提供更好的生活条件，提升脱贫户自发展的能力，"]
["121","长塘镇人民政府","长塘镇托坝社区","新屋组水沟（砖砌部分）","已完工",22,7,"完成新建水沟230米，完善社区基础水利设施建设，为脱贫户提供更好的生活条件。提升脱贫户自我发展的能力，方便群众农田水利灌溉及生产生活雨水排放，提高生活质量。"]
["122","长塘镇人民政府","长塘镇托坝社区","塘东组道路硬化","已完工",7,5,"完成塘东组组内道路硬化，完善基础设施，为周边群众及脱贫户提供便利，使群众满意度100%"]
["123","长塘镇人民政府","长塘镇托坝社区","优质水稻种植","已完工",30,15,"完成125亩优质水稻种植"]
["124","长塘镇人民政府","长塘镇人民政府","何洞水库主渠维修","已完工",155,10,"维修灌溉渠道，为何洞村脱贫户以及广大群众灌溉用水，群众满意度100%"]
["125","长塘镇人民政府","长塘镇人民政府","石田港犁头港清淤疏浚生态护坡、绿化","已完工",100,10,"通过水利维修，解决脱贫户及广大群众的灌溉用水，促进农业增产增收，群众满意度100%"]
["126","长塘镇人民政府","长塘镇人民政府","涵洞维修加固","已完工",50,20,"通过水利维修，解决脱贫户及广大群众的灌溉用水，促进农业增产增收，群众满意度101%"]
["127","长塘镇人民政府","长塘镇人民政府","长塘镇2024年养猪养鸡 ","已完工",18,6.6,"提升脱贫户生活质量，巩固脱贫攻坚成果，提高脱贫户收入"]
["128","长塘镇人民政府","长塘镇人民政府","长塘镇2024年公益岗位","已完工",20,10.4,"提升脱贫户生活质量，巩固脱贫攻坚成果，提高脱贫户收入"]
["129","桃林镇政府","白石村","白石村土木岭鸡场扩建","已完工",9.68,9,"提高村集体经济收益，促进附近就业率、改善村民生活质量和，对农村经济发展起到推动作用。"]
["130","桃林镇政府","大畈村","大畈村大屋片机埠维修","已完工",{"v":4,"d":"4.00"},4,"有效的改善了生产条件和生态环境，保障了农业生产，促进农民增收，为现代农业高质量发展打下坚实的基础。"]
["131","桃林镇政府","横铺村","横铺村村委会公路拓宽及提质改造","已完工",{"v":4,"d":"4.00"},4,"方便村民们出行，美化乡村环境，提升了村们的生活质量"]
["132","桃林镇政府","金盆村","金盆村自来水安装","已完工",{"v":6,"d":"6.00"},6,"改善村民们的饮用水质量，提高村民们的生活品质，有效的控制水资源的污染和浪费，增强村民们的安全感和获得感。"]
["133","桃林镇政府","旧李村","旧李村朱古冲新造油茶林","已完工",{"v":9,"d":"9.00"},9,"目标 1：可使茶园增加产量，从而增加村集体经济收入，目标2： 能为群众或脱贫户提供就近就业机会，使脱贫户每年增加收入，进一步巩固脱贫成效。"]
["134","桃林镇政府","骆坪村","骆坪村杜家塘加宽建设","已完工",{"v":68,"d":"68.00"},5,"改善水利基础设施便利农田水利灌溉为脱贫户和村民提高经济收入"]
["135","桃林镇政府","坪上村","下屋组大珑塘山塘维修、清淤","已完工",8.213,8,"1、 发展集体经济2、增加脱贫户及居民收入，提高居民生活幸福指数。"]
["136","桃林镇政府","坪头村","坪头村上闾组路基拓宽","已完工",{"v":7,"d":"7.00"},6,"目标1：降低事故风险，确保村民出行安全；目标2：完善交通运输条件，促进当地经济发展；\n目标3：促进乡村振兴发展"]
["137","桃林镇政府","清泉社区","清泉社区马塘组机耕路硬化","已完工",{"v":16,"d":"16.00"},9,"目标1：方便村民出行，目标2：促进乡村振兴的经  济发展"]
["138","桃林镇政府","三合村","三合村罗家组组级公路提质改造","已完工",{"v":25,"d":"25.00"},13,"促进农业发展，提高生态环境，改善居民生活环"]
["139","桃林镇政府","源冲村","源冲村沈陆组中塘维修","已完工",{"v":4,"d":"4.00"},4,"解决附近村民们的生活生产及农田灌溉问题，提高了灌溉利用率，增加了农作物产量致使村民们增产增收。"]
["140","桃林镇政府","东湖村","东湖村新建机耕路","已完工",{"v":5,"d":"5.00"},5,"1，提供村民及脱贫户的方便出行、耕种, 2，促使村民农业增收增产"]
["141","桃林镇政府","治水村","治水村山塘堰坝维修","已完工",{"v":15,"d":"15.00"},9,"目标 1：保障村民的粮食生产，避免耕地抛荒；目标2：使脱贫户增产，巩固脱贫成果"]
["142","桃林镇政府","中畈村","中畈村油茶林抚育","已完工",{"v":12,"d":"12.00"},7,"带动群众增收，促进集体经济发展"]
["143","桃林镇政府","苎麻社区","丁家冲水塘加深加宽建设","已完工",{"v":10,"d":"10.00"},10,"1、 发展集体经济2、增加脱贫户及居民收入，提高居民生活幸福指数。"]
["144","桃林镇政府","苎麻社区","福寿山2024年度200亩茶园补苗及抚育","已完工",{"v":20,"d":"20.00"},20,"1、 发展集体经济2、增加脱贫户及居民收入，提高居民生活幸福指数。"]
["145","桃林镇政府","桃林镇政府","桃林镇207户脱贫户及20户监测户产业奖补","已完工",14.36,14.36,"目标1：帮助脱贫户及监测户发展产业； 目标2：带动产业发展，帮助脱贫户及监测户  创收。"]
["146","桃林镇政府","桃林镇政府","桃林镇公益性岗位","已完工",{"v":17.2,"d":"17.20"},17.2,"目标1：帮助桃林镇辖区脱贫户及监测户解决就业； 目标2：巩固脱贫攻坚同乡村振兴有效衔接"]
["147","桃林镇政府","大畈村","大畈村新建水渠管道","已完工",{"v":2,"d":"2.00"},2,"目标1：方便村民农田耕种；\n目标2：使村民们增产增收；\n目标3：促进乡村振兴发展。"]
["148","桃林镇政府","源冲村","源冲村陈家组排水沟清淤及硬化","已完工",{"v":5,"d":"5.00"},5,"目标1：方便村民农田耕种；\n目标2：使村民们增产增收；\n目标3：促进乡村振兴发展。"]
["149","桃林镇政府","东湖村","东湖村陈家组水渠维修","已完工",{"v":6,"d":"6.00"},6,"目标1：确保农田水利灌溉，目标2：完善水利设施，促进当地农业增产增收；\n目标3：促进乡村振兴发展。"]
["150","桃林镇政府","旧李村","旧李村方畈组危桥重建","已完工",{"v":8,"d":"8.00"},3,"给村民们的交通出行带来了便利，解决了农村生产物资和生活物资的运输问题，有效地促进了农村的社会稳定。"]
["151","桃林镇政府","白石村","白石村天车组道路山体滑坡整险","已完工",{"v":2.6,"d":"2.60"},2,"保障道路畅通，确保村民们能安全出行，预防二次灾害发生，提升生态环境质量。"]
["152","桃林镇政府","中畈村","中畈村中畈村庄家组山塘维修","已完工",{"v":4.5,"d":"4.50"},3,"方便村民农田和植灌溉"]
["153","桃林镇政府","苎麻社区","新造福寿山莲子冲茶叶基地100亩","已完工",{"v":26,"d":"26.00"},23,"1、发展集体经济2、增加脱贫户及居民收入，提高居民生活幸福指数。"]
["154","桃林镇政府","源冲村","源冲村方家片蒋家山塘维修","已完工",{"v":5,"d":"5.00"},5,"有效解决附近村民们的生活生产及农田灌溉问题，提高了农作物产量致使村民们增产增收。"]
["155","桃林镇政府","横铺村","横铺村下畈组公路维修、驳坎","已完工",10.528,10,"解除了安全隐患，疏通了道路，保障村民人们的正常出行，促进乡村振兴经济发展。"]
["156","詹桥镇人民政府","詹桥镇","2024年詹桥镇团湾水库饮水工程","已完工",{"v":180,"d":"180.00"},20,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["157","詹桥镇人民政府","詹桥镇水泉村","2024年詹桥镇水泉村长坑公路拓宽","已完工",{"v":20,"d":"20.00"},10,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["158","詹桥镇人民政府","詹桥镇印石安置点","2024年詹桥镇易地搬迁安置点产业发展","已完工",{"v":8,"d":"8.00"},7,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果"]
["159","詹桥镇人民政府","詹桥镇壁山村","2024年詹桥镇壁山村钟家组至陈家组河港清理","已完工",{"v":35,"d":"35.00"},30,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["160","詹桥镇人民政府","詹桥镇分水村","2024年詹桥镇分水村各山组道路拓宽白改黑","已完工",{"v":65,"d":"65.00"},16,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["161","詹桥镇人民政府","詹桥镇贺畈社区","2024年詹桥镇贺畈社区管道铺设","已完工",{"v":8,"d":"8.00"},6,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["162","詹桥镇人民政府","詹桥镇三界村","2024年詹桥镇三界村村级公路拓宽","已完工",{"v":40,"d":"40.00"},9,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["163","詹桥镇人民政府","詹桥镇沙团村","2024年詹桥镇沙团村付家组生姜基地","已完工",{"v":28,"d":"28.00"},5,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果"]
["164","詹桥镇人民政府","詹桥镇泰和社区","2024年詹桥镇泰和社区石冲组公路硬化（第二期）","已完工",{"v":12,"d":"12.00"},10,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["165","詹桥镇人民政府","詹桥镇跳石村","2024年詹桥镇跳石村跳石港村级连接公路托宽","已完工",{"v":20,"d":"20.00"},4,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["166","詹桥镇人民政府","詹桥镇雁南村","2024年詹桥镇雁南村花屋场至下江坑渠道整修","已完工",{"v":12,"d":"12.00"},5,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["167","詹桥镇人民政府","詹桥镇印石村","2024年詹桥镇印石村杨家组蔬菜种植基地扩建","已完工",{"v":8,"d":"8.00"},5,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果"]
["168","詹桥镇人民政府","詹桥镇余湾村","2024年詹桥镇余湾村新建药材基地","已完工",{"v":20,"d":"20.00"},10,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果"]
["169","詹桥镇人民政府","詹桥镇云山村","2024年詹桥镇云山村上屋组公路维修及驳墈","已完工",{"v":15,"d":"15.00"},6,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["170","詹桥镇人民政府","詹桥镇长浩村","2024年詹桥镇长浩村饮水工程","已完工",{"v":24,"d":"24.00"},7,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["171","詹桥镇人民政府","詹桥镇壁山村","2024年詹桥镇壁山村庙坡组至陈家组道路提质改造","已完工",{"v":30,"d":"30.00"},23,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["172","詹桥镇人民政府","詹桥镇沙团村","2024年詹桥镇沙团村高岭片公路拓宽","已完工",{"v":25,"d":"25.00"},15,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["173","詹桥镇人民政府","詹桥镇水泉村","2024年詹桥镇水泉村老屋二组公路白改黑","已完工",{"v":8,"d":"8.00"},5,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["174","詹桥镇人民政府","詹桥镇分水村","2024年詹桥镇分水村下屋组山塘维修","已完工",{"v":7,"d":"7.00"},3,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["175","詹桥镇人民政府","詹桥镇印石村","2024年詹桥镇易地搬迁安置点基础设施更新","已完工",{"v":11.5,"d":"11.50"},10,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["176","詹桥镇人民政府","詹桥镇三界村","2024年詹桥镇三界村老屋组砌坎","已完工",{"v":5.6,"d":"5.60"},5,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["177","詹桥镇人民政府","詹桥镇分水村","2024年詹桥镇分水村上屋组砌墈","已完工",{"v":11.5,"d":"11.50"},10,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["178","詹桥镇人民政府","詹桥镇水泉村","2024年詹桥镇水泉村七湾组渠道整修","已完工",{"v":6.5,"d":"6.50"},5,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["179","詹桥镇人民政府","詹桥镇壁山村","2024年詹桥镇壁山村钟家组至庙坡组路灯整修及陈家组护坡","已完工",{"v":13,"d":"13.00"},13,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["180","临湘市民政局","詹桥镇三界村","2024年詹桥镇三界村四房组公路维修","已完工",5.18,5,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["181","临湘市民政局","詹桥镇壁山村","2024年詹桥镇壁山村青咀桥至钟家组人居环境整治","已完工",{"v":20,"d":"20.00"},10,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["182","临湘市民政局","詹桥镇分水村","2024年詹桥镇分水村人居环境整治","已完工",{"v":10,"d":"10.00"},5,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["183","詹桥镇人民政府","詹桥镇跳石村","2024年詹桥镇跳石村上郑组公路拓宽","已完工",{"v":15,"d":"15.00"},2,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["184","詹桥镇人民政府","詹桥镇贺畈社区","2024年詹桥镇贺畈社区昌前组至贺畈组、鸦下组及晏上组路灯改造","已完工",{"v":12,"d":"12.00"},3,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["185","詹桥镇人民政府","詹桥镇长浩村","2024年詹桥镇长浩村光明组片区饮水工程","已完工",{"v":12,"d":"12.00"},8,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["186","詹桥镇人民政府","詹桥镇","庭院经济","已完工",18.68,18.68,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果"]
["187","詹桥镇人民政府","詹桥镇","公益岗位","已完工",{"v":20,"d":"20.00"},17.2,"为群众及脱贫户提供就业机会，带动增收致富"]
["188","詹桥镇人民政府","詹桥镇壁山村","2024年詹桥镇壁山村安全饮水工程","已完工",{"v":10,"d":"10.00"},10,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["189","詹桥镇人民政府","詹桥镇","大云山旅游公路提质改造工程（第一期）","已完工",{"v":150,"d":"150.00"},150,"基础设施改造，提高脱贫户和其他群众生产生活条件"]
["190","云湖街道","云湖街道","2024年庭院经济奖补","已完工",10.84,10.84,"给大约100户、348人提供产业奖补"]
["191","云湖街道","云湖街道","2024年公益性岗位","已完工",{"v":14.8,"d":"14.80"},14.8,"5个村社区45户141人提供公益岗位"]
["192","云湖街道","王禾社区","庄上组道路硬化","已完工",{"v":20,"d":"20.00"},5,"庄上组道路硬化长500米宽3.5米"]
["193","云湖街道","飞跃社区","青龙嘴组级道路维修硬化","已完工",{"v":6,"d":"6.00"},3,"青龙嘴道路维修、硬化长200米宽3.5米"]
["194","云湖街道","三联村","自来水管网管网延伸工程","已完工",{"v":65,"d":"65.00"},4,"自来水管网安装10公里，保障群众饮水安全"]
["195","云湖街道","大岭村","三湾组至同德组河道清淤及沿河机耕路","已完工",{"v":80,"d":"80.00"},80,"三湾组至同德组河道清淤，修沿河机耕路硬化白改黑长4800米宽4米"]
["196","云湖街道","板桥村","陈家组公路护坡","已完工",{"v":35,"d":"35.00"},8,"道路硬化45平方，长26米、宽1.5米；护坡210立方"]
["197","云湖街道","安置小区","安置小区蔬菜基地水利等设施","已完工",{"v":10,"d":"10.00"},7,"蔬菜基地灌、排水及围栏设施"]
["198","云湖街道","安置小区","安置小区灾后重建","已完工",{"v":30,"d":"30.00"},20,"活动中心重建，充电棚修复及绿化等其他"]
["199","云湖街道","安置小区","优质稻种植基地","已完工",{"v":12,"d":"12.00"},8,"100亩优质稻种植"]
["200","云湖街道","大岭村","谢坡塘水库机埠等引水工程建设","已完工",{"v":25,"d":"25.00"},15,"大赵组至同德德长300米管网防锈焊接，砼镇墩及支墩建设，引水设备购买安装及进水渠清淤。"]
["201","云湖街道","板桥村","主公路水毁维修拓宽","已完工",{"v":17,"d":"17.00"},9,"道路维修护坡场160米，拓宽长140米宽2米。"]
["202","云湖街道","大岭村","组级公路维修拓宽","已完工",{"v":10,"d":"10.00"},10,"道路维修拓宽800米，宽4米，修一座通路桥"]
["203","云湖街道","王禾社区","水毁灌溉渠道疏通、维修及滑坡隐患整治","已完工",{"v":20,"d":"20.00"},6,"蒋一二组中渠水毁疏通300米，港下组渠道水毁疏通150米按管筒60米"]
["204","忠防镇政府","马家洞村","忠防镇马家洞村杨家冲河港冶理","已完工",6.5,3,"全长200米。护港坡100立方，保障村民生产生活用水，提高农业生产。"]
["205","忠防镇政府","沙坪村","忠防镇沙坪村鸦坡组水渠整修","已完工",25,10,"整修硬化800米、渠道现浇800米"]
["206","忠防镇政府","双港村","忠防镇双港村大竹组、山墈组沟渠整修","已完工",{"v":25,"d":"25.00"},24,"全长2300米沟渠及周边护坡修整"]
["207","忠防镇政府","汀畈社区","忠防镇汀畈社区高冲组公路修整","已完工",{"v":5,"d":"5.00"},4,"保障出行安全，节省出行时间"]
["208","忠防镇政府","响山村","忠防镇响山村大石组至五大路道路建设","已完工",{"v":30,"d":"30.00"},30,"路面提质改造500米、保障居民出行安全，节省出行时间"]
["209","忠防镇政府","渔潭村","忠防镇渔潭村薛家组、猫形组公路修整","已完工",{"v":9,"d":"9.00"},8,"沟渠修整1000米，保障村民生产生活用水，提高农业生产。"]
["210","忠防镇政府","雁峰村","忠防镇雁峰村港背组竹上组沿河道路修整","已完工",{"v":15,"d":"15.00"},15,"全长500米沟渠改建及硬化"]
["211","忠防镇政府","邱坪社区","忠防镇邱坪社区徐家、陈家组沟渠修整","已完工",{"v":13,"d":"13.00"},11,"全长500米。保障村民生产用水，提高农业生产。"]
["212","忠防镇政府","忠防镇","忠防镇2024年庭院经济发展","已完工",{"v":15,"d":"15.00"},11.8,"利于脱贫户自力更生，利用鼓励种养增加收入保障脱贫成效，奖补金额补贴种养支。"]
["213","忠防镇政府","马家洞村","忠防镇马家洞村谢龙至大同组公路拓宽硬化","已完工",{"v":9,"d":"9.00"},5,"完善基础设施，提高群众出行安全"]
["214","忠防镇政府","忠防社区","忠防镇忠防社区砖屋组道路提质改造","已完工",{"v":5,"d":"5.00"},2,"完善基础设施，提高群众出行安全"]
["215","忠防镇政府","雁峰村","忠防镇雁峰村坳背组沟渠改建及硬化","已完工",{"v":15,"d":"15.00"},13,"全长500米。保障村民生产生活用水，提高农业生产"]
["216","忠防镇政府","响山村","忠防镇响山村刘二组河港护坡工程","已完工",{"v":16,"d":"16.00"},14,"全长85米。保障村民生产生活用水，提高农业生产"]
["217","忠防镇政府","汀畈社区","忠防镇汀畈社区杨家公路边坡治理路面修整","已完工",{"v":6.517,"d":"6.52"},5.94,"全场100米、保障居民出行安全，节省出行时间"]
["218","忠防镇政府","雁峰村","忠防镇雁峰村下屋组公路护坡","已完工",{"v":15,"d":"15.00"},10,"砌坎及护坡高12米、长30米、宽3米"]
["219","忠防镇政府","汀畈社区","忠防镇汀畈社区何山组组级公路拓宽硬化","已完工",{"v":12,"d":"12.00"},10,"完成拓宽2米总宽3.5，长360米"]
["220","忠防镇政府","马家洞村","忠防镇马家洞村浏阳片水毁修复工程","已完工",5.72,2,"水毁修复，公路户基修复100米，沟渠修复100米、公路滑坡清理60米"]
["221","忠防镇政府","邱坪社区","忠防镇邱坪社区老屋及陈家组路灯安装工程","已完工",{"v":8,"d":"8.00"},6,"新安装路灯40盏"]
["222","忠防镇政府","响山村","响山村生态园路基建设","已完工",{"v":18,"d":"18.00"},15.8,"完成全长1.3公里，宽6米，水泥硬化600平方米"]
["223","忠防镇政府","响山村","响山村生态园新建桥梁工程","已完工",{"v":38,"d":"38.00"},31.73,"完成全长20米，宽4.5米，高6.5米"]
["224","忠防镇政府","响山村","响山村生态园新建钓鱼台工程","已完工",{"v":15,"d":"15.00"},11,"完成新建钓鱼台200个"]
["225","忠防镇政府","响山村","忠防镇响山村陆家组河港护坡工程","已完工",{"v":45,"d":"45.00"},41.47,"完成全长160米，宽1.8米，高4.5米"]
["226","忠防镇政府","忠防镇","忠防镇2024年公益岗位补贴","已完工",{"v":15,"d":"15.00"},14,"用于鼓励脱贫户监测户自力更生，做保洁员等公益性岗位奖补，保证收入问题。"]
["227","忠防镇政府","木形村","木形永洞组机械道路拓宽工程","已完工",{"v":22,"d":"22.00"},20,"完成拓宽长1300米，宽4.5米"]
["228","忠防镇政府","汀畈社区","汀畈社区青山咀组水渠建设","已完工",{"v":10,"d":"10.00"},10,"完成1800米水渠维修"]
["229","江南镇人民政府","洋溪村","洋溪村集体经济下团湖渔场仓库建设","已完工",{"v":28,"d":"28.00"},6,"150平方米"]
["230","江南镇人民政府","石岭村","江南镇石岭村粽叶基地基础设施建设与维护完善产业发展","已完工",10.13,3,"1次"]
["231","江南镇人民政府","江南镇","江南镇庭院经济产业奖补2024","已完工",{"v":24,"d":"24.00"},15.96,"775人"]
["232","江南镇人民政府","江南镇","江南镇公益性岗位2024","已完工",{"v":30.2,"d":"30.20"},18.4,"48人"]
["233","江南镇人民政府","东冶村","东冶村环村公路维修","已完工",{"v":10,"d":"10.00"},3,"长6.3公里，宽4.5米"]
["234","江南镇人民政府","盛塘村","_盛塘村四组道路修复","已完工",{"v":19.4,"d":"19.40"},15,"长600米，宽3.5米"]
["235","江南镇人民政府","灯塔村","灯塔村11组桥梁维修","已完工",{"v":8.2,"d":"8.20"},3,"1座"]
["236","江南镇人民政府","牛湖村","牛湖村8-19组道路维修","已完工",{"v":13,"d":"13.00"},8,"1条"]
["237","江南镇人民政府","谷花社区","谷花社区粮店路小学路维修、硬化","已完工",{"v":18,"d":"18.00"},16,"350米"]
["238","江南镇人民政府","长江村","_长江村10、11组道路加宽","已完工",{"v":8,"d":"8.00"},5,"300米"]
["239","江南镇人民政府","灯塔村","灯塔村砖厂至二级渠道路硬化维修","已完工",{"v":18,"d":"18.00"},17,"3000平方米"]
["240","江南镇人民政府","鸭栏村","江南镇鸭栏村荷叶洲片通组公路至冶湖渍堤","已完工",19.14,17,"长1080米，宽3.5米"]
["241","江南镇人民政府","儒溪社区","江南镇儒溪社区受灾机耕路维修","已完工",{"v":15,"d":"15.00"},10,"1560米"]
["242","江南镇人民政府","新洲村","江南镇新洲村道路受灾破损路面新建","已完工",{"v":24,"d":"24.00"},15,"长350米，宽4.5米"]
["243","江南镇人民政府","石岭村","临湘市_乡村建设行动_农村基础设施（含产业配套基础设施）_江南镇石岭村组公路水毁路段护坡砌浆石","已完工",12.58,10,"500米"]
["244","江南镇人民政府","儒溪社区","临湘市_乡村建设行动_农村基础设施（含产业配套基础设施）_江南镇儒溪社区道路维修","已完工",{"v":11,"d":"11.00"},3,"263米"]
["245","江南镇人民政府","鸭栏村","临湘市_乡村建设行动_农村基础设施（含产业配套基础设施）_鸭栏村沟渠疏浚","已完工",{"v":11,"d":"11.00"},9,"3400米"]
["246","江南镇人民政府","丁坊村","临湘市_乡村建设行动_农村基础设施（含产业配套基础设施）_江南镇丁坊村肖冲组山塘清淤","已完工",{"v":3,"d":"3.00"},3,"1处"]
["247","江南镇人民政府","江南村","临湘市-江南镇_乡村建设行动_农村基础设施（含产业配套基础设施）_江南村14、15、16组机耕路维修","已完工",{"v":6,"d":"6.00"},3,"1500米"]
["248","江南镇人民政府","丁坊村","临湘市-江南镇_乡村建设行动_农村基础设施（含产业配套基础设施）_唐家组沟渠疏浚","已完工",{"v":6.5,"d":"6.50"},4,"长5500米，宽4米"]
["249","坦渡镇人民政府","万峰村","坦渡镇万峰村石壁组新建水坝","已完工",21,19,"改善农田灌溉条件，带动群众及脱贫户的经济收入，提高生产生活质量。"]
["250","坦渡镇人民政府","红旗村","坦渡镇红旗村九屋组山塘护坡修建、清淤","已完工",11,3,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["251","坦渡镇人民政府","红旗村","坦渡镇红旗村干垅组山塘护坡修建、清淤","已完工",7,3,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["252","坦渡镇人民政府","农胜村","坦渡镇农胜村余福组渠道建设","已完工",6,6,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["253","坦渡镇人民政府","农胜村","坦渡镇农胜村大庄组山塘清淤","已完工",7,4,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["254","坦渡镇人民政府","联合村","坦渡镇联合村何庄组山塘清淤","已完工",12,7,"完善基础设施，改善农户生产生活条件，增加农户收入"]
["255","坦渡镇人民政府","联合村","坦渡镇联合村同心组山塘建设","已完工",12,5,"完善基础设施，改善农户生产生活条件，增加农户收入"]
["256","坦渡镇人民政府","新湖村","坦渡镇新湖村邓七垅渠道硬化","已完工",7.5,2,"解决群众灌溉难问题，减少生产成本，提高脱贫户收入"]
["257","坦渡镇人民政府","大和村","坦渡镇大和村枫树坡山塘水库整修","已完工",30,8,"改建基础设施，有效改善脱贫户和居民水体质量，提升山塘的蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。"]
["258","坦渡镇人民政府","长岭社区","坦渡镇长岭社区上岭组山塘清淤","已完工",12,5,"改建基础设施，有效改善脱贫户和居民水体质量，提升山塘的蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。"]
["259","坦渡镇人民政府","长岭社区","坦渡镇长岭社区杨家垄组山塘清淤","已完工",16,3,"改建基础设施，有效改善脱贫户和居民水体质量，提升山塘的蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。"]
["260","坦渡镇人民政府","农胜村","坦渡镇农胜村江家组抗旱机埠","已完工",8.52,6,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["261","坦渡镇人民政府","晓阳村","坦渡镇晓阳村塘角组上塘整修","已完工",13,7,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["262","坦渡镇人民政府","桐梓铺社区","坦渡镇桐梓铺社区一组新塘清淤","已完工",6,3,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["263","坦渡镇人民政府","晓阳村","坦渡镇晓阳村次咀组余家塘整修","已完工",14.54,11,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["264","坦渡镇人民政府","灯明村","坦渡镇灯明村畈屋组渠上山塘维修硬化","已完工",11.8,8,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["265","坦渡镇人民政府","桐梓铺社区","坦渡镇桐梓铺社区金咀组横塘整修","已完工",8,5,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["266","坦渡镇人民政府","韩桥村","坦渡镇韩桥村山塘清淤及整修","已完工",17.3,15,"改建基础设施，有效改善脱贫户居民水体质量，提升山塘蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。"]
["267","坦渡镇人民政府","坦渡村","坦渡镇坦渡村凤形组排灌渠道硬化","已完工",7.3,7,"完善基础建设，解决脱贫户和农户水田灌溉困难，提高经济效益增收"]
["268","坦渡镇人民政府","红旗村","坦渡镇红旗村上螃垅组山塘护坡修建与清淤","已完工",8,5,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。"]
["269","坦渡镇人民政府","坦渡镇","坦渡镇2024年庭院经济发展","已完工",18.55,15.84,"直接帮扶，提升脱贫户与监测户增加产业收入。"]
["270","坦渡镇人民政府","坦渡镇","坦渡镇2024年公益性岗位","已完工",16.8,15.2,"直接帮扶，提升脱贫户与监测户增加务工收入。"]
["271","坦渡镇人民政府","韩桥村","坦渡镇韩桥村米铺、周咀组公路硬化","已完工",52,50,"1、道路畅通，给脱贫户解决出行难问题。2、减少运输成本，从而为脱贫户增收"]
["272","坦渡镇人民政府","定湖村","坦渡镇定湖村湾内组机耕路硬化","已完工",9.3,5,"完善基础设施，解决脱贫户和农户出行难的问题，减少农副产品销售的运输成本，使脱贫户增收800元左右，从而巩固脱贫成果。"]
["273","坦渡镇人民政府","新湖村","坦渡镇新湖村小垅组公路硬化","已完工",17.9,8,"解决群众出行难问题，减少运输成本，提高脱贫户收入"]
["274","坦渡镇人民政府","韩桥村","坦渡镇韩桥村周家山、岭上组、老竹坡组公路硬化","已完工",80,76.8,"完善基础设施，解决脱贫户和农户出行难的问题，减少农副产品销售的运输成本，从而巩固脱贫成果。"]
["275","坦渡镇人民政府","灯明村","坦渡镇灯明村谈家组桥梁建设","已完工",10,8,"完善基础设施，解决脱贫户和农户出行难的问题，减少农副产品销售的运输成本，从而巩固脱贫成果。"]
["276","坦渡镇人民政府","坦渡村","坦渡镇坦渡村张家群力组公路硬化","已完工",11.5,7,"减少农户脱贫户产品运输成本，消除道路安全隐患。"]
["277","坦渡镇人民政府","韩桥村","坦渡镇韩桥村田畈组公路硬化","已完工",5.7,5,"道路畅通，给脱贫户解决出行难问题，减少运输成本，从而为脱贫户增收"]
["278","坦渡镇人民政府","定湖村","坦渡镇定湖村上下马蹄湖机耕路铺砂石","已完工",6.2,5,"道路畅通，给脱贫户解决出行难问题，减少运输成本，从而为脱贫户增收"]
["279","坦渡镇人民政府","韩桥村","坦渡镇韩桥村公路硬化及油路铺设","已完工",104,100,"道路畅通，给脱贫户解决出行难问题，减少运输成本，从而为脱贫户增收"]
["280","五里牌街道","五里街道花桥村","农田灌溉堰坝修建","已完工",4,3,"解决农田灌溉"]
["281","五里牌街道","五里街道火炬村","公路硬化","已完工",14,3,"方便居民平安出行"]
["282","五里牌街道","五里街道楠木村","道路维修","已完工",5.4,5,"方便居民平安出行"]
["283","五里牌街道","五里街道千针村","安全饮水","已完工",16,5,"保证居民饮水安全"]
["284","五里牌街道","五里街道松峰村","安全饮水","已完工",50.73,32,"保证居民饮水安全"]
["285","五里牌街道","五里街道新球社区","沟渠整修","已完工",6.026,3,"解决农田灌溉"]
["286","五里牌街道","五里街道新庄社区","公路拓宽","已完工",20,4,"方便居民平安出行"]
["287","五里牌街道","五里街道许畈村","公路硬化","已完工",28.2,4,"方便居民平安出行"]
["288","五里牌街道","五里街道烟冲村","道路拓宽","已完工",14.09,14,"方便居民平安出行"]
["289","五里牌街道","五里牌街道","庭院经济","已完工",12,12,"带动生产"]
["290","五里牌街道","五里牌街道","公益岗位","已完工",20,20,"符合条件的脱贫户和监测户全覆盖"]
["291","五里牌街道","五里街道烟冲村","道路建设","已完工",8.93,3,"方便居民平安出行"]
["292","五里牌街道","五里街道许畈村","山塘整修","已完工",5.946,2,"解决农田灌溉"]
["293","五里牌街道","五里街道新球社区","水渠整修","已完工",5.3,4,"解决农田灌溉"]
["294","五里牌街道","五里牌街道楠木村","山塘整修","已完工",30.02,20,"解决农田灌溉"]
["295","五里牌街道","五里街道楠木村","港堤砌护","已完工",9.1,3,"解决农田灌溉"]
["296","五里牌街道","五里街道烟冲村","山塘整修","已完工",5.46,3,"解决农田灌溉"]
["297","五里牌街道","五里牌街新庄社区","公路拓宽","已完工",15,5,"方便居民平安出行"]
["298","五里牌街道","五里牌街道烟冲村","东后组产业路建设","已完工",10.01,10,"带动生产"]
["299","五里牌街道","五里牌街道千针村","山塘整修千针村老千组","已完工",16,5,"解决农田灌溉"]
["300","五里牌街道","五里牌街道新庄社区","次坡组公路拓宽","已完工",21,10,"方便居民平安出行"]
["301","白羊田镇政府","白羊田社区","2024年白羊田镇白羊田社区上二组道路硬化维修","已完工",{"v":4.5,"d":"4.50"},4,"完成上二组机埠路硬化，路基3米宽，100米长，道路两侧石砌。为村民的出行和农作提供更多的便利。"]
["302","白羊田镇政府","西山村","2024年白羊田镇西山村大田至詹桥镇云山村群建道路拓宽升级改造，破损维修","已完工",{"v":80,"d":"80.00"},27,"完成大田至群建公路拓宽升级改造，全长约3000米，为村民的出行和农作提供更多的便利"]
["303","白羊田镇政府","方山村","2024年白羊田镇方山村殷家组麻石坡水圳维修","已完工",{"v":4,"d":"4.00"},4,"完成殷家组麻石坡水圳维修280米，保障群众农业灌溉，激发群众发展生产的积极性，促进增收。"]
["304","白羊田镇政府","八百村","2024年白羊田镇八百村沟渠疏浚","已完工",{"v":5.8,"d":"5.80"},4,"完成金盆组至凉亭组沟渠疏浚，长500米，两侧墙高度为40公分，底板宽为45公分，三面硬化，为村民的农作提供更多的便利。"]
["305","白羊田镇政府","双泉村","2024年白羊田镇双泉村老屋黎家花园口至石矶垅界碑一段道路拓宽","已完工",{"v":15.5,"d":"15.50"},10,"完成老屋黎家花园口至石矶垅界碑一段道路拓宽至8米，为村民的出行和农作提供更多的便利"]
["306","白羊田镇政府","合盘村","2024年白羊田镇合盘村农村安全饮水管网铺设项目","已完工",{"v":13,"d":"13.00"},10,"完成全村各组约33公里水厂管网铺设，解决合盘村全体村民生活、生产用水输送问题，完善农村供水基础设施，提高生活、生产供水保证率。"]
["307","白羊田镇政府","白羊田镇","产业奖补","已完工",{"v":16,"d":"16.00"},16,"对全镇422户中符合有劳动能力，发展意愿条件的脱贫户、监测户依照标准直接进行奖补，提高农户种养殖热情，增加经济收入。"]
["308","白羊田镇政府","白羊田镇","公益岗位奖补","已完工",{"v":19.6,"d":"19.60"},19.6,"帮助脱贫户、监测户就近就地就业，促进受益户稳定增收，防范返贫致贫风险。"]
["309","白羊田镇政府","方山村","白羊田镇2024年殷家至登东道路拓宽","已完工",11.17,8,"完成殷家至登东道路拓宽硬化1200米，保障群众安全出行，激发群众发展生产的积极性，促进增收。"]
["310","白羊田镇政府","白羊田镇","白羊田镇2024年双泉民生服务中心至海口道路水毁","已完工",{"v":12,"d":"12.00"},10,"完成双泉民生服务中心至海口道路水毁，保障群众安全出行。"]
["311","白羊田镇政府","双泉村","白羊田镇2024年石矶垅界碑至宋家洞道路拓宽","已完工",{"v":10,"d":"10.00"},5,"完成石矶垅界碑至宋家洞1300米道路拓宽至8米，提高双泉村、八百村、西山村村民出行安全。"]
["312","白羊田镇政府","西山村","2024年白羊田镇西山村四房组至林场组、西金公路、东沙公路西湖庙路段、东沙公路大山段、村部至何山组公路水毀维修","已完工",{"v":12.3,"d":"12.30"},10,"完成四房组至林场组公路长约40米滑坡，西金公路长约50米滑坡，东沙公路西湖庙路段滑坡60米，东沙公路大山段滑坡10处150米，村部至何山组公路滑坡60米。"]
["313","白羊田镇政府","白羊田社区","2024年白羊田社区宋坳公路白改黑","已完工",{"v":18,"d":"18.00"},15,"完成宋坳公路白改黑长400米，宽6米"]
["314","白羊田镇政府","八百村","2024年白羊田镇八百村周前组马家塘清淤、衬砌","已完工",6.57,6,"完成周前组马家塘清淤、衬砌。全长170米。高1米6，为村民的出行和农作提供更多的便利。"]
["315","白羊田镇政府","双泉村","2024年白羊田镇双泉村付陈组至左家组道路拓宽","已完工",{"v":11,"d":"11.00"},10,"完成付陈组-左家组3.5米道路拓宽至6米，全长约500米，为村民的出行和农作提供更多的便利。"]
["316","白羊田镇政府","白羊田社区","白羊田社区庄上组至刘湾东头组道路提质改造","已完工",{"v":25,"d":"25.00"},20,"完成白羊田社区庄上组至刘湾东头组长500米，宽5米道路白改黑及划线。为村民的出行和农作提供更多的便利。"]
["317","白羊田镇政府","八百村","2024年白羊田镇宋洞桥至贾家桥道路维修","已完工",{"v":51,"d":"51.00"},41,"完成长宋洞桥至贾家桥道路维1001.7米，宽4.5米。为村民的出行安全提供了保障。"]
["318","白羊田镇政府","八百村","2024年白羊田镇竹山组至三圣组沟渠疏浚","已完工",{"v":11,"d":"11.00"},9,"竹山组至三圣组沟渠疏浚长450米，底宽50厘米，高60厘米，为村民农业用水灌溉提供保障。"]
["合     计",{"$nulls":4},{"$f":"SUM(F4:F322)","v":{"v":14460.5261,"d":"14460.53"}},{"$f":"SUM(G4:G322)","v":9924.83}]