{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["新增"],"not_rendered":{"external_links":2,"defined_names":3,"comments":1},"read":"whole","date_system":"1900"}

{"sheet":"新增","index":0,"n_rows":212,"n_cols":25,"rows_kept":212,"merged":[[0,0,0,24],[1,0,1,6],[1,20,1,24],[2,0,4,0],[2,1,2,3],[2,4,4,4],[2,5,4,5],[2,6,4,6],[2,7,4,7],[2,8,4,8],[2,9,2,10],[2,11,4,11],[2,12,4,12],[2,13,2,15],[2,16,2,21],[2,22,4,22],[2,23,4,23],[2,24,4,24],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,9,4,9],[3,10,4,10],[3,13,4,13],[3,14,3,15],[3,16,4,16],[3,17,4,17],[3,18,4,18],[3,19,3,21],[211,0,211,6]]}
["临湘市2024年度巩固拓展脱贫攻坚成果和乡村振兴项目库拟入库申报表"]
["单位：(盖章)",{"$nulls":19},"时间： 2024年"]
["序号","项目类别",null,null,"乡","村","项目名称","建设性质","实施地点","时间进度",null,"责任单位","建设内容及规模","资金规模和筹资方式",null,null,"受益对象",{"$nulls":5},"绩效目标","联农带农机制","备注"]
[null,"项目类型","二级项目类型","项目子类型",{"$nulls":5},"计划开工时间","计划完工 时间",null,null,"项目预算总投资（万元）","其中",null,"受益村 数(个)","受益户 数(户 )","受益人口数（人）","其中"]
[{"$nulls":14},"财政资金（万元）","其他资金（万元）",{"$nulls":3},"受益脱 贫村数 (个)","受益脱贫户数及防止返贫监测对象户数(户)","受益脱贫人口数及防止返贫监测对象人口数(人)"]
[1,"乡村建设行动","农村基础设施","农村供水保障设施建设","黄盖镇",null,"黄盖镇机埠维修及防汛抗旱管道、水泥沟恢复","维修","黄盖镇",2024.08,2024.09,"黄盖镇","更换变压器2台、更换启闭机4台、新购启动柜变压器3台、\n新购3台潜水泵、控制柜、管道等，完成防汛抗旱管道及水泥沟恢复3000米。",60,35,25,4,200,770,0,9,25,"通过机埠维修、防汛抗旱管道及水泥沟恢复，保证黄盖各村社区农户农田的正常生产用水","通过电排维修、防汛管道及水泥沟恢复，保证黄盖镇各村社区田地的生产用水，避免因旱缺水、因汛内涝导致的农田减产，提高农田产量，增加农民收入。"]
[2,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","盛塘村","江南镇盛塘村受灾砂石路铺路","维修","江南镇盛塘村13-20组","2024.1",2024.12,"盛塘村","盛塘村13组-20组砂石铺路1520米",9,5,4,1,225,564,1,8,20,"目标1：受灾砂石路修路1520米。","通过砂石铺路方便群众运输，增加农户种养积极性扩大农业生产，为脱贫户每户增加收入500元/年。"]
[3,"产业发展项目","配套设施项目","小型农田水利设施建设","江南镇","灯塔村","江南镇灯塔村1-2组灌渠设施新建","新建","江南镇灯塔村1-2组","2024/\n9/16","2024/\n10/16","灯塔村","灯塔村烟波尾1-2组灌渠设施新建420米",8.4,7,1.4,1,195,785,null,8,23,"目标1：灌渠设施新建420米，方便村民农田耕种。","通过灌渠设施维修方便群众农业生产防汛抗旱，增加农户种养积极性扩大农业生产，为脱贫户每户增加收入500元/年。"]
[4,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","牛湖村","江南镇牛湖村4组桥梁维修","新建","江南镇牛湖村四组","2024/\n11/28","2024/\n12/28","牛湖村","牛湖村4组桥梁维修",6,5,1,1,130,520,null,4,12,"目标1：桥梁维修1座。","通过桥梁设施维修方便群众农业生产生活、出行，增加农户种养积极性扩大农业生产，为脱贫户每户增加收入500元/年。"]
[5,"产业发展项目","生产项目","休闲农业与乡村旅游","江南镇","石岭村","江南镇石岭村元家坝休闲垂钓基地建设","新建","江南镇石岭村",2024.11,2024.5,"石岭村","堤坝加固，钓台建设，休闲场地建设",20.13,15,5.13,1,50,200,null,8,20,"目标1：休闲垂钓基地建设1处\n","通过发展村集体经济，为脱贫户增收500元/年"]
[6,"产业发展项目","加工流通项目","产地初加工和精深加工","江南镇","石岭村","江南镇石岭村粽子厂房建设","新建","江南镇石岭村","2024/\n10",2024.5,"石岭村","场地平整与硬化  钢架棚搭建  附属设施建设",30.05,10,20.05,1,200,1500,null,10,30,"目标1：粽子厂房建设1座","通过发展村集体经济，为脱贫户增收500元/年"]
[7,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","新洲村","江南镇新洲村道路受灾破损路面新建","新建","新洲村","2024/\n10",2024.11,"新洲村","新洲村道路破损路面新建350米长，4.5米宽",24,10,14,2,1160,4600,null,35,83,"目标：新建350米长，4.5米宽资源路。","解决村民出行难的问题，村民与脱贫户农产品销售难问题，为脱贫户增收500元--1000元"]
[8,"产业发展项目","配套设施项目","小型农田水利设施建设","江南镇","丁坊村","江南镇丁坊村罗口截水闸","新建","唐家组罗口湖岔","2024/\n10",2024.11,"丁坊村","罗口截水闸",20,15,5,1,285,1120,1,6,17,"目标;修建节水闸1处","改善村民农业生产灌溉条件，为脱贫户增收500元/年"]
[9,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","谷花社区","江南镇谷花社区5组、8组受灾公路升级改造","新建","江南镇谷花社区","2024/\n10",2024.11,"谷花社区","道路新建1000米，宽3.5米",25,15,10,1,585,1560,1,9,35,"目标：道路新建1000米，宽3.5米","道路维修硬化完成改善群众农业生产条件，为脱贫户增收500元/年"]
[10,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","江南村","江南镇江南村6组受灾机耕路维修","维修","江南村6组","2024/\n11/13","2024/\n11/20","江南村","江南村6组1200米机耕路维修",6,3,3,1,129,427,1,4,12,"目标：1200米机耕路维修","方便农产品运输，为脱贫户增收500元/年"]
[11,"产业发展项目","生产项目","种植业基地","江南镇","东冶村","江南镇东冶村赤松茸种植","新建","棋杆组","9月","12月","东冶村","20亩",11,8,3,1,35,175,1,13,52,"目标：建设赤松茸种植基地20亩","通过发展村集体经济带动脱贫户增收500-1000元/年"]
[12,"产业发展项目","配套设施项目","小型农田水利设施建设","江南镇","长江村","江南镇长江村油菜花基地二组、五组渠道护坡","新建","2、5组","2024/\n10/1","2024/\n11/1","长江村","800米",10,8,2,1,550,2489,1,22,62,"目标1：新建渠道护坡800米","方便脱贫户及监测户等劳动力农业种养殖，为脱贫户增收300元/年"]
[13,"乡村建设行动","农村基础设施","产\n业\n路\n建\n设","江南镇","鸭栏村","江南镇鸭栏村荷叶洲片通组公路至冶湖渍堤","新建","鸭栏村",2024.2,2024.11,"鸭栏村","完成荷叶洲片通组路至冶湖渍堤全长1080米，宽3.5米产业路水泥硬化",49.14,15,34.14,1,1014,3896,null,26,72,"目标：完成荷叶洲片通组路至冶湖渍堤全长1080米，宽3.5米产业路水泥硬化","改善粮食生产条件，解决群众出行问题，带动脱贫户增收500元/年"]
[14,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","儒溪社区","江南镇儒溪社区受灾机耕路维修","维修","儒溪社区","2024/\n4/1","2024/\n4/30","儒溪社区","机耕路维修1560米",{"v":15,"d":"15.00"},10,5,1,126,376,null,7,15,"目标：机耕路维修1560米","带动农户，脱贫户、监测户发展产业，为脱贫户每户增收300元/年。"]
[15,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","谷花社区","江南镇谷花社区14组通村路至江盛路","改建","谷花社区","2024/\n10","2024/\n11","谷花社区","加宽、硬化宽1.5米、长1250米",28.35,15,13.35,1,825,3120,1,27,77,"目标：加宽、硬化宽1.5米、长1250米","改善农业生产条件，增加脱贫户收入500-1000元/年"]
[16,"产业发展项目","配套设施项目","小型农田水利建设","江南镇","丁坊村","江南镇丁坊村肖冲组山塘清淤","新建","丁坊村肖冲组","2024/\n10","2024/\n11","丁坊村","肖冲组山塘清淤",3,3,0,1,235,987,1,5,15,"完善了丁坊村基础建设，改善村民农业生产灌溉条件。","改善农户，脱贫户、监测户农业生产灌溉条件，增收300-500元/年，巩固脱贫成果。"]
[17,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","儒溪社区","江南镇儒溪社区道路维修","维修","儒溪社区","2024/\n8/1","2024/10月1日","儒溪社区","维修道路263米",{"v":11,"d":"11.00"},3,8,1,38,126,null,1,0,"加强基础建设，为产业发展提供条件，增加群众收入。该项目涉及农户38户126人，脱贫户及监测户1户1人。","带动农户，脱贫户、监测户发展产业，增收500元/年，巩固脱贫成果。"]
[18,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","石岭村","江南镇石岭村组公路水毁路段护坡砌浆石","新建","江南镇石岭村","2024/\n10","2024/\n12","石岭村","组公路水毁路段护坡砌浆石长500米",17.58,10,7.58,1,200,1500,null,10,20,"目标1：集体经济发展与产业建设\n目标2：发展经济方便农民出行增加农民经济收入   目标3：促进乡村振兴产业发展。","改善农业生产条件，增加脱贫户收入500-1000元/年"]
[19,"产业发展项目","生产项目","养殖业基地","江南镇","洋溪村","洋溪村集体经济下团湖渔场仓库建设","新建","洋溪村","2024/\n8/1","2024/\n10/1","洋溪村","洋溪村下团湖仓库建设150平方米",28,10,18,1,20,102,1,2,10,"目标：新建仓库1个","通过新建仓库，使脱贫户和普通农户养殖鱼虾提供方便，减少成本。"]
[20,"乡村建设行动","农村基础设施","农村道路建设","江南镇","盛塘村","盛塘村四组道路修复","维修","盛塘村","2024-11-01","2024-11-20","盛塘村","道路修复长600米，宽3.5米",29.4,13,16.4,1,225,564,1,8,20,"目标：道路维修600米","解决村民出行难；有效提高经济收入； 促进乡村振兴发展"]
[21,"乡村建设行动","农村基础设施","农村道路建设","江南镇","盛塘村","盛塘村二组桥修复","维修","盛塘村","2024-08-01","2024-09-01","盛塘村","桥梁修复，长25米，宽3.5米",12.5,8,4.5,1,225,564,1,8,20,"目标：桥梁修建1座","解决村民农业生产问题；有效提高经济收入； 促进乡村振兴发展"]
[22,"乡村建设行动","农村基础设施","农村道路建设","江南镇","灯塔村","灯塔村砂石铺路","新建","灯塔村","2024-10-10","2024-11-10","灯塔村","砂石铺路4530米",18.12,10,8.12,1,195,785,null,8,23,"目标：砂石铺路4530米","方便村民农田耕种；使脱贫户增产；促进乡村振兴发展。"]
[23,"乡村建设行动","农村基础设施","农村道路建设","江南镇","灯塔村","灯塔村11组桥梁维修","维修","灯塔村","2024-08-10","2024-08-25","灯塔村","桥梁维修1座",8.2,5,3.2,1,195,785,null,8,23,"目标：桥梁维修1座","方便村民进出；使脱贫户增产；促进乡村振兴发展"]
[24,"乡村建设行动","农村基础设施","农村道路建设","江南镇","灯塔村","灯塔村孙洲2、3组机埠维修","维修","灯塔村","2024-09-01","2024-09-20","灯塔村","机埠复位两座及机电设备更换",10.5,5,5.5,1,195,785,null,8,23,"目标：机埠维修2座","方便村民农田耕种；使脱贫户增产；促进乡村振兴发展。"]
[25,"乡村建设行动","农村基础设施","农村道路建设","江南镇","牛湖村","牛湖村8-19组道路维修","维修","牛湖村","2024/\n5/5","2024/\n7/5","牛湖村","道路维修1条",25,10,15,1,310,1100,null,8,18,"目标：道路维修1条","通过砂石铺路方便群众运输，增加农户种养积极性扩大农业生产。"]
[26,"乡村建设行动","农村基础设施","农村道路建设","江南镇","长江村","长江村3、4、13、5组道路硬化","新建","3、4、13、5组","2024/\n5/1","2024/\n6/1","长江村","1800米",25,15,10,1,550,2489,1,22,62,"目标：道路硬化1800米","通过道路硬化方便群众运输，增加农户种养积极性扩大农业生产。"]
[27,"乡村建设行动","农村基础设施","农村道路建设","江南镇","谷花社区","谷花社区粮店路小学路维修、硬化","新建","谷花社区街道组","2024年 5月","2024年 5月","谷花社区","总长350米",18,17,1,1,800,3200,null,27,78,"目标：道路维修硬化350米","通过道路硬化方便群众运输，增加农户种养积极性扩大农业生产。"]
[28,"乡村建设行动","农村基础设施","道路硬化","江南镇","长江村","长江村10、11组道路加宽","加宽","10、11组","2024/\n4/1","2024/\n5/1","长江村","300米",8,5,3,1,550,2489,1,22,62,"目标1：维护稳定脱贫\n目标2：方便脱贫户及监测户等劳动力农业种养殖，可以提高脱贫户平均收入，降低贫困发生率。","通过道路拓宽方便群众运输，增加农户种养积极性扩大农业生产。"]
[29,"乡村建设行动","农村基础设施","农村道路建设","江南镇","灯塔村","灯塔村砖厂至二级渠道路硬化维修","新建","灯塔村","2024-10-01","2024-10-20","灯塔村","道路硬化维修3000平方米",48,17,31,1,195,785,null,8,23,"目标：道路硬化维修3000平方米","方便村民进出；使脱贫户增产；促进乡村振兴发展"]
[30,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","石岭村","江南镇石岭村主公路茶园组至廖家组段路面拓宽坑塘地段护坡砌墙建设","新建","石岭村","2024-10-20","2024-11-20","石岭村","护坡砌墙0.5公里",98.5,10,88.5,1,200,1500,null,10,20,"目标1：集体经济发展与产业建设\n目标2：发展经济方便农民出行增加农民经济收入   目标3：促进乡村振兴产业发展。","改善农业生产条件，增加脱贫户收入100-200元/年"]
[31,"乡村建设行动","农村基础设施","农村供水保障设施建设 ","江南镇","丁坊村","自来水安装","新建","丁坊村","2024/\n4/1","2024/\n5/1","丁坊村","自来水安装",20,15,5,1,6,396,1,14,14,"目标：通过自来水的安装，更好地改善了脱贫户、监测户的用水安全。","加强基础建设，方便群众用水及发展生产，增加群众收入。"]
[32,"乡村建设行动","农村基础设施","其他","江南镇","鸭栏村","鸭栏村沟渠疏浚","维修","鸭栏村","2024-08-01","2024-08-20","鸭栏村","机埠引水渠清淤、清杂合计长3400米，宽8米；鱼池组排灌渠1900米，宽5米",31,15,16,1,1014,3896,null,26,72,"目标：机埠引水渠清淤、清杂合计长3400米，宽8米；鱼池组排灌渠1900米，宽5米","集体经济发展和建设 ；彻底解决粮食生产条件；促进乡村振兴产业发展"]
[33,"乡村建设行动","农村公共服务","公共照明设施","江南镇","丁坊村","丁坊村三合组路灯安装","新建","丁坊村","2024-10-01","2024-10-20","丁坊村","路灯安装35盏",8.4,4,4.4,1,6,396,1,14,14,"目标：路灯安装35盏","完善了丁坊村基础建设，改善人居环境，方便了群众夜间出行，提高人民生活水平。"]
[34,"乡村建设行动","农村公共服务","公共照明设施","江南镇","江南村","江南村9组路灯安装","新建","江南村","2024-09-01","2024-09-10","江南村","路灯安装25盏",6,3,3,1,129,427,1,4,12,"目标：路灯安装25盏","完善了江南村基础建设，改善人居环境，方便了群众夜间出行，提高人民生活水平。"]
[35,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","江南镇","江南村","江南村14、15、16组机耕路维修","维修","江南村","2024-09-05","2024-09-15","江南村","道路修建1500米",6,3,3,1,129,427,1,4,12,"目标：道路修建1500米","加强基础建设，为产业发展提供条件，方便农产品运输，增加群众收入。该项目涉及农户106户428人，脱贫户及监测户6户14人。"]
[36,"乡村建设行动","农村基础设施","农村供水保障设施建设 ","江南镇","丁坊村","唐家组沟渠疏浚","维修","丁坊村","2024-10-10","2024-10-20","丁坊村","沟渠清淤5500米",6.5,4,2.5,1,6,396,1,14,14,"目标：沟渠清淤5500米","方便村民农田耕种；使脱贫户增产；促进乡村振兴发展。"]
[37,"产业发展项目","配套设施项目","小型农田水利设施建设","长安街道","杨田村","杨田村灾后重建","新建","杨田村","2024.7.1","2024.8.28","杨田村","下山桥拓宽维护加固：长10米，宽8米；山体滑坡：土石方3000立方米；水沟重建及驳岸：长度5.2公里（双向）",80,70,10,1,725,3995,1,16,31,"下山桥拓宽维护加固：长10米，宽8米；山体滑坡：土石方3000立方米；水沟重建及驳岸：长度5.2公里（双向）","方方便农户出行，利于农作物灌溉。"]
[38,"乡村建设行动","农村基础设施","农村道路建设","长安街道","荆竹山村","荆竹山村刘家组集中建房点连接路拓宽硬化。","新建","荆竹山村刘家组",2024.1,"2024.05.10","荆竹山村","路面拓宽硬化200米，路肩护坡，排水沟修建",17.65,5,12.65,1,83,428,0,10,29,"路面拓宽硬化200米，路肩护坡，排水沟修建","方便刘家、坳上等8个组的群众出行"]
[39,"产业发展项目","配套设施项目","小型农田水利设施项目","长安街道","集庄社区","长安街道集庄社区堰坝整修","改扩建","集庄社区","2024.10.20","2024.11.20","集庄社区","清淤1000方，驳岸300方",6,5,1,1,40,190,0,2,8,"清淤1000方，驳岸300方，","解决周边农田灌溉用水问题，有利于粮食增产，增加老百姓收入。"]
[40,"产业发展项目","配套设施项目","小型农田水利设施建设","坦渡镇","晓阳村","次咀组余家塘整修","改建","晓阳村次咀组","2024.7.1","2024.9.1","晓阳村","扩建塘面积7.8亩，清淤加深度3.5米，山塘整修堤坝护砌长38米，高2.8米。",14.54,11,3.54,1,29,114,0,10,37,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。","改善水利条件，提高作物产量，使农户增收400-600元"]
[41,"产业发展项目","配套设施项目","小型农田水利设施建设","坦渡镇","灯明村","畈屋组渠上山塘维修硬化","改建","灯明村畈屋组","2024.7.22","2024.10.25","灯明村","清淤250立方，塘堤长28米，高2.8米，底宽3.2米，六方块3050块",11.8,8,3.8,1,68,258,0,6,20,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。","改善水利条件，提高作物产量，使农户增收400-600元"]
[42,"产业发展项目","配套设施项目","小型农田水利设施建设","坦渡镇","桐梓铺社区","金咀组横塘整修","改建","金咀组","2024.10.1","2024.10.31","桐梓铺社区","清淤2664立方米",8,5,3,1,32,109,1,4,19,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。","改善水利条件，提高作物产量，使农户增收400-600元"]
[43,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","韩桥村","田畈组公路硬化","新建","韩桥村田畈组","2024.8.1","2024.8.10","韩桥村","长100米，宽4米，厚20公分",5.7,5,0.7,1,75,286,0,10,35,"1、道路畅通，给脱贫户解决出行难问题。2、减少运输成本，从而为脱贫户增收","使脱贫户增收800元以上"]
[44,"乡村建设行动","农村基础设施","农村道路建设通村通户","坦渡镇","韩桥村","公路硬化","新建","韩桥村米铺、周咀组","2024.11.1","2024.11.30","韩桥村","长1050米，宽3.5米，厚20公分",52,50,2,1,135,536,0,17,72,"1、道路畅通，给脱贫户解决出行难问题。2、减少运输成本，从而为脱贫户增收","使脱贫户增收800元以上"]
[45,"乡村建设行动","农村基础设施","产业路","坦渡镇","韩桥村","公路硬化及油路铺设","新建","马家组","2024.9.1","2024.9.30","韩桥村","公路硬化及油路铺设1200米",104,100,4,1,185,688,0,15,68,"1、道路畅通，给脱贫户解决出行难问题。2、减少运输成本，从而为脱贫户增收","使脱贫户增收800元以上"]
[46,"产业发展项目","配套设施项目","小型农田水利设施建设","坦渡镇","韩桥村","山塘清淤及整修","改建","茶山、彭湾、龚家、上屋、米铺组","2024.8.20","2024.10.18","韩桥村","清淤4200立方，填埋水管80米",17.3,15,2.3,1,205,690,0,11,39,"改建基础设施，有效改善脱贫户居民水体质量，提升山塘蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。","使脱贫户增收800元以上"]
[47,"乡村建设行动","农村基础设施","产业路","坦渡镇","定湖村","上下马蹄湖机耕路铺砂石","改建","定湖村上下马蹄湖","2024.8.18","2024.8.25","定湖村","长6千米，宽4米",6.2,5,1.2,1,180,723,0,12,42,"1、道路畅通，给脱贫户解决出行难问题。2、减少运输成本，从而为脱贫户增收","使脱贫户增收800元以上"]
[48,"产业发展项目","配套设施项目","小型农田水利设施建设","坦渡镇","坦渡村","凤形组排灌渠道硬化","改建","坦渡村凤形组","2024.11.27","2024.12.30","坦渡村","渠道硬化长380米、宽0.5米、高0.5米",7.3,7,0.3,1,142,468,0,7,17,"完善基础建设，解决脱贫户和农户水田灌溉困难，提高经济效益增收","改善水利条件，提高作物产量，为脱贫户和农户增收300-500元左右"]
[49,"乡村建设行动","农村基础设施","农村道路建设","桃林镇","白石村委会","白石村天车组道路山体滑坡整险","新建","白石村天车组","2024.9.1","2024.9.30","白石村委会","山体整险、清运土方300方",3.5,2,1.5,1,48,216,1,1,3,"保障道路畅通，确保村民们能安全出行，预防二次灾害发生，提升生态环境质量。","方便村民们出行，解除滑坡危及村民安全的重大隐患。"]
[50,"产业发展项目","配套设施项目","小型农田水利设施建设","桃林镇","源冲村委会","源冲村陈家组排水沟清淤及硬化","新建","源冲村陈家组","2024.9.20","2024.10.20","源冲村委会","全长65米，高1.3米，宽1米",5.5,5,0.5,1,63,286,1,2,7,"目标1：方便村民农田耕种；目标2：使村民们增产增收；目标3：促进乡村振兴发展。","改善耕种基础设施，提高村民们耕种积极性，致使村们增产增收。"]
[51,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","桃林镇","横铺村委会","横铺村下畈组公路维修、驳坎","新","横铺村下畈组","2024.9.20","2024.10.20","横铺村委会","驳坎长35米，公路维修40米",11.5,10,1.5,1,135,632,1,6,17,"解除了安全隐患，疏通了道路，保障村民人们的正常出行，促进乡村振兴经济发展。","给村民们出行带来了便利，保障了村民们的出行安全。"]
[52,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田镇","白羊田镇方山村","白羊田镇2024年殷家至登东道路拓宽","改建","殷家至登东",2024.8,2024.9,"白羊田镇方山村","殷家至登东道路拓宽全长1200米",31.17,8,23.17,1,806,2745,0,51,161,"完成殷家至登东道路拓宽硬化1200米，保障群众安全出行，激发群众发展生产的积极性，促进增收。","改善了生产生活条件，方便了村民出行，增强民众幸福感，激发群众发展生产的积极性。"]
[53,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田镇","白羊田镇","白羊田镇2024年双泉民生服务中心至海口道路水毁","改建","双泉民生服务中心至海口",2024.5,2024.6,"白羊田镇","长70米，坎高2米，面宽60厘米，底宽1.8米",35,10,25,1,352,753,1,6,19,"完成双泉民生服务中心至海口道路水毁，保障群众安全出行。","保障群众安全出行，激发群众发展生产的积极性，促进增收"]
[54,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田镇","白羊田镇双泉村","白羊田镇2024年石矶垅界碑至宋家洞道路拓宽","改建","石矶垅界碑至宋家洞",2024.8,2024.1,"白羊田镇双泉村","完成石矶垅界碑至宋家洞1300米道路拓宽至8米",30,5,25,3,1256,3453,2,22,67,"完成石矶垅界碑至宋家洞1300米道路拓宽至8米，提高双泉村、八百村、西山村村民出行安全。","保障群众安全出行，激发群众发展生产的积极性，促进增收"]
[55,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田镇","白羊田镇西山村","2024年白羊田镇西山村四房组至林场组、西金公路、东沙公路西湖庙路段、东沙公路大山段、村部至何山组公路水毀维修","改建","西山村四房组至林场组、西金公路、东沙公路西湖庙路段、东沙公路大山段、村部至何山组",2024.7,2024.8,"白羊田镇西山村","四房组至林场组公路长约40米滑坡，西金公路长约50米滑坡，东沙公路西湖庙路段滑坡60米，东沙公路大山段滑坡10处150米，村部至何山组公路滑坡60米",12.3,10,2.3,1,1011,3113,1,71,181,"完成四房组至林场组公路长约40米滑坡，西金公路长约50米滑坡，东沙公路西湖庙路段滑坡60米，东沙公路大山段滑坡10处150米，村部至何山组公路滑坡60米。","保障群众安全出行，激发群众发展生产的积极性，促进增收"]
[56,"乡村建设行动","农村基础设施","农村供水保障设施","白羊田镇","八百村","2024年白羊田镇八百村周前组马家塘清淤、衬砌","改建","周前组",2024.1,2024.11,"八百村","周前组马家塘清淤、衬砌。全长170米。高1米6",6.5,6,0.5,1,252,920,1,14,32,"完成周前组马家塘清淤、衬砌。全长170米。高1米6，为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为老百姓种植农作提供更多便利，提高生活生产质量，推动乡村产业振兴。"]
[57,"乡村建设行动","农村基础设施","道路建设","白羊田镇","双泉村","2024年白羊田镇双泉村付陈组至左家组道路拓宽","改建","付陈组-左家组",2024.11,2024.12,"双泉村","3.5米道路拓宽至6米，全长500米",21,10,11,1,220,895,1,13,28,"完成付陈组-左家组3.5米道路拓宽至6米，全长约500米，为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为出行和农作提供更多便利，提高生活质量，助力乡村振兴。"]
[58,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田镇","白羊田社区","白羊田社区庄上组至刘湾东头组道路提质改造","改建","白羊田社区庄上组、东头组、花园组",2024.4,2024.12,"白羊田社区","白羊田社区庄上组至刘湾东头组长500米，宽5米道路白改黑及划线",45,20,25,1,45,135,0,6,10,"完成白羊田社区庄上组至刘湾东头组长500米，宽5米道路白改黑及划线。为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为出行和农作提供更多便利，提高生活质量，助力乡村振兴。"]
[59,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田镇","八百村","2024年白羊田镇宋洞桥至贾家桥道路维修","改建","宋洞桥至贾家桥",2024.7,2024.8,"八百村","长1001.7米，宽4.5米",50,41,9,1,145,1097,1,20,26,"完成长宋洞桥至贾家桥道路维1001.7米，宽4.5米。为村民的出行安全提供了保障。","通过道路改建，为保障了村民的出行安全及农作物运输、农用机械进出提供了便利。"]
[60,"乡村建设行动","农村基础设施","农村供水保障设施","白羊田镇","八百村","2024年白羊田镇竹山组至三圣组沟渠疏浚","改建","竹山组至三圣组",2024.7,2024.8,"八百村","长450米，底宽50厘米，高60厘米",9.9,9,0.9,1,84,463,1,10,24,"竹山组至三圣组沟渠疏浚长450米，底宽50厘米，高60厘米，为村民农业用水灌溉提供保障。","通过沟渠疏浚激发群众发展生产的积极性，促进增收，改善农业生产条件，保障农业丰收。"]
[61,"产业发展项目","生产项目","水产养殖发展","聂市镇","聂市镇马垅村","叶桥垸水面生态养殖","新建","马垅村叶桥垸","2024年 1月","2024年 12月","马垅村","800亩水面生态养殖项目，由村集体统一实行人放天养，养殖草鱼、白鲢、桂花鱼、鲫鱼等四大家鱼常规渔业养殖。",25,20,5,1,753,3164,1,40,123,"巩固脱贫成效，壮大集体经济年收入约40万元，吸收脱贫劳动力就业，该项目涉及农户753户3164人，其中脱贫户40户123人。","解决脱贫户及农户就业"]
[62,"乡村建设行动","农村基础设施","\n农村道路建设（通村路、通户路、小型桥梁等）\n","聂市镇","聂市镇官田村","旭畈组至枫林路基拓宽","新建","聂市镇官田村","2024年 4月","2024年 9月","官田村","路基拓宽1.5米、长600米",4,3,1,1,740,2900,1,64,184,"改善农村产业发展条件增加农民收入，该项目涉及农户740户2900人，其中脱贫户64户184人。","加强基础建设，为产业发展提供条件，巩固脱贫成果。"]
[63,"乡村建设行动","农村基础设施","\n农村道路建设（通村路、通户路、小型桥梁等）\n","聂市镇","聂市镇红士村","老冲组水毁工路驳岸","新建","聂市镇红士村","2024年 7月","2024年 8月","红士村","老冲组水毁工路驳岸，方便群众出行及发展生产，建设规模，长20米，高5.2米",4.3,3,1.3,1,28,132,1,2,4,"方便群众出行以及发展农业生产。该项目涉及农户28户132人，其中脱贫户2户4人。","加强基础建设，为产业发展提供条件，巩固脱贫成果。"]
[64,"产业发展项目","配套设施项目","小型农田水利设施建设","聂市镇","聂市镇新安村","江院、昔冲山塘维修","新建","聂市镇新安村","2024年 10月","2024年12 月","聂市镇新安村","江院、昔冲2座山塘全面清淤1000余立方米、建新附属设施涵管25米，溢洪渠40米，地管60米。",10,8,2,1,90,380,null,4,7,"江院、昔冲2座山塘全面清淤1000余立方米、建新附属设施涵管25米，溢洪渠40米，地管60米。改善下游300余亩农田灌溉条件，涉及农户90户，380人，脱贫户1户4人。","带动农户，脱贫户发展产业，巩固脱贫成果。"]
[65,"乡村建设行动","农村基础设施","\n农村道路建设（通村路、通户路、小型桥梁等）\n","聂市镇","黄盖村","黄盖村防汛","新建","土咀垸、余桥垸、高桥垸","2024年 7月","2024年7 月 22日","黄盖村","土咀垸、余桥垸、高桥垸易损地段加固及灾后修复",20,15,5,1,368,1154,null,12,36,"土咀垸、余桥垸、高桥垸易损地段加固及灾后修复，方便群众发展农业生产及保障群众生命财产安全。该项目改良3200亩农田灌溉条件，涉及农户368户，1154人，脱贫户12户36人","带动农户，脱贫户发展生产，确保群众生命财产安全"]
[66,"乡村建设行动","农村基础设施","\n农村道路建设（通村路、通户路、小型桥梁等）\n","聂市镇","聂市镇长源村","长源村防汛","新建","长源村","2024年7","2024年10","长源村","新长源垸及九成撇洪渠、叶家桥撇洪渠易损地段加固及灾后修复",22,18,4,1,598,2151,null,17,36,"新长源垸及九成撇洪渠、叶家桥撇洪渠易损地段加固及灾后修复，方便群众发展农业生产及保障群众生命财产安全。该项目改良4000亩农田灌溉条件，涉及农户598户，21514人，脱贫户17户36人","带动农户，脱贫户发展生产，确保群众生命财产安全"]
[67,"乡村建设行动","农村基础设施","\n农村道路建设（通村路、通户路、小型桥梁等）\n","聂市镇","聂市镇同德村","同德村防汛","新建","聂市镇同德村","2024年 6月","2024年 7月","同德村","同德垸堤垸及撇洪渠易损地段加固及灾后修复",70,20,50,1,355,1250,null,12,32,"同德垸堤垸及撇洪渠易损地段加固及灾后修复，改良下游农田灌溉条件1100亩，方便群众发展农业生产及保障群众生命财产安全。该项目涉及农户398户，1194人，脱贫户17户36人。","带动农户，脱贫户发展生产，确保群众生命财产安全"]
[68,"产业发展项目","配套设施项目","小型农田水利设施建设","聂市镇","沿河社区","山墈组沟渠清淤","新建","沿河社区山墈组","2024年 10月","2024年 12月","沿河社区","沟渠清淤1000米，盖板500米",8,6,2,1,76,253,null,3,13,"方便群众农田灌溉，增产增收.","加强基础建设，为产业发展提供条件，巩固脱贫成果"]
[69,"乡村建设行动","农村基础设施","\n农村道路建设（通村路、通户路、小型桥梁等）\n","聂市镇","聂市镇凤形村","下冲组、付冲组、向冲组水毁驳岸工程恢复","新建","聂市镇凤形村","2024年 9月","2024年 12月","凤形村","下冲组、付冲组、向冲组水毁驳岸工程恢复（长250米，高2米）",10,5,5,1,149,860,null,11,28,"水毁驳岸工程恢复可有效灌溉农田作物，群众用水，稳固脱贫成效。该项目涉及农户149户860人，其中脱贫户11户28人","加强基础建设，为产业发展提供条件，巩固脱贫成果。"]
[70,"乡村建设行动","农村基础设施","\n农村道路建设（通村路、通户路、小型桥梁等）\n","聂市镇","聂市镇权桥村","下卢组汛期水毁桥梁修复","新建","聂市权桥村","2024年 9月","2024年 12月","权桥村","下卢组汛期水冲毁桥梁修复（长6.5米，宽4米，厚度30厘米）",8,6,2,1,152,690,null,5,16,"水毁桥梁修复恢复可有效灌溉农田作物，稳固脱贫成效。该项目涉及农户152户690人，其中脱贫户5户16人","加强基础建设，为产业发展提供条件，巩固脱贫成果。"]
[71,"乡村建设行动","农村基础设施","农村道路建设（通村路、通户路、小型桥梁等）","聂市镇","马垅村","沈上至乘石路连接路","新建","马垅村","2024年 9月","2024年 11月","马垅村","沈上至乘石路连接路，全长1000米，宽3.5米，厚0.2米",30,10,20,1,254,951,1,12,42,"方便群众出行以及发展农业生产。该项目涉及农户254户951人，其中脱贫户12户42人。","加强基础建设，为产业发展提供条件，巩固脱贫成果。"]
[72,"乡村建设行动","农村基础设施","农村道路建设（通村路、通户路、小型桥梁等）","聂市镇","聂市镇新安村","孙坳组、虎形组机耕路修建","新建","聂市镇新安村","2024年 9月","2024年 11月","聂市镇新安村","孙坳组至虎形组长3000米，宽3.5米机耕路修建",8,7,1,1,85,325,null,5,10,"修建孙坳组至虎形组长3000米，宽3.5米机耕路，改善农业生产条件，稳固脱贫成效。该项目涉及农户85户325人，其中脱贫户5户10人","加强农村道路建设，为农业生产，产业发展提供条件，巩固脱贫成果。"]
[73,"乡村建设行动","农村基础设施","农村道路建设（通村路、通户路、小型桥梁等）","聂市镇","聂市镇同德村","王家组山塘整修","新建","聂市镇同德村","2024年 11月","2024年12 月","聂市镇同德村","王家组山塘面积10亩，部分清淤，堤翻新加固，地管30米新做，改善灌溉面积450亩",3,2,1,1,90,390,null,1,5,"王家组山塘面积10亩，部分清淤，堤翻新加固，地管30米新做，改善灌溉面积450亩，涉及农户90户，390人，脱贫户1户2人。","带动农户，脱贫户发展产业，巩固脱贫成果。"]
[74,"乡村建设行动","农村基础设施","农村道路建设（通村路、通户路、小型桥梁等）","聂市镇","聂市镇汤畈村","临观组山塘驳岸清淤","新建","聂市镇汤畈村","2024年 12月1日","2024年1 2月30日","聂市镇汤畈村","清淤5亩，驳岸全长80米，宽0.5米，高2米。",8,5,3,1,38,152,null,2,4,"方便群众发展农业生产。该项目涉及农户38户152人，其中脱贫户12户4人。","加强基础建设，为产业发展提供条件，巩固脱贫成果。"]
[75,"乡村建设行动","农村基础设施","\n农村道路建设（通村路、通户路、小型桥梁等）\n","聂市镇","聂市镇同德村","新建组组级公路硬化工程项目","新建","聂市镇同德村","2024年 2月","2024年3 月","同德村","新建组组级公路路面硬化，全长550米，宽3米，厚30cm",18,12,6,1,238,1256,1,12,39,"改善农村道路基础设施建设，增加农民收入，该项目涉及农户238户1256人，其中脱贫户12户39人。","加强基础建设，为产业发展提供条件，巩固脱贫成果。"]
[76,"乡村建设行动","村庄规划编制(含修编)","村庄规划编制(含修编)","聂市镇","聂市镇乘岭社区","乘岭社区乡村规划提质项目","新建","聂市镇乘岭社区","2024年 10月","2024年 12月","聂市镇乘岭社区","对乘岭社区全村域范围进行整体策划。",10,10,0,1,708,2886,0,32,104,"对乘岭社区全村域范围进行整体策划。该项目涉及农户708户2886人，其中脱贫户32户104人","对乘岭社区全村域范围进行整体策划，加强基础建设，为社区发展提供条件，巩固脱贫成果。"]
[77,"乡村建设行动","农村基础设施","配套基础设施","五里牌街道","烟冲村","东后组产业路建设","新建","烟冲村东后组","2024.5","2024.6","烟冲村","1.修建长1.5千米，宽3米机械路；\n修建长5米，宽4米桥体；",12,10,2,1,102,451,null,5,21,"此路改建好之后可以提高农民的出行质量。","此路改建好之后可以提高农民的出行质量，达到农民平安出行的满意度，使农民家中的农产品外出销售，从而提高农民收入。"]
[78,"乡村建设行动","农村基础设施","配套基础设施","五里牌街道","新庄社区","公路维修","改建","次坡组","2024.12.01","2024.12.28","新庄社区","维修1公里",24,10,14,1,120,720,null,6,10,"方便居民平安出行","改善居民交通安全，提高居民生活水平"]
[79,"乡村建设行动","农村基础设施","农村道路建设","云湖街道","大岭村","组级公路维修拓宽","改建","蒋家组至黄家组",2024.8,2024.12,"大岭村","道路维修拓宽800米，宽4米，修一座通路桥",100,10,90,1,108,1324,1,1,1,"蒋家组至黄家组道路维修拓宽800米，宽4米，修一座通路桥","减少群众日常出行成本，促进产业发展，带动农户稳定增收，改善人居环境。"]
[80,"乡村建设行动","农村基础设施","农村道路建设","云湖街道","板桥村","主公路水毁维修拓宽","改建","板桥组至白果树",2024.9,2024.11,"板桥村","道路维修护坡场160米，拓宽长140米宽2米。",17,4,13,1,92,427,1,13,48,"板桥组至白果树屋场村主公路水毁维修护坡长160米，道路拓宽长140米，拓宽宽2米。","消除交通隐患，减少群众日常出行成本，促进产业发展，带动农户稳定增收，改善人居环境。"]
[81,"乡村建设行动","农村基础设施","农村道路建设","云湖街道","大岭村","同德至港下过港桥建设","新建","同德组至王禾港下组",2024.9,2024.12,"大岭村","大岭村同德组至王禾社区港下组新修一座过港桥，桥面宽5米，桥跨度16米，高2.4米，桥面混凝土厚度30公分",26,null,26,1,324,1184,1,1,3,"修建一座过港桥，桥面宽5米，桥跨度16米，高2.4米，桥面混凝土厚度30公分","方便农户日常出行，降低生产成本，带动产业发展。"]
[82,"乡村建设行动","农村基础设施","农村道路建设","云湖街道","大岭村","谢坡塘水库机埠等引水工程建设","新建","同德组",2024.9,2024.12,"大岭村","大赵组至同德德长300米管网防锈焊接，砼镇墩及支墩建设，引水设备购买安装及进水渠清淤。",25,null,25,1,324,1184,1,1,3,"长300米管网防锈焊接，砼镇墩及支墩建设，引水设备购买安装及进水渠清淤。","保障600多亩农田灌溉用水安全，降低农户生产成本，促进农户稳定增收。"]
[83,"乡村建设行动","农村基础设施","其他","云湖街道","王禾社区","水毁灌溉渠道疏通、维修及滑坡隐患整治","新建","王禾社区",2024.7,2024.12,"王禾社区","蒋一二组中渠水毁疏通300米，港下组渠道水毁疏通150米按管筒60米",14,8,6,1,226,803,1,1,1,"蒋一二组中渠水毁疏通300米，港下组渠道水毁疏通150米按管筒60米","保障农田管排水安全和农户日常出行安全、促进稳定增收"]
[84,"产业发展项目","配套设施项目","小型农田水利设施建设","长塘镇","古洞村","龙四组机耕路硬化","新建","龙四组","2024.7.1","2024.9.30","古洞村","道路全长518米",36,30,6,1,185,627,1,5,16,"通过水利维修，解决脱贫户及广大群众的灌溉用水，促进农业增产增收，使群众满意度达到100%","改善一般群众与脱贫户的生产生活，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，使群众满意度达到100%"]
[85,"产业发展项目","配套设施项目","小型农田水利设施建设","长塘镇","何洞村","李家组农田生产设施建设","新建","李家组","2024.7.20","2024.8.20","何洞村村委会","道路拓宽200米，地坪清淤填埋300平方",6,5,1,1,75,220,1,3,8,"通过道路维修，解决脱贫户及广大群众的的出行问题，促进农业增产增收，使群众满意度达到100%","改善一般农户与脱贫户的生产生活，有利于农田灌溉，方便村民出行，增加经济收入"]
[86,"乡村建设行动","农村基础设施","农村道路建设","长塘镇","托坝社区","塘东组道路硬化","新建","塘东组","2024.11.10","2024.12.30","托坝社区","硬化长度150米 宽4米 厚0.2米",7,5,2,1,260,480,1,3,4,"完成塘东组组内道路硬化，完善基础设施，为周边群众及脱贫户提供便利，使群众满意度100%","完成塘东组组内道路硬化，完善基础设施，为周边群众及脱贫户农业运输提供便利。"]
[87,"产业发展项目","配套设施项目","小型农田水利设施建设","长塘镇","长塘镇","马安村杨四屋组涵洞维修加固","改建","石田村马安村","2024.8.30","2024.12.30","长塘镇","涵洞长470米宽1米高1.5米",50,40,10,2,500,3000,1,9,20,"通过水利维修，解决脱贫户及广大群众的灌溉用水，促进农业增产增收，使群众满意度达到100%","改善一般群众与脱贫户的生产生活，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，使群众满意度达到100%"]
[88,"产业发展项目","配套设施项目","小型农田水利设施建设","长塘镇","长塘镇","石田港犁头港清淤疏浚生态护坡、绿化","扩建","石田村柳厂村","2024.8.30","2024.12.30","长塘镇","长5000米",100,80,20,2,500,3000,1,9,20,"通过水利维修，解决脱贫户及广大群众的灌溉用水，促进农业增产增收，使群众满意度100%","改善一般群众与脱贫户的生产生活，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，使群众满意度达到100%"]
[89,"乡村建设行动","人居环境整治","农村垃圾治理","长塘镇","长塘镇","长塘镇环境卫生基础设施","新建","长塘镇","2024.8.30","2024.12.30","长塘镇","购买环境卫生垃圾桶3500个",60,40,20,8,8792,28592,8,191,548,"完善全镇垃圾桶个数，为广大脱贫户以及群众创造更好的生活条件，使群众满意度达到100%","完善社区基础设施建设，为社区脱贫户以及广大群众创造了更好、更便利的生活条件，为群众提供安全保障，使群众满意度达到100%"]
[90,"产业发展项目","配套设施项目","小型农田水利设施建设","长塘镇","石田村","灌溉渠道维修","重建","石田片","2024.1.1","2024.5.1","石田村","长1000米、宽0.6米、高0.6米",5,5,0,1,"280户",1120,1,7,18,"灌溉渠道，为石田村脱贫户以及广大群众灌溉用水，群众满意度100%。","灌溉渠道，为石田村脱贫户以及广大群众灌溉用水，群众满意度100%。"]
[91,"产业发展项目","配套设施项目","引调水工程","临湘市",null,"临湘市“引团济龙”引调水工程","新建","临湘市詹桥镇、羊楼司镇",2025,2027,"临湘市水利局","设计年均引调水量4200万m3，引水流量3.2m3/s",200,200,null,93,67435,368543,12,340,1853,"为龙源水库补充水源，改善和保障龙源灌区灌溉用水和临湘城区用水及周边乡镇人畜用水条件，提高区域水资源配置水平，促进临湘市农业发展。","灌溉用水保证率从无工程时的40%提高至81%；供水保证率从无工程时的76.5%提高至96.8%"]
[92,"产业发展项目","配套设施项目","灌区建设、排涝能力建设等","临湘市",null,"2024年增发国债项目地方配套资金（水利）","新（改）建、","临湘市各乡镇",2024.4,2024.12,"临湘市水利局","新建幸福灌区、渭田湖灌区；江南灌区、龙源灌区节水配套改造；排涝能力建设；铁山咀低排闸除险加固、鸭栏低排闸除险加固、小型病　险水库除险加固、信息化建设等",406.03,406.03,null,45,32561,165865,6,180,985,"至2024年11月底，主体工程建设完成，2024年12月底，项目资金支付完成。","改善当地居民生产生活用水条件，提高区域防洪排涝能力，提高百姓幸福指数。"]
[93,"产业发展项目","配套设施项目",null,"临湘市","黄盖湖村、三界村、贺畈社区、灯塔村、板桥村、如斯村、文白社区、梧桐铺社区、联合村、杨田村等","临湘市2024年小型农业水利设施建设","改建","临湘市各镇（街道）相关村、组",2024.9,2024.12,"项目建设相关村（社区）","山塘清淤238座，机埠改造21处，节水改造渠道5.5km，山上经济作物山塘清淤31处。",840,840,null,103,850,2720,6,40,152,"提高山塘蓄水能力","改善实施村灌溉条件、提高农产品种植产量"]
[94,"产业发展项目","加工流通项目","农产品仓储保鲜冷链基础设施建设","临湘市","雅团村等","临湘市2024年农产品产地冷藏保鲜设施建设项目","新建","雅团村等","2024.7","2024.11","临湘市农业农村局市场信息与对外交流股","完成4个示范家庭农场、农民合作社示范社和已注册登记的农村集体经济组织实施主体的农产品产地产地冷藏保鲜设施建设，每个实施主体冷库库容控制在1000立方米以下。",197,197,null,4,82,528,1,4,15,"加强农产品产地冷藏保鲜设施建设，不断提升设施综合利用效率，满足田头贮藏保鲜和商品化处理需要，打造支撑农产品上行的产地综合服务平台。","企业+基地+村集体+农户，农户入股分红及务工相结合"]
[95,"产业发展项目","金融保险配套项目","新型经营主体贷款贴息","临湘市",null,"临湘市新型经营主体贷款贴息","贷款利息补贴","临湘市各乡镇",2024.3,2024.12,"临湘市农业农业村局","临湘市新型农业经营主体贷款利息贴息",231,231,null,null,81,{"$nulls":4},"减轻全市新型农业经营主体融资成本负担","通过对新型农业经营主体贷款贴息，促进新型农业经营主体加大对农业投入，带动周边产业发展，增加农民收入"]
[96,"产业发展项目","生产项目","种植业基地","临湘市",null,"集中育秧设施建设","新建","临湘市","2024年4月","2024年12月","临湘市农业农村 局","集中育秧设施建设购置育秧盘补贴。",300,300,null,10,275,867,4,73,160,"项目一是稳定粮食生产面积，增加粮食产量；二是新型经营主体和龙头企业发挥带动作用；三是鼓励、促进脱贫户种植的积极性，四是增加脱贫户种植收益，防止返贫风险。","通过有偿或无偿为种植户（贫困种植户）提供己育好的水稻秧苗，保障大田秧苗的数量、质量，减少无技术，无人工育不好秧的风险。提供优良，高产的水稻秧苗确保粮食产量的增加，种植收益的增加。"]
[97,"产业发展项目","生产项目","种植业基地","临湘市","木形村、双港村、忠防社区居委会、响山村、汀畈社区居委会、沙坪村、马安村、黄金村、清泉居委会","岳阳市临湘市忠防镇等四个乡镇木形村等九个村高标准农田建设项目(二〇二四年)","新建/改造","忠防镇、长塘镇、羊楼司镇、桃林镇","2024-10","2025-02","临湘市农业农村局","1：土地平整228.63亩，进出平衡地块耕地恢复28.87亩。\n2：山塘整治11座，整修拦水坝9座，泵站8座(其中新建6座，整修2座)、输水管16条长4563m，骨干灌渠修筑219条长48460m，其中新建37条，长10255m，整修182条，长38205m。骨干排渠修筑44条长8926m，其中新建6条，长2410m，整修38条，长6516m。进出水口1755座，闸门448座，盖板涵778座，人行桥753座，跌水222座，过路涵管359座，量水设施258处，路渠标牌269处，生物通道及取水码头54座。\n3：修筑机耕路56条，长22085m，其中新建18条，长5971m，整修38条，长16114m，田间道路包含级配碎石机耕路45条，长16031m，硬化机耕路11条，长6054m。错车道87座，掉头点27座，交叉路口(T字路口)58座，坡口231座，机耕桥1座，挡土墙一处42m。",1172,{"$f":"N102","v":1172},0,9,{"$f":"[2]入库项目申报分类汇总表!H82","v":0},{"$f":"[2]入库项目申报分类汇总表!I82","v":0},{"$f":"[2]入库项目申报分类汇总表!J82","v":0},100,200,"目标 1:完成土地平整228.63亩，进出平衡地块耕地恢复28.87亩。\n目标 2：完成山塘整治11座，整修拦水坝9座，泵站8座(其中新建6座，整修2座)、输水管16条长4563m，骨干灌渠修筑219条长48460m，其中新建37条，长10255m，整修182条，长38205m。完成骨干排渠修筑44条长8926m，其中新建6条，长2410m，整修38条，长6516m。修筑进出水口1755座，闸门448座，盖板涵778座，人行桥753座，跌水222座，过路涵管359座，量水设施258处，路渠标牌269处，生物通道及取水码头54座。\n目标 3：完成修筑机耕路56条，长22085m，其中新建18条，长5971m，整修38条，长16114m，田间道路包含级配碎石机耕路45条，长16031m，硬化机耕路11条，长6054m。错车道87座，掉头点27座，交叉路口(T字路口)58座，坡口231座，机耕桥1座，挡土墙一处42m。","企业+村集体+农户，劳务用工和绩效收益相结合"]
[98,"产业发展项目","配套设施项目","设施农业建设项目","临湘市","乘岭社区、骆平村","临湘市2024年设施农业建设项目","新建","乘岭社区、骆平村","2024.10.1","2024.12.31","乘岭社区、骆平村","乘岭社区建设:260亩水肥一体化喷淋滴灌网（棚外）及配套设施；骆平村建设：新建鸡舍大棚1700平方米，蛋鸡智能化养殖设备1套",111,111,0,2,1195,4377,0,9,32,"2024年度新建水肥一体化喷淋滴灌网（棚外）及配套设施260亩，新建鸡舍大棚1700平方米，农业生产设施条件明显改善，减轻农药化肥使用量，减少环境污染，提高周边劳动力岗位及劳务收入，受益群众满意度大于90%。","通过以务工、收购农产品、提供服务等方式与农户建立利益联结机制"]
[99,"产业发展项目","加工流通项目","\n农产品仓储保鲜冷链基础设施建设","临湘市",null,"2023年县域经济奖励资金","奖补","临湘市",2024.01,"2024.11","临湘市农业农村局","1、农作物品种改良、品种更新换代及新产品研发；2、农产品加工、冷链仓储物流设施设备、产地商品化处理和初加工设施设备；3、基础设施建设、品牌宣传等。",500,200,300,5,100,200,2,30,50," 1:对脱贫户进行产业帮扶，提升脱贫户发展特色产业的积极性。\n2：对脱贫户开展送种苗、技术指导、保底回收、劳动务工、土地流转等帮扶措施。\n 3：增加脱贫户（监测户）的产业收益，使监测户人均增加300元/户的收入，防止返贫风险。","龙头企业+基地+农户"]
[100,"产业发展项目","生产项目","种植业","临湘市",null,"2024年省帮扶产业发展\n重点项目","改建","羊楼司镇、五里街道等",2024.07,2024.12,"临湘市农业农村局","重点支持水果、茶叶、蔬菜、中药材4类帮扶主导产业分类发展。其中巩固类重点支持品种改良、品种更新换代、新产品开发及新技术、新工艺引进，农产品精深加工，副产物综合利用和以农业产业为主体的一二三产业融合发展；升级类重点支持生产基地标准化、设施化、机械化建设，农（林）产品产地商品化处理和初加工、冷链仓储物流设施设备建设，农产品品牌打造和产销对接，促进解决农产品“卖难”问题。",265,212,53,6,410,1250,2,265,615,"对村集体进行产业帮扶措施，通过该项目一是鼓励、促进村集体发展产业的积极性，二是增加脱贫户（监测户）发展产业的收益，防止返贫风险。","企业+基地+村集体+农户，劳务用工和产业分红相结合"]
[101,"产业发展项目","生产项目","种植业","临湘市","石田村、桐梓铺社区、长岭社区、鸭栏村、灯塔村","岳阳市市级示范社\n重点培育项目","新建","长塘镇、坦渡镇、江南镇","2024年1月","2024年12月","临湘市农业农村局","岳阳市市级农民合作社重点培育，以奖代投",19,19,null,5,267,856,1,38,105,"帮助提升运营质量、强化服务带动能力，进一步促进高质量发展","农户+农民合作社的经营模式：农户为合作社提供劳务用工，合作社为农户提供社会化服务"]
[102,"产业发展项目","加工流通项目","加工业","临湘市",null,"优势百亿产业","以奖代投","临湘市","2024年1月","2024年12月","临湘市农业农村局","1、生产设备升级改造；2、年加工3000吨黄精生产线等。",30,20,10,2,30,50,1,4,6," 1:对脱贫户进行产业帮扶，提升脱贫户发展百亿优势特色产业的积极性。\n2：增加脱贫户（监测户）的产业收益，使监测户人均增加300元/户的收入，防止返贫风险。","龙头企业+基地+农户"]
[103,"产业发展项目","配套设施项目","小型水利设施","临湘市","中山湖渔场","大堤维修","维修","中山湖渔场","2024年11月底","2024年12月底","农业农村局","大堤900米维修，用土方加宽加固",40,20,20,1,150,600,{"$nulls":3},"由于风浪冲洗，使大堤变窄，容易垮塌，所以必须加宽加固，不使内垸2100亩水田受淹。","保障群众的生产和生活"]
[104,"乡村建设行动","农村基础设施","农村道路建设","临湘市","横河堤","新发组道路硬化","新建","横河堤新发组","2024.10.8","2024.10.28","农业农村局","道路硬化，长486米，宽4米，厚20厘米",26.5,10,16.5,2,126,615,null,25,76,"硬化道路486米，解决320亩农田生产运输困难问题","解决新发组及附近群众交通运输难题，方便上岸渔民、群众生活生产"]
[105,"产业发展项目","配套设施项目","小型水利设施","临湘市","白沙洲","龙虾池平整旱地","土地平整","白沙洲畜牧良种场","2024年11月底","2024年12月底","农业农村局","内垸龙虾池50亩平整为旱地",26,20,6,1,56,283,{"$nulls":3},"平整旱地50亩，群众人均增收400元","保障群众的生产和生活"]
[106,"乡村建设行动","人居环境整治","农村污水治理","临湘市","白沙洲","渠道清淤",null,"白沙洲畜牧良种场","2024年11月底","2024年12月底","农业农村局","垸内6条沟渠需清理",12,10,2,1,56,283,{"$nulls":3},"垸内6条沟渠，约1500米，保障200多亩良田生产","保障群众的生产和生活"]
[107," 乡村建设行动","农村基础设施","农村道路建设","临湘市","种猪种鸡场","谭家桥桥梁维修","维修","杨田路1号","2024.9.20","2024.10.5","农业农村局","维修桥梁一座",5.86,5,0.86,3,180,1200,1,11,20,"谭家桥加装安全防护栏，桥墩两侧和路面维修","方便群众生产生活安全出行"]
[108," 乡村建设行动","农村基础设施","农村道路建设","临湘市","新建渔场","王家、张山两组道路硬化","新建","新建渔场","2024.9.13","2024.10.08","农业农村局","道路硬化，长470米，宽4米，厚20厘米",17,10,7,2,95,503,null,15,53,"道路硬化，长470米，宽4米，厚20厘米","解决本场和周边村270亩农田生产运输困难问题"]
[109,"乡村建设行动","农村基础设施","农村道路建设","忠防镇","马家洞村","忠防镇马家洞村谢龙至大同组公路拓宽硬化","改建","马家洞村",2024.8,2024.9,"马家洞村委会","道路设施拓宽500米，宽1.5米 ",9,9,0,1,368,1100,1,30,90,"完善基础设施，提高群众出行安全","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，增加了脱贫户及村民的生活收入，群众满意度100%。"]
[110,"乡村建设行动","农村基础设施","农村道路建设","忠防镇","忠防社区","忠防镇忠防社区砖屋组道路提质改造","改建","忠防社区",2024.8,2024.9,"忠防社区","路面提质改造150米",5,5,0,1,26,122,0,4,7,"完善基础设施，提高群众出行安全","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，增加了脱贫户及村民的生活收入，群众满意度100%。"]
[111,"乡村建设行动","农村基础设施","农村水利建设","忠防镇","雁峰村","忠防镇雁峰村坳背组沟渠改建及硬化","改建","雁峰村",2024.8,2024.8,"雁峰村","水毁管道修复500米",15,15,0,1,55,135,0,3,6,"全长500米。保障村民生产生活用水，提高农业生产","保障脱贫户和周边群众的生产生活用水，增加脱贫户和周边群众的农业收入，群众满意度100%。"]
[112,"乡村建设行动","农村基础设施","农村道路建设","忠防镇","木形村","木形永洞组机械道路拓宽工程","改建","永洞组",2024.9,2024.9,"木形村","拓宽长1300米，宽4.5米",22,22,0,1,32,160,0,14,35,"完善基础设施，提高群众出行安全","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，增加了脱贫户及村民的生活收入，群众满意度100%。"]
[113,"乡村建设行动","农村基础设施","农村道路建设","忠防镇","响山村","响山村生态园路基建设","改建","响山村响山组",2024.8,2024.12,"响山村","全长1.3公里，宽6米，水泥硬化600平方米",18,18,0,1,75,320,0,5,7,"完善基础设施，提高群众出行安全","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，增加了脱贫户及村民的生活收入，群众满意度100%。"]
[114,"乡村建设行动","农村基础设施","农村桥梁建设","忠防镇","响山村","响山村生态园新建桥梁工程","新建","响山村响山组",2024.8,2024.12,"响山村","全长20米，宽4.5米，高6.5米",38,38,0,1,75,320,0,5,7,"完善基础设施，提高群众出行安全","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，增加了脱贫户及村民的生活收入，群众满意度100%。"]
[115,"乡村建设行动","农村基础设施","其  他","忠防镇","响山村","响山村生态园新建钓鱼台工程","新建","响山村响山组",2024.8,2024.12,"响山村","新建钓鱼台200个",15,15,0,1,75,320,0,5,7,"增加了脱贫户及村民的生活收入","增加了脱贫户及村民的生活收入，群众满意度100%。"]
[116,"乡村建设行动","农村基础设施","农村水利建设","忠防镇","响山村","忠防镇响山村陆家组河港护坡工程","新建","响山村陆家组",2024.8,2024.12,"响山村","全长160米，宽1.8米，高4.5米",45,45,0,1,130,526,0,9,15,"完善基础设施，提高群众出行安全","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，增加了脱贫户及村民的生活收入，群众满意度100%。"]
[117,"产业发展项目","配套设施项目","小型农田水利建设","忠防镇","响山村","忠防镇响山村刘二组河港护坡工程","新建","响山村刘二组",2024.8,2024.12,"响山村","长85米  高3.5米  宽1.5米，约450立方",16,16,0,1,75,320,0,5,7,"全长85米。保障村民生产生活用水，提高农业生产","保障脱贫户和周边群众的生产生活用水，增加脱贫户和周边群众的农业收入，群众满意度100%。"]
[118,"乡村建设行动","农村基础设施","农村供水保障设施建设","忠防镇","木形村","忠防镇木形片区集中供水工程","新建","木形村祠堂组",2024.1,2024.12,"木形村","新建木形水厂日供水960吨， 供水范围5各村，用地面积1875平方米",999.44,999.44,0,5,316,2136,0,46,128,"新建水厂。保障村民生产生活用水，提高农业生产","保障周边五个村脱贫户和周边群众的生产生活用水，增加脱贫户和周边群众的农业收入，群众满意度100%。"]
[119,"产业发展项目","配套设施项目","小型农田水利建设","忠防镇","雁峰村","忠防镇雁峰村坳背组沟渠改建及硬化","改建","雁峰村",2024.8,2024.9,"雁峰村","水毁管道修复500米",15,15,0,1,55,135,0,3,6,"全长500米。保障村民生产生活用水，提高农业生产","保障脱贫户和周边群众的生产生活用水，增加脱贫户和周边群众的农业收入，群众满意度100%。"]
[120,"产业发展项目","配套设施项目","小型农田水利建设","忠防镇","马家洞村","忠防镇马家洞村浏阳片水毁修复工程","新建","马家洞村浏阳组",2024.8,2024.12,"马家洞村委会","水毁修复，公路户基修复100米，沟渠修复100米、公路滑坡清理60米",6,6,0,1,28,98,0,4,11,"100米道路修复完善基础设施，提高群众出行安全","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，增加了脱贫户及村民的生活收入，群众满意度100%。"]
[121,"乡村建设行动","农村基础设施","其他","忠防镇","坵坪社区","忠防镇坵坪社区老屋及陈家组路灯安装工程","新建","坵坪社区老屋及陈家组",2024.8,2024.12,"坵坪社区","新安装路灯40盏",8,8,0,1,43,162,0,2,8,"新增安装路灯40盏，提高群众出行安全","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，群众满意度100%。"]
[122,"乡村建设行动","农村基础设施","农村道路建设","忠防镇","汀畈社区","忠防镇汀畈社区何山组组级公路拓宽硬化","新建","何山组",2024.8,2024.12,"汀畈社区","拓宽2米总宽3.5，长360米",12,12,0,1,40,135,0,2,8,"完善基础设施，提高群众出行安全","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，增加了脱贫户及村民的生活收入，群众满意度100%。"]
[123,"乡村建设行动","农村基础设施","农村道路建设","忠防镇","雁峰村","忠防镇雁峰村下屋组公路护坡","新建","下屋组",2024.8,2024.12,"雁峰村","砌坎及护坡高12米、长30米、宽3米",15,15,0,1,55,135,0,3,6,"完善基础设施，砌坎及护坡高12米、长30米、宽3米","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，增加了脱贫户及村民的生活收入，群众满意度100%。"]
[124,"乡村建设行动","农村基础设施","农村道路建设","忠防镇","响山村","大石坳旅游景点旅游公路白改黑","新建","响山村",2024.7,2024.11,"忠防镇人民政府","旅游公路白改黑2.8km；破板换板及拓宽800米；纵向排水沟500米；一个公厕（45平方米）",191.7,140,51.7,1,201,790,0,5,7,"完成旅游公路白改黑15400m²，破板换板及拓宽800米；纵向排水沟500米；一个公厕（45平方米）","保障脱贫户脱贫户和周边群众的出行安全、增加脱贫户和周边群众的生活收入，群众满意度100%"]
[125,"乡村建设行动","农村基础设施","其他","忠防镇","响山村","大石坳旅游景点网红洞（幽深莫测）","新建","响山村",2024.7,2024.11,"忠防镇人民政府","网红洞人工挖洞660m³、洞内金景观建设",135,0,135,1,77,341,0,6,15,"完成网红洞人工挖洞660m³、洞内金景观建设","带动周边旅游产业链的发展，增加创业就业机会，增加脱贫户和周边群众的生活收入，群众满意度100%"]
[126,"乡村建设行动","农村基础设施","农村道路建设","忠防镇","木形村","木形村红色文旅活动中心配套项目","新建","木形村",2024.7,2024.11,"忠防镇人民政府","木形村进村公路白改黑19800m²，安装护栏2000m、路灯132盏，巩固护坡1506m²。",269.03,139,130.03,1,316,2136,0,46,128,"完成木形村进村公路白改黑19800m²，安装护栏2000m、路灯132盏，巩固护坡1506m²。","保障脱贫户和村民安全出行，减少交通事故，提高了生活质量，增加了脱贫户及村民的生活收入，群众满意度100%。"]
[127,"乡村建设行动","农村基础设施","农村道路建设","忠防镇","响山村","响山狮子山旅游配套项目基础设施","新建","响山村",2024.7,2024.11,"忠防镇人民政府","旅游公路白改黑3.8公里，破板更换及道路拓宽1000米，新建纵向排水沟750米",240.2,120,120.2,1,198,698,0,6,11,"完成旅游公路白改黑3.8公里，破板更换及道路拓宽1000米，新建纵向排水沟750米。","保障脱贫户脱贫户和周边群众的出行安全、增加脱贫户和周边群众的生活收入，群众满意度100%"]
[128,"乡村建设行动","农村基础设施","农村道路建设","忠防镇","响山村","响山狮子山旅游配套项目娱乐设施","新建","响山村",2024.7,2024.11,"忠防镇人民政府","构建攀岩设施；飞拉达设施；水上游船设施，露天泳池建设（开放设施），水上休息亭建设（开放设施）等。",115,0,115,1,208,798,0,5,8,"完成构建攀岩设施；飞拉达设施；水上游船设施，露天泳池建设（开放设施），水上休息亭建设（开放设施）等。","带动周边旅游产业链的发展，增加创业就业机会，增加脱贫户和周边群众的生活收入，群众满意度100%"]
[129,"产业发展项目","生产项目","种植业基地","忠防镇","响山村","忠防社区集体经济合作社育秧工厂","新建","忠防社区",2024.7,2024.11,"忠防镇人民政府","育秧工厂车间建设、水泥地板900m²、轻钢结构大棚车间900m²、运输皮带、水稻育秧硬盘、托盘30000个、连栋大棚（塑料大棚）10亩、浸种池、大棚秧盘喷水设备、育秧流水线、叠盘机、送盘机、打浆机、自动送土机、筛土机一套。",279.25,200,79.25,1,26,122,0,4,7,"完成育秧工厂车间建设、水泥地板900m²、轻钢结构大棚车间900m²、运输皮带、水稻育秧硬盘、托盘30000个、连栋大棚（塑料大棚）10亩、浸种池、大棚秧盘喷水设备、育秧流水线、叠盘机、送盘机、打浆机、自动送土机、筛土机一套。","增加了脱贫户及村民的生活收入，群众满意度100%。"]
[130,"产业发展项目","生产项目","种植业基地","忠防镇","木形村","高山油茶产业发展项目","新建","木形村、响山村、马家洞村、忠防社区",2024.7,2024.11,"忠防镇","新造油茶高产林400亩，低产林抚育改造1100亩，修建砂石产业路、灌溉沟、林道，并购置移动式可调动力喷雾器、割灌机、割灌机、水泵等。",300.6,185,115.6,4,560,2832,1,190,554,"完成新造油茶高产林400亩，低产林抚育改造1100亩，修建砂石产业路、灌溉沟、林道，并购置移动式可调动力喷雾器、割灌机、割灌机、水泵等。","利于脱贫户自力更生，利用鼓励种养增加收入保障脱贫成效，增加周边群众收入。"]
[131,"乡村建设行动","农村基础设施","农村水利建设","忠防镇","木形村","忠防镇安全饮水工程泵站建设工程、供水及设备及管网建设","新建","木形村、新田村、双港村、响山村",2024.7,2024.11,"忠防镇","泵站建设土石方工程31900.00m³、建筑工程400m²，过滤器、吸附器、超滤器、反渗透器、管线安装12000m、安装控制阀门并建设阀门井。",742.7922,552,190.7922,4,308,1438,0,154,411,"完成泵站建设土石方工程31900.00m³、建筑工程400m²，过滤器、吸附器、超滤器、反渗透器、管线安装12000m、安装控制阀门并建设阀门井。","保障脱贫户和周边群众的生产用水、增加脱贫户和周边群众的农业收入，群众满意度100%"]
[132,"乡村建设行动","农村基础设施","农村供水保障设施建设","忠防镇","木形村","忠防镇安全饮水工程泵站设备及安装工程，辅助设施设备","新建","木形村、新田村、双港村、响山村",2024.7,2024.11,"忠防镇","泵机组设备及安装、管道、阀门及安装7000m、电气控制系统设备及安装。辅助设施设备项目包括泵站管理用房及设备、通风、照明、消防等辅助设施、泵站与外部的连接道路建设1020m²，泵站设备及安装工程项目包括泵机组设备及安装（过滤器1台、吸附器1台、超滤器1台、反渗透器1台）、管道、阀门及安装、电气控制系统设备及安装。",367.408,178,189.408,4,308,1438,0,154,411,"完成泵机组设备及安装、管道、阀门及安装7000m、电气控制系统设备及安装。辅助设施设备项目包括泵站管理用房及设备、通风、照明、消防等辅助设施、泵站与外部的连接道路建设1020m²，泵站设备及安装工程项目包括泵机组设备及安装（过滤器1台、吸附器1台、超滤器1台、反渗透器1台）、管道、阀门及安装、电气控制系统设备及安装。","保障脱贫户和周边群众的生产用水、增加脱贫户和周边群众的农业收入，群众满意度100%"]
[133,"产业发展项目","配套设施项目","小型农田水利建设","忠防镇","响山村","忠防镇响山村河港河道清淤及排水设施","新建","响山村",2024.7,2024.11,"响山村委会","预计河道清淤13000多方、管道200米",24.16,0,24.16,1,260,820,0,8,29,"完成河道清淤13000多方、管道200米","改善河流水质和生态环境，促进生物多样性保护和水资源可持续利用提升。村民的居住环境和幸福感，促进乡村旅游产业的发展，为村民增加经济收入来源。"]
[134,"产业发展项目","配套设施项目","小型农田水利建设","忠防镇","响山村","忠防镇响山村河港护坡加固","新建","响山村",2024.7,2024.11,"响山村委会","预计河道护坡加固2.8km排水设施完善",346.08,140,206.08,1,260,820,0,8,29,"完成河道护坡加固2.8km排水设施完善","改善河流水质和生态环境，促进生物多样性保护和水资源可持续利用提升。村民的居住环境和幸福感，促进乡村旅游产业的发展，为村民增加经济收入来源。"]
[135,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","壁山村","2024年詹桥镇壁山村庙坡组至陈家组道路提质改造","扩建","壁山村庙坡组至陈家组",2024.9,2024.9,"壁山村","壁山村庙坡组至陈家组道路提质改造1公里",42,null,42,1,45,198,1,11,36,"为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[136,"乡村建设行动","人居环境整治","村容村貌提升","詹桥镇","壁山村","2024年詹桥镇壁山村青咀桥至钟家组人居环境整治","新建","壁山村",2024.9,2024.11,"壁山村","壁山村青咀桥至钟家组人居环境整治2.5公里",20,null,20,1,45,198,1,11,36,"生产生活条件改善，提升自然条件，增加群众获得感、幸福感。带动沿线人居环境整治提升、助力美丽屋场建设。","基础设施+农户保障相结合"]
[137,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","壁山村","2024年詹桥镇壁山村钟家组至庙坡组路灯整修及陈家组护坡","扩建","壁山村",2024.8,2024.12,"壁山村","壁山村钟家组至庙坡组路灯整修70盏，新增路灯10盏，陈家组护坡368平方米",13,null,13,1,45,198,1,11,36,"为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[138,"乡村建设行动","农村基础设施","农村供水保障设施建设","詹桥镇","长浩村","2024年詹桥镇长浩村光明组片区饮水工程","新建","长浩村",2024.8,2024.12,"长浩村","长浩片区（光明组、光辉组、万明组、万兴组）供水蓄水池维修加固，饮水管加装2500米，修建二级供水坝蓄水量100m³",12,null,12,1,219,726,1,15,53,"为了群众饮水和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[139,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","三界村","2024年詹桥镇三界村老屋组砌坎","新建","三界村",2024.8,2024.9,"三界村","三界村老屋组砌坎长20米，宽2米，高4米",5.6,null,5.6,1,42,368,1,3,8,"为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[140,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","三界村","2024年詹桥镇三界村四房组公路维修","新建","三界村四房组",2024.7,2024.7,"三界村","三界村四房组公路整修硬化185米",5.18,null,5.18,1,956,3368,1,6,12,"为了方便群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[141,"乡村建设行动","农村基础设施","其他","詹桥镇",null,"2024年詹桥镇易地搬迁安置点基础设施更新","新建","詹桥镇易地搬迁安置点",2024.9,2024.12,"詹桥镇易地搬迁安置点","安置点基础设施（屋顶维修350平方米、栽种桂花树40棵）",11.5,null,11.5,12,80,274,4,80,274,"此项目实施，通过安置点基础设施建设，提高住户生活质量，提升脱贫户脱贫质量，进一步巩固脱贫成果","基础设施+农户保障相结合"]
[142,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","分水村","2024年詹桥镇分水村上屋组砌坎","新建","分水村",2024.9,2024.12,"分水村","分水村上屋组洞坑处砌坎长60米，宽1.5米，高2.6米",11.5,null,11.5,1,53,336,1,8,20,"为了群众种植灌溉，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[143,"乡村建设行动","人居环境整治","村容村貌提升","詹桥镇","分水村","2024年詹桥镇分水村人居环境整治","新建","分水村",2024.9,2024.12,"分水村","分水村G353沿线及各组级公路约5.4公里环境整治",10,null,10,1,235,896,1,16,48,"改善老百姓生活条件，提高出行便利，增加群众幸福感，带动本村人居环境整治提升，助力美丽屋场建设。","基础设施+农户保障相结合"]
[144,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","水泉村","2024年詹桥镇水泉村七湾组渠道整修","重建","水泉村七湾组",2024.8,2024.9,"水泉村","水泉村七湾组渠道整修150米",6.5,null,6.5,1,37,165,1,4,16,"解决群众出行和\n农业生产生活条件","基础设施+农户保障相结合"]
[145,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","詹桥镇","贺畈社区","2024年詹桥镇贺畈社区昌前组至贺畈组、鸦下组及晏上组路灯改造","扩建","贺畈社区",2024.8,2024.12,"贺畈社区","贺畈社区昌前组至贺畈组、鸦下组及晏上组路灯改造，新增路灯45盏",12,null,12,1,110,570,1,8,36,"为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[146,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","跳石村","2024年詹桥镇跳石村上郑组公路拓宽","改建","跳石村上郑组","2024.10.1",2024.12,"跳石村","跳石村上郑组公路拓宽长200米，拓宽2米",15,null,15,1,35,109,1,3,7,"为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[147,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","云山村","大云山旅游公路提质改造工程（第一期）","新建","云山村",2024.7,2024.12,"云山村","云山村路提质改造面积3275㎡，大云山路提质改造面积17400㎡，大云山公路路基修补施工面积9250㎡，大云山公路排水沟300m、浆砌石挡土墙1140m³、山咀土方挖运施工1000m³",396,150,246,1,1086,2977,1,8,17,"为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[148,"乡村建设行动","农村基础设施","其他","詹桥镇","壁山村","詹桥镇壁山村新增文旅服务配套工程建设项目","新建","壁山村",2024.7,2024.11,"壁山村","红色旅游产业路1800m、新建120m²红色农特文化园建筑、提质改造1700m²红军会议遗址、新建108m²配套公厕、180立方应急储水池",238.592,140,98.592,1,19873,56827,1,57,172,"通过改善景区基础设施，提升接待能力的同时也提高游客的旅游体验，增加游客满意度和口碑传播；通过景点的提升项目，带动周边旅游产业链的发展，增加创业就业机会，促进群众增收，促进当地经济繁荣。","基础设施+农户保障相结合"]
[149,"乡村建设行动","农村基础设施","其他","詹桥镇","壁山村","詹桥镇壁山村教育基地提质改造及附属设施建设项目","新建","壁山村",2024.7,2024.11,"壁山村","壁山老区爱国主义教育基地提质改造700㎡，壁山老区爱国主义教育基地照明设施，壁山老区爱国主义教育基地给排水，对1250m²军事体验乐园进行扩建（包含新增体验设施等）。",257.7,140,117.7,1,19873,56827,1,57,172,"通过改善景区基础设施，提升接待能力的同时也提高游客的旅游体验，增加游客满意度和口碑传播；通过景点的提升项目，带动周边旅游产业链的发展，增加创业就业机会，促进群众增收，促进当地经济繁荣。","基础设施+农户保障相结合"]
[150,"乡村建设行动","农村基础设施","其他","詹桥镇","壁山村","詹桥镇壁山革命烈士陵园提质改造项目","新建","壁山村",2024.7,2024.11,"壁山村","提质改造136名烈士共眠的烈士陵园（主要包括1800m长的烈士陵园破损路面拓宽、换板、排水沟、白改黑，烈士陵园纪念平台提质改造，纪念碑提质改造与碑体加固，120㎡烈士英名事迹石碑及衣冠冢提质改造，陵园入口处烈士英名录建设）。教育基地及烈士陵园周边交通基础设施配套建设项目主要包括20m长、6m宽红军溪桥梁建设及防护，烈士陵园道路港边砌磡，原砼路面加铺沥青1.8公里，破损砼路面进行换板800㎡及沿线附属零星工程。",632.96,407,225.96,1,19873,56827,1,57,172,"通过改善景区基础设施，提升接待能力的同时也提高游客的旅游体验，增加游客满意度和口碑传播；通过景点的提升项目，带动周边旅游产业链的发展，增加创业就业机会，促进群众增收，促进当地经济繁荣。","基础设施+农户保障相结合"]
[151,"产业发展项目","加工流通项目","加工业","詹桥镇","壁山村","壁山洗水茶加工生产线建设","新建","壁山村",2024.7,2024.11,"壁山村","新建 216m²生产线厂房一间；新建厂区晾晒坪、挡土墙；购置洗水茶筛选设备一套、炒茶烘干设\n备一套及其他配套设备。",115.2,50,65.2,1,19873,56827,1,57,172,"预计项目的实施四村人均可支配收入年均增长10%以上，预计四村集体经济每年可增收入10余万元，产业发展受益达10年以上。本项目以镇为框架实施一村一品，为做大做强“壁山红”等地域品牌进行有益的探索。","基础设施+农户保障相结合"]
[152,"产业发展项目","生产项目","种植业基地","詹桥镇","壁山村","壁山洗水茶种植基地扩建","新建","壁山村",2024.7,2024.11,"壁山村","壁山洗水茶种植基地扩建项目包括120 亩土地平整、360000 株苗木购置、肥料购置及植保维护。",48.6,15,33.6,1,19873,56827,1,57,172,"预计项目的实施四村人均可支配收入年均增长10%以上，预计四村集体经济每年可增收入10余万元，产业发展受益达10年以上。本项目以镇为框架实施一村一品，为做大做强“壁山红”等地域品牌进行有益的探索。","种植基地+农\n户就业相结合"]
[153,"产业发展项目","加工流通项目","加工业","詹桥镇","水泉村","绿豆粉皮生产线产能提升","新建","水泉村",2024.7,2024.11,"水泉村","包含\n600m²切丝车间提质改造、100m²生产厂房改造、960m²冷藏储存\n设施建设、购置搅拌机、蒸煮设备、烘干机及其他配套设备。",334.4,160,174.4,1,19873,56827,1,57,172,"预计项目的实施四村人均可支配收入年均增长10%以上，预计四村集体经济每年可增收入10余万元，产业发展受益达10年以上。本项目以镇为框架实施一村一品，为做大做强“壁山红”等地域品牌进行有益的探索。","基础设施+农户保障相结合"]
[154,"产业发展项目","生产项目","休闲农业与乡村旅游","詹桥镇","水泉村","水泉村特色民宿项目","新建","水泉村",2024.7,2024.11,"水泉村","包含民宿主体建筑改造 800m²、民宿产业路提质改造，产业路长 1500m 宽 6m，共计 9000m²沥青路面。",286,100,186,1,19873,56827,1,57,172,"预计项目的实施四村人均可支配收入年均增长10%以上，预计四村集体经济每年可增收入10余万元，产业发展受益达10年以上。本项目以镇为框架实施一村一品，为做大做强“壁山红”等地域品牌进行有益的探索。","基础设施+农户保障相结合"]
[155,"产业发展项目","生产项目","种植业基地","詹桥镇","余湾村","杨梅种植采摘基地","新建","余湾村",2024.7,2024.11,"余湾村","包含土地整理（含杂草）80 亩、灌溉沟渠建设、果树种植 80 亩、植保维护、道路硬化与砂石路铺设 300m。",41.2,null,41.2,1,19873,56827,1,57,172,"预计项目的实施四村人均可支配收入年均增长10%以上，预计四村集体经济每年可增收入10余万元，产业发展受益达10年以上。本项目以镇为框架实施一村一品，为做大做强“壁山红”等地域品牌进行有益的探索。","种植基地+农\n户就业相结合"]
[156,"产业发展项目","生产项目","种植业基地","詹桥镇","长浩村","大豆玉米套种基地建设","新建","长浩村",2024.7,2024.11,"长浩村","包含土地整理 500m²、土壤改良\n500m²、排灌系统建设、病虫害防治。",44,4,40,1,19873,56827,1,57,172,"预计项目的实施四村人均可支配收入年均增长10%以上，预计四村集体经济每年可增收入10余万元，产业发展受益达10年以上。本项目以镇为框架实施一村一品，为做大做强“壁山红”等地域品牌进行有益的探索。","种植基地+农\n户就业相结合"]
[157,"产业发展项目","加工流通项目","品牌打造和展销平台","詹桥镇","壁山村","壁山红区域品牌打造","新建","壁山村",2024.7,2024.11,"壁山村","壁山红区域品牌打造项目包含线上短视频制作、品牌线上推\n广，线下制作品牌手册、组织品牌推广、组织产销专业人才培训。",50,10,40,1,19873,56827,1,57,172,"预计项目的实施四村人均可支配收入年均增长10%以上，预计四村集体经济每年可增收入10余万元，产业发展受益达10年以上。本项目以镇为框架实施一村一品，为做大做强“壁山红”等地域品牌进行有益的探索。","基础设施+农户保障相结合"]
[158,"乡村建设行动","农村基础设施","其他","詹桥镇","长浩村","林下经济产业配套防护设施建设工程（长浩村防火林带、隔离带）","新建","长浩村",2024.7,2024.11,"长浩村","项目主要建设内容为林下经济产业配套防护设施建设项目，\n包含新建防火林带、隔离带 4440m 长 30m，共计 133200m²",79,null,79,1,19873,56827,1,57,172,"预计项目的实施四村人均可支配收入年均增长10%以上，预计四村集体经济每年可增收入10余万元，产业发展受益达10年以上。本项目以镇为框架实施一村一品，为做大做强“壁山红”等地域品牌进行有益的探索。","基础设施+农户保障相结合"]
[159,"乡村建设行动","农村基础设施","其他","詹桥镇",null,"林下经济产业配套防护设施建设工程","新建","詹桥镇",2024.7,2024.11,"詹桥镇","购置林产业发展监测与防控专用装备一套；新建林下经济产业服务及展示中心 65m²、专用设备与装置保管室 15m²。",42.34,null,42.34,1,19873,56827,1,57,172,"预计项目的实施四村人均可支配收入年均增长10%以上，预计四村集体经济每年可增收入10余万元，产业发展受益达10年以上。本项目以镇为框架实施一村一品，为做大做强“壁山红”等地域品牌进行有益的探索。","基础设施+农户保障相结合"]
[160,"产业发展项目","配套设施项目","产业园(区)","詹桥镇","印石村","印石村生态有机农业产业配套建设项目","新建","印石村",2024.7,2024.12,"印石村","八味豆豉产能提升：对印石村八味豆豉厂厂房提质改造 500 平方米，扩建 360m²地面晾晒基地、440m²高空晾晒基地，新建 100 亩黑豆种植基地。\n有机蔬菜基地建设：通过“小田改大田”等新增印石村杨家组蔬菜种植基地 240 亩，新增种植基地水利灌溉设施，购置病虫防治及植保设备等。",251.4,130,121.4,1,19873,56827,1,57,172,"通过项目的实施，村人均可支配收入年均增长10%以上，村集体经济年收入增长6万元以上。","公司+基地+农户"]
[161,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","詹桥社区","詹桥河詹桥片区段护砌（东岸组至塘畈段两岸）","新建","詹桥社区",2024.7,2024.11,"詹桥社区","詹桥河詹桥片区段护砌（东岸组至塘畈段两岸）\n3082m",123.2616,50,73.2616,1,19873,56827,1,57,172,"为了群众饮水和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[162,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","印石村","詹桥河印石村段护砌（排柳段右岸）","新建","印石村",2024.7,2024.11,"印石村","詹桥河印石村段护砌（排柳段右岸）260m",10.3845,null,10.3845,1,19873,56827,1,57,172,"为了群众饮水和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[163,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","水泉村","詹桥河水泉村段护砌（寺畈段左岸）","新建","水泉村",2024.7,2024.11,"水泉村","詹桥河水泉村段护砌（寺畈段左岸）1459m",58.3625,20,38.3625,1,19873,56827,1,57,172,"为了群众饮水和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[164,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","詹桥社区","詹桥社区芦冲港全河段护砌（灌溉）","新建","詹桥社区",2024.7,2024.11,"詹桥社区","詹桥社区芦冲港全河段护砌（灌\n溉）2163m",86.5375,30,56.5375,1,19873,56827,1,57,172,"为了群众饮水和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[165,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","壁山村","壁山村钟家组至庙坡组河岸护砌","新建","壁山村",2024.7,2024.11,"壁山村","壁山村钟家组至庙坡组河岸护砌 2941m",117.6588,80,37.6588,1,19873,56827,1,57,172,"为了群众饮水和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[166,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","印石村","詹桥河（印石高速公路出口处）护砌","新建","印石村",2024.7,2024.11,"印石村","詹桥河（印石高速公路出口处）护砌 700m",27.995968,10,17.995968,1,19873,56827,1,57,172,"为了群众饮水和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[167,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","雁南村","雁南村片区河港治理河岸护砌","新建","雁南村",2024.7,2024.11,"雁南村","雁南村片区河港治理河岸护砌\n（刘一段两岸）3296m",131.859,60,71.859,1,19873,56827,1,57,172,"为了群众饮水和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[168,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","印石村","印石村大塘灌区西干渠建设","新建","印石村",2024.7,2024.11,"印石村","干渠建设土方开挖回填 300m³、浆砌石、DN300pe 管道2860m",129.9012,100,29.9012,1,19873,56827,1,57,172,"为了群众饮水和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[169,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","长浩村","村组公路水毁修复工程（长浩村）","新建","长浩村",2024.7,2024.11,"长浩村","村组公路水毁修复工程 609 ㎡",12.18512,10,2.18512,1,19873,56827,1,57,172,"解决群众出行和\n农业生产生活条件","基础设施+农户保障相结合"]
[170,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","詹桥社区","村组公路水毁修复工程（詹桥社区）","新建","詹桥社区",2024.7,2024.11,"詹桥社区","詹桥社区芦冲组\n村组公路水毁修复工程 17 ㎡",0.34944,null,0.34944,1,19873,56827,1,57,172,"解决群众出行和\n农业生产生活条件","基础设施+农户保障相结合"]
[171,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","余湾村","村组公路水毁修复工程（余湾村）","新建","余湾村",2024.7,2024.11,"余湾村","村组公路水毁修复工程 177 ㎡",3.52792,null,3.52792,1,19873,56827,1,57,172,"解决群众出行和\n农业生产生活条件","基础设施+农户保障相结合"]
[172,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","印石村","村组公路水毁修复工程（印石村）","新建","印石村",2024.7,2024.11,"印石村","村组公路水毁修复工程 258 ㎡",5.16356,null,5.16356,1,19873,56827,1,57,172,"解决群众出行和\n农业生产生活条件","基础设施+农户保障相结合"]
[173,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","雁南村","村组公路水毁修复工程（雁南村）","新建","雁南村",2024.7,2024.11,"雁南村","雁南村龙门子水库\n村组公路水毁修复工程 14 ㎡",0.28224,null,0.28224,1,19873,56827,1,57,172,"解决群众出行和\n农业生产生活条件","基础设施+农户保障相结合"]
[174,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","水泉村","村组公路水毁修复工程（水泉村）","新建","水泉村",2024.7,2024.11,"水泉村","水泉村老屋二组\n村组公路水毁修复工程 69 ㎡",1.37936,null,1.37936,1,19873,56827,1,57,172,"解决群众出行和\n农业生产生活条件","基础设施+农户保障相结合"]
[175,"产业发展项目","配套设施项目","小型农田水利建设","詹桥镇","壁山村","村组公路水毁修复工程（壁山村）","新建","壁山村",2024.7,2024.11,"壁山村","壁山村至长浩村主干道\n村组公路水毁修复工程 234 ㎡",4.6776,null,4.6776,1,19873,56827,1,57,172,"解决群众出行和\n农业生产生活条件","基础设施+农户保障相结合"]
[176,"产业发展项目","配套设施项目","产业园(区)","詹桥镇","雁南村","詹桥育秧工厂建设项目","新建","雁南村",2024.7,2024.11,"雁南村","包括新建育秧工厂（包\n括 1000m²轻钢结构大棚车间，一套运输皮带，3 万个水稻育秧硬盘、托盘，10 亩塑料大棚，1 个浸种池，1 套大棚秧盘喷水设备，打造 1 条育秧流水线，购置叠盘机、送盘机、打浆机、自动送土机、筛土机），新建育秧工厂仓库（建设轻钢结构仓库，购置装载机、叉车，并打造叠盘加温密室），配套产业路建设。",296.8,180,116.8,1,19873,56827,1,57,172,"育秧工厂可以为全镇14个村社供应秧苗","采用村级合作社+基地+农户的方式；项目由村集体经济组织实施。联农带农方式包括土地流转、务工就业，收益分红等。"]
[177,"产业发展项目","生产项目","种植业基地","詹桥镇","印石村","优质水稻种植示范片建设（印石村）","新建","印石村",2024.7,2024.11,"印石村","包括覆盖 600 亩滴灌喷灌\n设施完善、灌溉渠道衬砌240米、环农田道路及田间砂石路硬化（机耕道）500㎡、泵站及变电设施建设与管道铺设1800米",142.8,90,52.8,1,19873,56827,1,57,172,"育秧工厂可以为全镇14个村社供应秧苗","采用村级合作社+基地+农户的方式；项目由村集体经济组织实施。联农带农方式包括土地流转、务工就业，收益分红等。"]
[178,"产业发展项目","配套设施项目","其他","詹桥镇","雁南村","农业小水源提升工程（雁南村）","新建","雁南村",2024.7,2024.11,"雁南村","雁南村9座：老官坡门前塘，陆家新塘，铁垅坑山塘，罗鼓山塘，黄泥塘，西家坡塘，八号垅山塘，屋自坡，出水坳",103,30,73,1,19873,56827,1,57,172,"山塘整治后预计新增山塘蓄水能力近6万立方米。","采用村级合作社+基地+农户的方式；项目由村集体经济组织实施。联农带农方式包括土地流转、务工就业，收益分红等。"]
[179,"产业发展项目","配套设施项目","其他","詹桥镇","水泉村","农业小水源提升工程（水泉村）","新建","水泉村",2024.7,2024.11,"水泉村","水泉村4座：狮形塘，陆家垅塘，雪埂塘，南山山塘",22,null,22,1,19873,56827,1,57,172,"山塘整治后预计新增山塘蓄水能力近6万立方米。","采用村级合作社+基地+农户的方式；项目由村集体经济组织实施。联农带农方式包括土地流转、务工就业，收益分红等。"]
[180,"产业发展项目","配套设施项目","其他","詹桥镇","印石村","农业小水源提升工程（印石村）","新建","印石村",2024.7,2024.11,"印石村","印石村6座：凤形塘，锅底塘，老屋塘，陆家烟火塘，松坳塘，店山岭",31,null,31,1,19873,56827,1,57,172,"山塘整治后预计新增山塘蓄水能力近6万立方米。","采用村级合作社+基地+农户的方式；项目由村集体经济组织实施。联农带农方式包括土地流转、务工就业，收益分红等。"]
[181,"产业发展项目","配套设施项目","其他","詹桥镇","詹桥社区","农业小水源提升工程（詹桥社区）","新建","詹桥社区",2024.7,2024.11,"詹桥社区","詹桥社区6座：烟火塘，沙石塘，彭垅组水塘，大屋组水塘，冷家塘，芦冲烟火塘",33,null,33,1,19873,56827,1,57,172,"山塘整治后预计新增山塘蓄水能力近6万立方米。","采用村级合作社+基地+农户的方式；项目由村集体经济组织实施。联农带农方式包括土地流转、务工就业，收益分红等。"]
[182,"乡村建设行动","农村基础设施","农村供水保障设施建设","詹桥镇",null,"詹桥镇水厂提质改造建设","新建","詹桥镇",2024.7,2024.11,"水厂","新建 200m³詹桥片区絮凝沉淀清水池、30m²詹桥片区加矾加\n氯间，完善詹桥片区污泥处理系统",175,null,175,1,19873,56827,1,57,172,"提升詹桥镇饮用水供水质量，确保居民饮用水安全与健康，还能够增强供水系统的稳定性和可靠性，减少因水质问题引发的公共卫生事件，进一步促进社会经济的可持续发展和居民生活质量的全面提升。","基础设施+农户保障相结合"]
[183,"乡村建设行动","农村基础设施","农村供水保障设施建设","詹桥镇",null,"詹桥社区及水泉等四个村社区供水管网建设","新建","詹桥镇",2024.7,2024.11,"水厂","詹桥社区及水泉等四个村社供水管网建设，自团湾水库出水管，经雁南村、印石村、水泉村，沿詹桥河流向至定康桥、詹桥中学，加压至水厂。包括开高压口、平表、挖沟、铺管、回填，沿途有悬空固定，架设天桥增设三厢四线加压设施二处，全长2320m 铺用全钢丝骨架管 pe200/160/110，詹桥社区及水泉等四个村社 9282m110#供水管网改造、安装分户智能水表 1054 个",391.292,147,244.292,1,19873,56827,1,57,172,"提升詹桥镇饮用水供水质量，确保居民饮用水安全与健康，还能够增强供水系统的稳定性和可靠性，减少因水质问题引发的公共卫生事件，进一步促进社会经济的可持续发展和居民生活质量的全面提升。","基础设施+农户保障相结合"]
[184,"乡村建设行动","农村基础设施","农村供水保障设施建设","詹桥镇","壁山村","壁山村安全饮水工程","新建","壁山村",2024.7,2024.11,"壁山村","建设壁山村高岭组 200 ㎡蓄水池、蓄水坝，更换壁山村高岭组 1200m 的 110#饮水管道。",53,53,null,1,19873,56827,1,57,172,"提升詹桥镇饮用水供水质量，确保居民饮用水安全与健康，还能够增强供水系统的稳定性和可靠性，减少因水质问题引发的公共卫生事件，进一步促进社会经济的可持续发展和居民生活质量的全面提升。","基础设施+农户保障相结合"]
[185,"乡村建设行动","农村基础设施","农村供水保障设施建设","詹桥镇","雁南村","团湾水库除险加固提质改造项目","新建","团湾水库",2024.6,2024.11,"团湾水库管理所","1、团湾水库除险加固。团湾水库大坝坝体、两岸坝肩及溢洪道控制段基础防渗，上游坝坡现有干砌块石护坡整修，踏步及马道拆除重建，坝顶防浪墙和路面拆除重建，下游侧增设防护栏，溢洪道一级泄槽末端及消力池拆除重建，下游坝坡现有护坡整修排水沟、踏步及马道整修，转弯连接段底板拆除重建左岸护坡拆除重建，二级泄槽底板拆除重建，泄槽两岸边坡加固，泄槽末端新建挑流鼻坎，大坝上、下游近坝岸坡加固，完善大坝安全监测及雨水情测报设施；防汛公路加固改造（800米）；大坝白蚁防治；重建防汛仓库（300平方米）；\n2、团湾水库提质。封堵原导流隧洞，输水隧洞进口取水塔和工作桥通过丙乳砂浆抹面及C30砼加固；更换闸门吊杆，金属结构除锈防腐，增设启闭设备备用电源，完善电气配套设施；输水隧洞洞身砼衬砌外壁全线采用回填灌浆加固修复；更换输水隧洞出口放空岔管的控制闸阀。",3918,null,3918,1,19873,56827,1,57,172,"一是提升水库安全性：通过除险加固工程，可以显著提高水库的安全性，防止发生溃坝等严重事故，保障周边居民的生命财产安全。二是改善生态环境：水库除险加固工程有助于减少水土流失，改善周边区域的生态环境。同时，稳定的水库水位和流量有助于维护生态平衡，促进生物多样性。三是增强防灾减灾能力，加固后的水库将更好地发挥其防洪、抗旱等功能，有效减轻自然灾害对周边区域的影响，提高防灾减灾能力。四是提升居民生活质量，通过提供稳定、清洁的水源和优美的生态环境，水库除险加固工程将直接提升周边居民的生活质量，增强居民的幸福感和满意度。","基础设施+农户保障相结合"]
[186,"就业项目","就业培训","技能培训","詹桥镇",null,"现代中药材产业技术培训","新建","詹桥社区",2024.7,2024.11,"詹桥镇","种植培训。（包括黄精、石菖蒲、白芪等特色中药材的种植、加工技术培训，对接湖南中医药大学专业教授针对中药材种植开展种植技术教学）；\n销售培训。（包括抖音等平台产品销售技能培训、乡村振兴技能培训）。",50,20,30,1,19873,56827,1,57,172,"提升中药材产业的整体水平、促进产业可持续发展、加强人才培养与技术创新以及满足市场需求。最终推动当地中药材产业的健康、快速发展。通过项目的实施，每年按计划开展现代中药材产业技术培训。","就业培训+农户就业相结合"]
[187,"产业发展项目","生产项目","种植业基地","詹桥镇","詹桥社区","中药材产业示范基地建设","新建","詹桥社区",2024.7,2024.11,"詹桥镇","包括建设黄精种苗繁育基地 6 亩，油茶黄精项种示范基地 80 亩及土地平整、种子及块茎或幼苗购置、水利灌溉设施等，基地临河港边坡产业路拓宽提质150米。",134,30,104,1,19873,56827,1,57,172,"通过项目的实施，人均可支配收入年均增长10%以上，带动全镇种植户20余户，培育种植大户2户；培育发展特色产业1个。","土地流转、技术培训、村集体入股分红、务工就业等，为零散种植户提供技术培训，提供种苗以及产品加工等配套服务等"]
[188,"产业发展项目","生产项目","种植业基地","詹桥镇","三界村","中药材生产基地建设（三界村）","新建","三界村",2024.7,2024.11,"三界村","石菖蒲种植基地100亩",160,20,140,1,19873,56827,1,57,172,"通过项目的实施，人均可支配收入年均增长10%以上，带动全镇种植户20余户，培育种植大户2户；培育发展特色产业1个。","土地流转、技术培训、村集体入股分红、务工就业等，为零散种植户提供技术培训，提供种苗以及产品加工等配套服务等"]
[189,"产业发展项目","生产项目","种植业基地","詹桥镇","水泉村","中药材生产基地建设（水泉村）","新建","水泉村",2024.7,2024.11,"水泉村","金银花种植基地30亩",6,6,null,1,19873,56827,1,57,172,"通过项目的实施，人均可支配收入年均增长10%以上，带动全镇种植户20余户，培育种植大户2户；培育发展特色产业1个。","土地流转、技术培训、村集体入股分红、务工就业等，为零散种植户提供技术培训，提供种苗以及产品加工等配套服务等"]
[190,"产业发展项目","配套设施项目","其他","詹桥镇","詹桥社区","中药材加工能力建设","新建","原詹桥\n小学",2024.7,2024.11,"詹桥镇","包括新建 1 条黄精加工生产线，240㎡生产车间厂房建设，100㎡黄精清洗车间建设，大型烘干设备及自动化包装机购置，158㎡蒸煮车间等提质，冷库建设240㎡。",259.6,74,185.6,1,19873,56827,1,57,172,"通过项目的实施，人均可支配收入年均增长10%以上，带动全镇种植户20余户，培育种植大户2户；培育发展特色产业1个。","土地流转、技术培训、村集体入股分红、务工就业等，为零散种植户提供技术培训，提供种苗以及产品加工等配套服务等"]
[191,"产业发展项目","生产项目","种植业基地","羊楼司镇","友爱村","友爱村楠竹产业示范基地建设项目","改建","友爱村",2024.6,2024.12,"友爱村","建设300亩示范竹林，其中笋用林150亩、笋材两用150亩；低产林改300亩，使低产林立竹量达到180株/亩；建设林道3公里",160,100,60,1,124,647,0,3,10,"建设示范竹林，提高群众收入","土地流转"]
[192,"产业发展项目","生产项目","休闲农业与乡村旅游","羊楼司镇","龙窖山村","龙窖山旅游设施建设项目一期","新建","龙窖山村",2024.6,2024.12,"龙窖山村","景区公路改扩建2.6公里，宽4米",228.8,80,148.8,1,541,2450,0,3,12,"完善乡村旅游基础设施建设，促进产业发展，解决剩余劳力就业、增加脱贫（监测）户经济收入","带动产业发展和农民增收"]
[193,"产业发展项目","生产项目","休闲农业与乡村旅游","羊楼司镇","龙窖山村","龙窖山旅游设施建设项目二期","新建","龙窖山村",2024.6,2024.12,"龙窖山村","建设景区观景台1个，200平方米；建设景区旅游公厕2个",140.6,0,140.6,1,541,2450,0,3,12,"完善乡村旅游基础设施建设，促进产业发展，解决剩余劳力就业、增加脱贫（监测）户经济收入","带动产业发展和农民增收"]
[194,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","羊楼司镇","友爱村","友爱村柳坪路段公路塌方护砌","新建","友爱村","2024.10.14","2024.11.20","友爱村","柳坪路段公路塌方护砌长120米，宽1米，高2米",10,10,0,1,24,56,0,1,3,"确保辖区群众方便出行，改善人居环境","带动生产、提高收入"]
[195,"产业发展项目","配套设施项目","小型农田\n水利设施\n建设","羊楼司镇","雅团村","水利堰坝整修","新建","下屋组",2024.1,2024.11,"雅团村","雅团村下屋组处堰坝整修全长48米，高3米",19,8,11,1,75,236,0,7,23,"堰坝整修，解决农田灌溉问题，使村民的生活得到保障","解决农田灌溉问题，使农业生产条件得到改善，村民的生产生活得到保障"]
[196,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","羊楼司镇","黄沙村","入户断头路硬化花屋组","新建","花屋组","2024年8月25","2024年12月30","黄沙村","入户断头路共长410米",12.5,10.5,2,1,15,50,0,3,11,"改善人居环境，方便群众出行","改善人居环境，方便群众出行"]
[197,"产业发展项目","配套设施项目","小型农田\n水利设施\n建设","羊楼司镇","文白社区","文白社区港渠护砌2024","新建","赵家组","2024.10.12","2024.10.30","文白社区","200米",15,9,6,1,134,405,0,4,13,"护砌港渠200米，减少洪涝灾害，确保辖区居民生命财产安全","护砌港渠200米，减少洪涝灾害，确保辖区居民生命财产安全"]
[198,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","羊楼司镇","新屋村","栗楠至梁家组公路整修","改建","新屋村栗楠至梁家组","2024.9.10","2024.10.10","新屋村","公路整修1.5公里，路基加宽2.5米",6.5,5,1.5,1,138,1260,1,12,34,"改善脱贫户的生产生活条件，方便村民出行","为脱贫户提供就业岗位，增加脱贫人口收入"]
[199,"产业发展项目","生产项目","休闲农业与乡村旅游","羊楼司镇","三港村","三港村和美湘村建设","新建","三港村","8月","12月","三港村","建设和美湘村，基础设施建设及旅游附属设施",500,100,400,1,245,1250,1,6,24,"带动脱贫、监测户劳动就业增加收入","带动脱贫、监测户劳动就业增加收入，发展村集体经济"]
[200,"产业发展项目","生产项目","种植业基地","羊楼司镇","三港村","种植中药材后续管理","新建","三港村付家组",2024.7,2024.11,"三港村","三港村付家组种植中药材26亩后续管理：  （施肥、施药、除草）",5,3,2,1,245,1250,1,6,24,"种植中药材后续管理带动脱贫、监测户劳动就业增加收入","种植中药材后续管理带动脱贫、监测户劳动就业增加收入，发展村集体经济"]
[201,"产业发展项目","配套设施项目","小型农田水利建设","羊楼司镇","明星村","河道清淤","改造","宋家组",2024.9,2024.9,"明星村","河道清淤160米长5米宽",3.6,3.6,0,1,44,198,1,5,22,"河道清淤，为脱贫户及监测户提供出行安全","河道清淤，带动产业发展和农民收入"]
[202,"产业发展项目","生产项目","种植业基地","羊楼司镇","金鸡社区","八月蛋种植基地","新建","三屋组",2024.7,2024.11,"金鸡社区","种植八月蛋20亩",15,10,5,1,28,0,2,7,null,"八月蛋种植基地为脱贫户提高劳动就业便利，带动脱贫增收","八月蛋种植基地为脱贫户提高就业便利，增加\n百姓收入\n\n"]
[203,"产业发展项目","配套设施项目","小型农田水利建设","羊楼司镇","龙窖山村","龙窖山村山洪地质灾害水毁工程","恢复建设","龙窖山村",2024.9,2024.11,"龙窖山村","1.龙溪组龙溪寨门口河堤护砌168立方米；2.路面硬化78平方米；3.龙溪组桥头河堤护砌81立方米；4.钟家铺组河堤护砌94.5立方米",10.4,10,0.4,1,421,1860,0,3,12,"完善乡村基础设施建设，促进产业发展，解决剩余劳力就业、增加脱贫（监测）户经济收入","确保辖区部分居民方便出行，改善人居环境"]
[204,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","羊楼司镇","双山村","双山村铁家组道路850米硬化","新建","双山村","2024.9.14","2024.10.20","双山村","铁家组道路850米硬化",36,15,21,1,23,70,0,2,5,"确保辖区群众方便出行，改善人居环境","带动生产、提高收入"]
[205,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","羊楼司镇","石壁村","石壁村东头至水桶产业路路基拓宽","改建","石壁村","2024.9.14","2024.10.20","石壁村","长1500米，宽1.5米至2米",4.2,3,1.2,1,14,35,0,3,12,"确保辖区群众方便出行，改善人居环境","带动生产、提高收入"]
[206,"产业发展项目","配套设施项目","小型农田\n水利设施\n建设","羊楼司镇","文白社区","文白社区挖沟清\n淤2024","新建","文白社区","2024.11.14","2024.12.20","文白社区","上街挖沟清淤174米",5.5,3,2.5,1,23,76,0,2,5,"挖沟清淤174米确保辖区部分居民方便出行，改善人居环境","挖沟清淤174米确保辖区部分居民方便出行，改善人居环境"]
["合    计",{"$nulls":12},{"$f":"SUM(N6:N211)","v":21383.770508},{"$f":"SUM(O6:O211)","v":10741.57},{"$f":"SUM(P6:P211)","v":10642.200508},149,null,null,26,{"$f":"SUM(U6:U211)","v":5823},{"$f":"SUM(V6:V211)","v":18003}]