{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["2023年"],"not_rendered":{"defined_names":2,"comments":1},"read":"whole","date_system":"1900"}

{"sheet":"2023年","index":0,"n_rows":262,"n_cols":25,"rows_kept":262,"merged":[[0,0,0,24],[1,0,1,6],[1,16,1,24],[2,0,4,0],[2,1,2,3],[2,4,4,4],[2,5,4,5],[2,6,4,6],[2,7,4,7],[2,8,4,8],[2,9,2,10],[2,11,4,11],[2,12,4,12],[2,13,2,15],[2,16,2,21],[2,22,4,22],[2,23,4,23],[2,24,4,24],[3,1,4,1],[3,2,4,2],[3,3,4,3],[3,9,4,9],[3,10,4,10],[3,13,4,13],[3,14,3,15],[3,16,4,16],[3,17,4,17],[3,18,4,18],[3,19,3,21],[261,0,261,7]]}
["临湘市2023年度巩固拓展脱贫攻坚成果和乡村振兴项目库入库项目申报表"]
[{"$nulls":16},"时间：2022年11月15日"]
["序号","项目类别",null,null,"乡","村","项目名称","建设性质","实施地点","时间进度",null,"责任单位","建设内容及规模","资金规模\n和筹资方式",null,null,"受益对象",{"$nulls":5},"绩效目标","联农带农机制","备注"]
[null,"项目类型","二级项目类型","项目子类型",{"$nulls":5},"计划开工时间","计划完工时间",null,null,"项目预算总投资（万元）","其中",null,"受益村（个数）","受益户数（户）","受益人口数（人）","其中"]
[{"$nulls":14},"财政资金（万元）","其他资金（万元）",{"$nulls":3},"受益脱贫村数（个）","受益脱\n贫户数\n及防止\n返贫监\n测对象\n人口数\n（人）","受益脱\n贫人口\n数\n及防止\n返贫监\n测对象\n人口数\n（人）"]
[1,"乡村建设行动","农村基础设施","农村道路建设","江南镇","谷花社区","谷花社区\n14组公路\n至江盛路\n维修项目","维\n修","谷花社区","2023/\n3/1","2023/\n4/1","谷花社区","道路维修硬化1.3公里",42,10,32,1,550,2000,null,18,50,"目标1：改善道路设施。目标2：方便村民生产，出行；3：为经济社会发展提供保障","为解决居民生产出行等问题，加强社区居民基础设施和生态环境建设，改善居民生产生活条件，促进经济发展，增加居民收入，使居民生活水平不断提高，逐步达到小康生活"]
[2,"产业发展","加工物流项目","市场建设","江南镇","谷花社区","谷花社区\n集贸市场\n维修项目","维\n修","谷花社区","2023/\n3/1","2023/\n4/1","谷花社区","集贸市场\n维修改造3000㎡",28,5,23,1,1120,4550,null,26,74,"目标1：发展集体经济；目标2：增加贫困户及居民生活幸福指数。","为解决居民生产出行等问题，加强社区居民基础设施和生态环境建设，改善居民生产生活条件促      进经济发展，增加居民收入，居民生活水平不断提高，逐步达到小康生活"]
[3,"产业发展","配套基础设施项目","小型农田水利设施建设","江南镇","东冶村","东冶村大坳组沟渠修缮","维修","东冶村","2023/\n3/1","2023/\n5/1","东冶村","沟渠修缮4.5公里",10,5,5,1,50,300,null,3,10,"目标1：方便村民农田耕种；目标2：使脱贫户增产；目标3：促进乡村振兴发展。","通过沟渠修缮方便农田灌溉，增加农户种养积极性，使其增产增收；方便防汛期间排渍。"]
[4,"乡村建设行动","农村基础设施","外江抗旱机埠维修","江南镇","灯塔村","灯塔村外江抗旱机埠维修","维修","灯塔村","2023/\n3/1","2023/\n5/1","灯塔村","外江抗旱机埠维修",13.5,10,3.5,1,355,1420,null,17,49,"目标1：方便村民农田耕种；目标二：使脱贫户增产；目标3：促进乡村振兴发展。","通过外江抗旱机埠维修方便农田灌溉，增加农户种养积极性，使其增产增收；方便防旱期间抽水。"]
[5,"产业发展","配套基础设施项目","小型农田水利设施建设","江南镇","灯塔村","灯塔村孙洲12组至清江口沟渠清淤","维修","灯塔村","2023/\n3/1","2023/\n4/1","灯塔村","灯塔村孙洲12组至清江口沟渠清淤",9.45,5,4.45,1,130,528,null,6,18,"目标1：方便村民农田耕种；目标2：使脱贫户增产；目标3：促进乡村振兴发展。","通过沟渠清淤方便农田灌溉，增加农户种养积极性，使其增产增收；方便防汛抗旱期间排渍抽水。"]
[6,"产业发展","配套基础设施项目","小型农田水利设施建设","江南镇","儒溪社区","儒溪社区山塘清淤、修缮","维修","儒溪社区","2023/\n3/1","2023/\n4/1","儒溪社区","山塘清淤、修缮41口17.57万立方",13.33,5,8.33,1,702,2289,null,11,27,"目标1：方便村民农田耕种；目标2：使脱贫户增产；目标3：促进乡村振兴发展。","通过山塘清淤、修缮方便水源蓄积，增强农田灌溉，增加农户种养积极性，使其增产增收。"]
[7,"产业发展","配套基础设施项目","小型农田水利设施建设","江南镇","江南村","江南村6、13.、15组机耕路维修","维修","江南村","2023/\n3/20","2023/\n4/25","江南村","2公里",10,5,5,1,210,843,null,4,12,"目标1：除险加固保民生；目标2：为脱贫户和群众提供水利灌溉保农业创收","改变项目区贫困群众出行难；改善村级交通运输安全状况，增加脱贫户和监测户种植积极性，使其增产增收。"]
[8,"产业发展","配套基础设施项目","小型农田水利设施建设","江南镇","江南村","江南村七组危桥维修","维修","江南村","2023/\n5/1","2023/\n6/1","江南村","宽3.5米，长6米",6,5,1,1,201,697,null,3,9,"目标1：方便村民出行；目标2：促进乡村振兴经济发展","改善村民生产出行运输安全状况；方便村民农田灌溉，使其增产增收；方便防汛期间排渍。"]
[9,"乡村建设行动","农村基础设施","渠道桥头新建","江南镇","长江村","长江村2、3、4、13、5组渠道桥头新建","维修","长江村","2023/\n1/1","2023/\n3/1","长江村","渠道桥头新建7座",20,15,5,1,260,1350,1,8,21,"目标1：除险加固保民生；目标2：为脱贫户和群众提供水利灌溉保农业创收","通过对渠道桥头新建，重新埋入水泥管道，清理渠道垃圾，提高水流速度，加快农田灌溉   ，使其增产增收，方便防汛抗旱期间抽水。"]
[10,"乡村建设行动","农村基础设施","沟渠清淤","江南镇","长江村","长江村3、4、13、5组沟渠清淤","维修","长江村","2023/\n11/2","2023/\n12/2","长江村","2000米",12,10,2,1,245,1250,1,8,21,"目标1：方便村民农田耕种；目标2：使脱贫户增产；目标3：促进乡村振兴发展。","通过沟渠清淤、修缮方便水源蓄积，增强农田灌溉，增加农户种养积极性，使其增产增收。"]
[11,"乡村建设行动","农村基础设施","机耕路铺塘渣","江南镇","长江村","长江村14组机耕路铺塘渣","维修","长江村","2023/\n2/10","2023/\n2/25","长江村","2公里 ",5,4,1,1,15,56,1,8,21,"目标1：改善道路设施。目标2：方便村民生产，出行；3：为经济社会发展提供保障","为解决居民生产出行等问题，加强社区居民基础设施和生态环境建设，改善居民生产生活条件，促进经济发展，增加居民收入，使居民生活水平不断提高，逐步达到小康生活"]
[12,"乡村建设行动","农村基础设施","农村道路建设","江南镇","洋溪","洋溪村斑竹坡西湾路道路硬化","新建","洋溪村","2023/\n4/1","2023/\n5/1","洋溪村","斑竹坡西湾路道路硬化",32,10,22,1,10,35,1,3,13,"目标1：改善道路设施。目标2：方便村民生产，出行；3：为经济社会发展提供保障","通过道路硬化，方便农户出行，有利于农户生产建设"]
[13,"产业发展","配套基础设施项目","小型农田水利设施建设","江南镇","洋溪村","洋溪村2组机埠维修","维修","洋溪村","2023/\n6/1","2023/\n8/1","洋溪村","洋溪村2组机埠维修",18,10,8,1,20,102,1,2,10,"目标1：方便村民农田耕种；目标二：使脱贫户增产；目标3：促进乡村振兴发展。","通过机埠维修，方便农户发展种植业，有利于农户生产建设"]
[14,"乡村建设行动","农村基础设施","农村道路建设","江南镇","牛湖村","牛湖村16组道路硬化","维修","牛湖村","2023/\n3/5","2023/\n4/5","牛湖村","道路建设",45,10,35,1,315,1120,null,12,30,"目标1：方便村民出行及交通运输便利；目标2：促进经济发展","为解决居民农产品运输、销售等问题，加强\n社区居民基础设施和生态环境建设，\n改善居民生产生活条件，促进经济\n发展，增加居民收入，使居民生活\n水平不断提高，逐步达到小康生活"]
[15,"产业发展","配套基础设施项目","沟渠清淤","江南镇","牛湖村","牛湖村老泥沟","维修","牛湖村","2023/\n3/5","2023/\n4/5","牛湖村","牛湖村老泥沟",9.8,5,4.8,1,530,2100,null,16,48,"目标1：方便村民农田耕种；目标二：使脱贫户增产；目标3：促进乡村振兴发展。","通过沟渠清淤方便农田灌溉，增加农户种养积极性，使其增产增收；方便防汛抗旱期间排渍抽水。"]
[16,"产业发展","配套基础设施项目","小型农田水利设施建设","江南镇","丁坊村","丁坊村山塘清淤、修缮","维修","丁坊村","2023/\n3/1","2023/\n4/1","丁坊村","山塘清淤、修缮26口21.6万立方",10,5,5,1,660,2336,null,11,27,"目标1：方便村民农田耕种；目标二：使脱贫户增产；目标3：促进乡村振兴发展。","通过山塘清淤、修缮方便水源蓄积，增强农田灌溉，增加农户种养积极性，使其增产增收。"]
[17,"产业发展","配套基础设施项目","小型农田水利设施建设","江南镇","鸭栏村民委员会","鸭栏村沟渠清淤、疏浚","维修","鸭栏村民委员会","2023/\n3/1","2023/\n4/1","鸭栏村民委员会","沟渠清淤、疏浚7.1万立方",30.5,25,5.5,1,876,3896,1,10,60,"目标1：方便村民农田耕种；目标2：使脱贫户增产；目标3：促进乡村振兴发展。","通过沟渠清淤、蔬峻方便水源蓄积，增强农田灌溉，增加农户种养积极性，使其增产增收。"]
[18,"产业发展","生产项目","产业奖补","江南镇","江南镇","江南镇产业奖补","新建","江南镇13个村（社区）","2023/\n3/1","2023/\n4/1","江南镇","产业奖补225户",20,20,0,13,225,670,1,225,670,"目标1：帮助脱贫户及监测户发展产业；目标2：带动产业发展，帮助脱贫户及监测户创收。","通过产业奖补，增加脱贫户和监测户的种养积极性，使其增产增收"]
[19,"就业项目","公益岗位","公益岗位","江南镇","江南镇","公益岗位","新建","江南镇13个村（社区）","2023/\n3/1","2023/\n4/1","江南镇","公益岗位40个",24,12,12,13,40,40,1,40,40,"目标1：帮助桃林镇辖区脱贫户及监测户解决就业；目标2：巩固脱贫攻坚同乡村振兴有效衔接","公益岗位为脱贫户和监测户提供工作岗位，使其收入增加"]
[20,"产业发展","生产项目                                                                           ","水产养殖业发展","长安街道",null,"长安街道2023年产业发展","新建","长安街道","2023.03.01","2023.07.30","长安街道","103户脱贫户及监测户发展养殖业，并实行一定的奖补",15,10,5,5,103,275,1,103,275,"激发脱贫户及监测户内生动力，鼓励其发展产业，增加收入，巩固脱贫成效","激发脱贫户及监测户内生动力，鼓励其发展产业，增加收入，巩固脱贫成效"]
[21,"就业项目","公益性岗位","公益性岗位","长安街道",null,"长安街道2023年公益性岗位奖补","新建","长安街道","2023.01.01","2023.12.31","长安街道","公益性岗位奖补26人",15.6,7.8,7.8,5,26,26,1,26,26,"鼓励脱贫户及监测户就近就业务工，增加收入","鼓励脱贫户及监测户就近就业务工，增加收入"]
[22,"产业发展","配套基础设施项目","小型农田水利设施建设","长安街道","荆竹山村","李家组农田灌溉渠道硬化","新建","荆竹山村李家组",2023.05,2023.06,"荆竹山村","清理渠道内的淤泥100方，硬化渠道内的底板",8,5,3,1,35,170,0,2,4,"方便农田灌溉，","方便农田灌溉，提高农户及脱贫户的农田种植收入"]
[23,"乡村建设行动","农村基础设施","农村道路建设","长安街道","荆竹山村","主公路海螺矿区公路硬化","新建","荆竹山村张家组",2023.06,2023.07,"荆竹山村","道路硬化500米",37,30,7,1,240,1300,0,16,40,"方便群众出行","改善张家、刘家、坳上等8个组的群众生产生活条件，方便出行"]
[24,"乡村建设行动","农村基础设施","农村道路建设","长安街道","杨田村","杨田村大屋组至长安河路段公路硬化","新建","杨田村大屋组","2023.03.01","2023.06.01","杨田村","道路硬化500米",22,15,7,1,26,152,1,16,31,"方便群众出行","改善大屋组的群众生产生活条件，方便出行"]
[25,"乡村建设行动","农村基础设施","农村道路建设","长安街道","杨田村","杨田村罗家组公路硬化","新建","杨田村罗家组","2023.04.01","2023.07.01","杨田村","道路硬化400米",17,10,7,1,25,100,1,16,31,"方便群众出行","改善罗家组的群众生产生活条件，方便出行"]
[26,"产业发展","生产项目","养殖业","桃林镇","钟杨村","钟杨村菜家塘山羊养殖基地","新建","钟杨村菜家塘",2023.1,"2023.3.","钟杨村委会","建设养殖基地100平方米，购买60只山羊",20,10,10,1,30,126,1,16,49,"目标1：增加集体经济收入。目标2：解决脱贫户就业。目标3：促进乡村振兴产业发展","增加贫困户收入，带动就业，促进经济发展"]
[27,"产业发展","配套基础设施项目","小型农田水利设施建设","桃林镇","治水村","山塘维修","维修","治水村治一组、花申组各一座","2023年2月","2023年4月","治水村委会","维修山塘2座堤坝维修，山塘清淤",15,10,5,1,50,210,1,5,11,"目标1：保障村民的粮食生产，避免耕地抛荒；目标2：使脱贫户增产，巩固脱贫成果","解决村民的耕种问题，促进村民的经济发展"]
[28,"产业发展","生产项目","种植业基地","桃林镇","横铺村","千公塘茶园综合体","新造","横铺村千公塘","2023年2月","2023年3月","横铺村委会","新造60亩",20,10,10,1,146,586,1,20,40,"目标1：可使茶园增加产量，增加村集体收入；目标2：为群众及脱贫户提供就近就业机会，带动经济增收，巩固脱贫成效。","解决周边群众及脱贫户就业率，巩固脱贫成果，促进经济发展。"]
[29,"产业发展","生产项目","种植业基地","桃林镇","旧李村","旧李村朱古冲新造油茶林","新造","旧李村朱古冲","2023年2月","2023年3月","旧李村委会","新造25亩",15,8,7,1,861,3380,1,33,120,"目标1：可使茶园增加产量，从而增加村集体经济收入；目标2：能为群众或脱贫户提供就业机会，带动脱贫户增收，进一步巩固脱贫成效。","解决脱贫户就业率，使他们增收，巩固脱贫成果，促进经济发展。","转2022年入库项目"]
[30,"产业发展","生产项目","种植业基地","桃林镇","坪头村","坪头村大冲茶园低改","改造","大冲","2023年1月","2023年5月","平头村委会","100亩茶园于2023年人工开林，低改茶园和补种新苗",30,20,10,1,849,2857,1,31,102,"目标1;维护稳定脱贫；目标2：增加村集体、脱贫户（监测户）和村民收入。","使村民及脱贫户（监测户）增加经济收入，促进经济发展。"]
[31,"产业发展","生产项目","种植业基地","桃林镇","白石村","白石村天车茶园基地","改造","白石村天车岭","2023年3月","2023年4月","白石村委会","改造50亩",10,7,3,1,20,76,1,5,16,"目标1：增加村集体经济收入；目标2：解决脱贫户就近就业；目标3：促进乡村振兴发展。","增加脱贫户收入，带动就业，促进经济发展。"]
[32,"产业发展","生产项目","养殖类","桃林镇","白石村","白石村肉牛养殖","新建","白石村赵泥组","2023年4月","2023年4月","白石村委会","新建牛棚100平方米，肉牛10头",10,8,2,1,30,123,1,4,18,"目标1：增加村集体经济收入；目标2：解决脱贫户就近就业；目标3：促进乡村振兴发展。","增加脱贫户收入，带动就业，促进经济发展。"]
[33,"产业发展","配套基础设施项目","小型农田水利设施建设","桃林镇","中畈村","中畈村庄家组山塘维修","维修","中畈村庄家组","2023年2月","2023年3月","中畈村委会","全面清淤及山塘维修，堤坝长75米，宽20米，高5米",10,8,2,1,34,135,1,1,3,"目标1：方便村民农田耕种；目标2：使脱贫户增产；目标3：促进乡村振兴发展。","方便村民农田耕种，促进乡村振兴发展。"]
[34,"产业发展","配套基础设施项目","小型农田水利设施建设","桃林镇","中畈村","中畈村西冲山塘维修","维修","中畈村肖家组","2023年2月","2023年3月","中畈村委会","整塘清淤、清运、驳墈",8,6,2,1,24,108,1,2,7,"目标1：方便村民农田耕种；目标2：使脱贫户增产；目标3：促进乡村振兴发展。","方便村民农田耕种，促进乡村振兴发展。"]
[35,"产业发展","配套基础设施项目","小型农田水利设施建设","桃林镇","大畈村","大畈村刘家组山塘维修","维修","大畈村刘家组","2023年2月","2023年3月","大畈村委会","全面清淤及山塘维修，堤坝长30米，宽8米，高3米。",10,8,2,1,53,209,1,3,9,"目标1：方便村民农田耕种；目标2：使脱贫户增产；目标3：促进乡村振兴发展。","方便村民农田耕种；促进乡村振兴发展。"]
[36,"产业发展","配套基础设施项目","小型农田水利设施建设","桃林镇","大畈村","大畈村方家组新塘维修","维修","大畈村方家组","2023年2月","2023年3月","大畈村委会","整塘清淤清运，驳墈",8,6,2,1,102,423,1,5,16,"目标1：方便村民农田耕种；目标二：使脱贫户增产；目标3：促进乡村振兴发展。","方便村民农田耕种；促进村民增收及乡村振兴发展。"]
[37,"产业发展","配套基础设施项目","小型农田水利设施建设","桃林镇","金盆村","金盆村山塘维修","维修","金盆村梅家组、邓畈组、条二组","2023年2月","2023年3月","金盆村委会","三座山塘全面清淤、清运",15,8,7,1,113,462,1,3,7,"目标1：方便村民农田耕种；目标二：使脱贫户增产；目标3：促进乡村振兴发展。","方便村民农田耕种；促进村民增收及乡村振兴发展。"]
[38,"产业发展","配套基础设施项目","小型农田水利设施建设","桃林镇","畈上村","畈上村下条片新建水渠","新建","畈上村下条片","2023年3月","2023年4月","畈上村委会","长500米，宽1米，厚0.3米",20,10,10,1,18,75,1,1,3,"目标1：方便村民农田耕种；目标2：使脱贫户增产；目标3：促进乡村振兴发展。","方便村民农田耕种增产；促进经济发展。"]
[39,"产业发展","配套基础设施项目","小型农田水利设施建设","桃林镇","月山村","月山村上屋组河道维修","维修","月山村上屋组","2023年3月","2024年4月","月山村委会","打驳岸及硬化400立方米",12,10,2,1,105,368,1,3,7,"目标1：维护稳定脱贫；目标2：解决脱贫户种植生产用水问题","维护稳定脱贫，解决脱贫户种植生产用水问题"]
[40,"产业发展","生产项目","种植业基地","桃林镇","苎麻社区","苎麻社区福寿山200亩茶叶基地补苗与抚育","新栽","苎麻社区福寿山","2023年2月","2023年3月","苎麻社区","200亩茶叶基地补苗与抚育",20,16,4,1,342,1400,1,15,38,"目标1：发展集体经济；目标2：增加贫困户及居民生活幸福指数。","可提供部分居民及脱贫户的就业机会"]
[41,"产业发展","生产项目","种养殖业基地","桃林镇","桃林镇","桃林镇160户脱贫户及30户监测户产业奖补","新建","桃林镇","2023年2月","2023年4月","桃林镇人民政府","辖区18个村到户类产业发展",17,17,0,18,190,590,18,190,590,"目标1：帮助脱贫户及监测户发展产业；目标2：带动产业发展，帮助脱贫户及监测户创收。","帮助脱贫户及监测户发展产业；带动产业发展，帮助脱贫户及监测户创收。","到户类"]
[42,"就业项目","公益性岗位","就业帮扶","桃林镇","桃林镇","桃林镇公益性岗位","新建","桃林镇","2023年1月","2023年12月","桃林镇人民政府","辖区18个村54个公益性岗位",16.2,16.2,0,18,54,162,18,54,162,"目标1：帮助桃林镇辖区脱贫户及监测户解决就业；目标2：巩固脱贫攻坚同乡村振兴有效衔接","帮助桃林镇辖区脱贫户及监测户解决就业；巩固脱贫攻坚同乡村振兴有效衔接"]
[43,"乡村建设行为","农村基础设施建设","产业路建设","桃林镇","苎麻社区","苎麻社区福寿山产业路石洞水库路段道路硬化","道路硬化","苎麻社区福寿山","2023年2月10日","2023年3月10日","苎麻社区","0.75公里产业路硬化",30,25,5,1,342,1400,1,15,38,"目标1：提供社区居民及脱贫户的就业。目标2：方便出行、耕种，带动社区产业及休闲旅游。","巩固脱贫攻坚，促进乡村振兴，提高社区居民生活质量。"]
[44,"乡村建设行为","农村基础设施建设","农村供水保障设施建设","桃林镇","金盆村","金盆村饮用自来水安装","新建","金盆村长春片","2023年3月","2023年4月","金盆村委会","长春片区全覆盖",22,12,10,1,163,640,1,7,23,"目标1：解决村民安全饮水；目标2：提高村民生活质量；目标是3：促进乡村振兴发展","解决村民安全饮水，提升生活质量，增强村民节约用水意识。"]
[45,"乡村建设行为","农村基础设施建设","农村道路（桥梁）建设","桃林镇","旧李村","旧李村马岭组新建桥梁","新建","旧李村马岭组","2023年1月","2023年2月","旧李村委会","长7米，宽4米，厚0.4米",12,10,2,1,36,149,1,4,17,"目标1：方便村民出行；目标2：促进乡村振兴经济发展","方便村民耕种，为经济发展提供保障"]
[46,"乡村建设行为","农村基础设施建设","农村道路建设（机耕路）","桃林镇","横铺村","横铺村祠堂组机耕路硬化","新建","横铺村祠堂组","2023年3月","2023年4月","横铺村委会","长500米，宽3.5米，厚0.2米",15,9,6,1,78,320,1,4,10,"目标1：方便村民耕种，收割，增加脱贫户收入；目标2：促进乡村振兴经济发展","方便村民耕种，为经济发展提供保障"]
[47,"乡村建设行为","农村基础设施建设","水利设施建设","桃林镇","源冲村","源冲村木冲山塘维修","维修","源冲村中门组","2023年1月","2023年2月","源冲村委会","堤坝维修，塘管更换，山塘清淤",8,5,3,1,46,168,1,3,11,"目标1：除险加固保民生；目标2：为脱贫户和群众提供水利灌溉保农业创收","增加脱贫户收入，便利农民耕种，促进经济发展"]
[48,"乡村建设行为","农村基础设施建设","农村道路建设","桃林镇","大畈村","大畈村公路拓宽及硬化","新建","大畈村高家岭至坡里段","2023年2月","2023年4月","大畈村委会","全长0.8公里，宽不得低于4米",28,20,8,1,78,312,1,17,50,"目标1：改善道路设施。目标2：方便村民生产，出行；3：为经济社会发展提供保障","方便村民出行，促进经济发展"]
[49,"乡村建设行为","农村基础设施建设","农村道路建设","桃林镇","治水村","治水村村主干道公路拓宽","新建","治水村破塘组至德兴沿路6个组","2023年2月","2023年5月","治水村委会","拓宽3米，硬化4.5公里",50,30,20,1,859,3216,1,39,119,"目标1：方便村民出行及交通运输便利；目标2：促进经济发展","带动村民产业发展及交通便利"]
[50,"乡村建设行为","农村基础设施建设","农村道路（桥梁）建设","桃林镇","治水村","治水村桥梁建设","重建","治水村陈条、近池组各一座","2023年2月","2023年4月","治水村委会","重建2座分别为长8米，宽7米",30,20,10,1,856,3216,1,39,119,"目标1：使村民出行更方便；目标2：促进乡村振兴发展","带动村民产业发展及交通便利"]
[51,"乡村建设行为","农村基础设施建设","农村道路建设（通村、通组、通户路）","桃林镇","坪上村","坪上村汤桥口至君王桥公路拓宽","公路拓宽","坪上村","2023年3月","2023年4月","坪上村委会","长1285米，宽3米，厚20公分",30.84,12,18.84,1,118,606,1,3,9,"目标1：改善水利设施；目标2：方便了脱贫户及周边老百姓安全出行；3：为经济发展提供保障，增加脱贫户收入，降低贫户户发生机率。","改善水利设施，方便了脱贫户及周边的安全出行，为经济发展提供保障，增加脱贫户收入，降低贫户户发生机率。"]
[52,"产业发展","生产项目","种植业基地","羊楼司镇","新屋村","新屋村粮食生产","新建","临湘市羊楼司镇新屋村李家组","2023.4.","2023.6. ","新屋村","种植水稻210亩",30.3,30,0.3,1,120,452,1,15,49,"种植水稻210亩，为脱贫户及监测户提供就业岗位，增加收入","流转土地210亩，带动产业发展和农民就业增收。"]
[53,"乡村建设行动","农村基础设施","其他","羊楼司镇","尖山社区","竹情安置小区中38栋南侧山体滑坡整修","基础设施","尖山社区竹情安置小区","2023.4.","2023.7.","尖山社区","700平方",29.6,26,3.6,1,510,2120,0,4,186,"改善人居环境，排除安全隐患","改善人居环境，排除安全隐患"]
[54,"易地搬迁后扶","易地搬迁后扶","“一站式”社区综合服务设施建设","羊楼司镇","尖山社区","竹情安置小区基础设施维护","基础设施","尖山社区竹情安置小区","2323.3.","2023.5.","尖山社区","竹情安置小区所有基础设施",15.7,15,0.7,1,510,2120,0,4,186,"完善基础设施，美化人居环境，让易地搬迁户能安心搬得出，住得稳","完善基础设施，美化人居环境，让易地搬迁户能安心搬得出，住得稳"]
[55,"产业发展","生产项目","种植业基地","羊楼司镇","文白社区","茅铺山板栗园","新建","上畈组茅铺山","2023年2月","2023年4月","文白社区","150亩",95,10,85,null,23,180,0,3,20,"种植板栗150亩，为脱贫户及监测户增加收入","流转土地150亩，带动产业发展和农民就业增收"]
[56,"乡村建设行动","农村基础设施","其他","羊楼司镇","文白社区","港渠护砌","新建","赵家组港渠护砌",2023.2,2023.6,"文白社区","200米",9.5,5,4.5,1,26,214,0,4,18,"护砌港渠200米，沿港农户农田能够有水灌溉","使沿线农户稻谷增加收入"]
[57,"产业发展","生产项目","养殖业基地","羊楼司镇","黄金村","黑山羊养殖",null,"黄金村排楼组","2023年4月","2023年5月","黄金村","搭棚100平方养殖黑山羊60只",12,5,7,1,26,150,0,3,10,"养殖黑山羊60只，为村民增加收入","流转土地100平方，带动养殖产业发展和村民利益增收"]
[58,"产业发展","生产项目","种植业基地","羊楼司镇","明星村","明星村斗岭组中草药种植基地","新建","明星村斗岭组","2023年2月","2023年4月","临湘市羊楼司镇明星村","种植中草药120亩",65,5,60,1,33,141,1,4,14,"种植中草药120亩，为脱贫户及监测户增加收入","流转土地120亩，带动产业发展和农民就业增收"]
[59,"产业发展","生产项目","种植业基地","羊楼司镇","梧桐铺社区","梧桐铺棉油种植基地","新建","梧桐铺社区刘家组","2023年5月","2024年4月","临湘市羊楼司镇梧桐铺社区","种植棉花、油菜共110亩",18,12,6,1,34,187,0,2,5,"种植棉花、油菜110亩，为脱贫户提供就业岗位，增加收入","流转土地55亩，带动产业发展和农民就业增收。"]
[60,"产业发展","生产项目","种植业基地","羊楼司镇","金鸡社区","金鸡社区八月蛋种植基地","新建","金鸡社区三屋组","2023年2月","2023年5月","临湘市羊楼司镇金鸡社区","种植八月蛋20亩",15,10,5,1,28,125,0,8,25,"种植八月蛋20亩，为脱贫户提供就业岗位，增加收入","流转土地30亩，带动产业发展和农民就业增收。"]
[61,"产业发展","生产项目","休闲农业与乡村旅游","羊楼司镇","梅池村","梅池民宿建设一期","新建","梅池村","2023年2月","2023年10月","临湘市羊楼司镇梅池村","民宿建设223平方",50,20,30,1,136,238,0,4,6,"建设民宿223平方，为脱贫户及监测户提供就业岗位，增加收入","带动旅游产业发展和农民就业增收"]
[62,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","羊楼司镇","柘庄村","柘庄村道路改造","改造","柘庄村","2023年3月","2023年4月","临湘市羊楼司镇柘庄村","村道路改造4.7公里",95,50,45,1,426,2065,0,10,23,"道路改造，为脱贫户及监测户提供就业岗位，增加收入","道路改造4.7公里，带动产业发展和农民就业增收"]
[63,"产业发展","生产项目","种植业基地","羊楼司镇","黄沙村","黄沙村粮油种植基地（一期）","新建","黄沙村坝头组","2023年1月","2023年6月","黄沙村","种植油菜500亩",15,5,10,1,125,715,0,9,32,"种植油菜500亩，为脱贫户及监测户增加收入","流转土地500亩，带动产业发展和农民就业增收"]
[64,"产业发展","配套基础设施项目","小型农田水利设施建设","羊楼司镇","黄沙村","黄沙村河堤护砌及疏通","基础设施","黄沙村","2023年3月","2023年8月","临湘市羊楼司镇黄沙村","河堤护砌800米、疏通河道2000米",30,10,20,1,300,1500,0,15,"53人","消除水患、确保粮食生产种植，增加群众收入","为脱贫户提供就业岗位，增加收入"]
[65,"产业发展","生产项目","种植业基地","羊楼司镇","龙窖山村","龙窖山猕猴桃种植基地建设（一期）","水果采摘园种植","龙窖山村铺上组肖家畈","2023年3月","2023年11月","临湘市羊楼司镇龙窖山村","整地40亩、深耕40亩、辅路1200米、新栽猕猴桃40亩",20,15,5,1,315,1260,0,26,81,"融合一二三产发展，打造乡村旅游产品，解决周边群众和脱贫人口和防止返贫监测对象户增加经济收入","合作社+农户、土地流转、劳动就业、脱贫户分红"]
[66,"产业发展","生产项目","种植业基地","羊楼司镇","雅团村","雅团村粮食生产","新建","雅团村","2023.3. ","2023.10. ","临湘市羊楼司镇雅团村","种植水稻360亩",27.6,25,2.6,1,139,463,0,12,35,"种植水稻360亩，为脱贫户提供就业岗位，增加收入。","流转土地360亩，带动产业发展和村民就业增收。"]
[67,"产业发展","生产项目","种植业基地","羊楼司镇","和平村","和平村立体养殖","新建","和平村张家冲组","2023.4.","2023.6.","临湘市羊楼司镇和平村","搭棚500平方米.鱼塘4000平方米.鹅100只.鱼500尾.羊30只.鸡200只",16,6,10,1,"87户","356人",0,"3户","11人","鹅100只.鱼500尾.羊30只.鸡200只.为村集体增加收入","流转4500平方米带动立体养殖和村集体增收"]
[68,"产业发展","生产项目","种植业基地","羊楼司镇","三港村","生态农庄","新建","细港组","2023.4.","2023.10.","三港村","建设民宿及农庄",80,70,10,1,775,3015,1,30,91,"建设民宿及农庄，增加集体经济收入，发展农民就业增收","建设民宿及农庄，增加集体经济收入，发展农民就业增收"]
[69,"产业发展","生产项目","种植业基地","羊楼司镇","三港村","采摘园","新建","细港组","2023.4.","2023.10.","三港村","种植面积20亩",50,40,10,1,775,3015,1,30,91,"流转土地30亩为脱贫户及监测户提供岗位，增加集体经济收入","流转土地30亩，带动产业发展和农民增收"]
[70,"就业项目","公益性岗位","公益性岗位","羊楼司镇","羊楼司镇","羊楼司镇公益性岗位2023","新建","羊楼司镇","2023年1月","2023年5月","临湘市羊楼司镇","脱贫户及监测户343户1024人",36,18,18,14,6,236,3,60,236,"为部分有劳力的脱贫户及监测户设岗增收","通过设立岗位激发脱贫对象劳动激情，增加收入"]
[71,"就业项目","务工补助","劳动奖补","羊楼司镇","羊楼司镇","羊楼司镇产业奖补2023","新建","羊楼司镇","2023年1月","2023年5月","临湘市羊楼司镇","脱贫户及监测户343户1024人",25,25,null,20,343,1024,3,260,803,"改善困难群众的生产生活，增加村民收入和带动村级集体经济事业发展。","通过产业奖补部分重点产业发展对象，激发各村（社区）群众发展生产和村（社区）发展集体产业的的积极性，同时也能改善困难群众的生产生活，增加村民收入和带动村级集体经济事业发展。"]
[72,"产业发展","生产项目","养殖业基地","羊楼司镇","友爱村","黑山羊养殖","新建","友爱村下湾组","2023年4月","2023年5月","友爱村","搭棚120平方，养殖黑山羊80只",20,10,10,1,306,1380,0,8,25,"养殖黑山羊80只，为村民增加收入","流转土地120平方，带动养殖产业发展和村民利益增收"]
[73,"产业发展","加工物流项目","产地初加工和精深加工","羊楼司镇","双山村","景然新材料公司入股经营","新建","双山村大屋组","2023年3月","2023年8月","临湘市羊楼司镇双山村","新增生产线一条，设备12台",80,30,50,1,32,108,0,2,3,"增加一条生产线，设备12台，为脱贫户提供就业岗位，增加收入","土地流转20亩，带动产业发展，为农民增加就业收入"]
[74,"产业发展","生产项目","种植业基地","羊楼司镇","石壁村","双季稻种植基地提质改造","新建","赵家、咀上、新屋、孟家、李访组","2023年1月","2023年5月","临湘市羊楼司镇石壁村","山塘维修、沟渠疏通机埠、排渠建设",40,35,5,1,350,980,0,4,13,"保障农田生产、增产增收，为脱贫户及监测户提供就业岗位，增加收入","带动产业发展和农民就业增收。"]
[75,"产业发展","生产项目","种植业基地","羊楼司镇","石壁村","有机稻油基地扩面100亩","新建","莲花组、何家组","2023年1月","2023年7月","临湘市羊楼司镇石壁村","100亩稻油基地提质改造",20,18,2,1,280,620,0,5,20,"为脱贫户及监测户提供就业岗位，增加收入","流转土地39亩，带动产业发展和农民就业增收"]
[76,"产业发展","生产项目","种植业基地","羊楼司镇","如斯村","如斯村陈家冲板栗园基地（二期）","新建","如斯村下湾组大西组","2023年2月","2023年4月","临湘市羊楼司镇如斯村","种植板栗60亩",18,15,3,1,43,215,0,1,3,"增加村集体经济收入，同时为脱贫户提供劳力就业，增加收入。","流转林地60亩，带动产业发展和当地农民就业增收。"]
[77,"产业发展","生产项目","种植业 基地","黄盖","广坪村","黄盖镇广坪村棉花基地建设","新建","广坪村新洲组","4月","12月","黄盖镇广坪村","300亩棉花基地建设，包括机耕路硬化等",60,40,20,1,35,110,1,2,4,"完成300亩棉花基地建设，带动广坪村棉花特色产业发展","通过进行棉花基地打造，带动棉花产业发展，带动新洲组群众就业致富，提升农户经济收入。"]
[78,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄盖","团山社区","黄盖大道支路拓宽硬化及污水道清理","新建","团山社区黄盖大道","5月","6月","黄盖镇团山社区","支路拓宽硬化及污水道清理约3公里",15,10,5,1,30,95,1,2,6,"完成约3公里道路硬化和污水道清理，为村民的出行和农作提供更多的便利。","提高村民劳动致富的热情，降低了返贫致贫发生率，稳定脱贫攻坚成果，助力乡村振兴。"]
[79,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","黄盖","团山社区","文卫路污水道提质改造及支路硬化维护","维修","团山社区文卫路","5月","6月","黄盖镇团山社区","污水道提质改造及支路硬化维护约1.5公里",15,10,5,1,48,100,1,3,7,"完成污水道提质改造及支路硬化维护约1.5公里，改善居民生产生活条件。","改善团山社区文卫路居民生产生活条件，为出行和农作提供更多便利，提高生活质量。"]
[80,"乡村建设行动","农村基础设施","农村供水保障设施建设","黄盖","团山社区","萝卜湖水库维护及应急砂石库建设","维修","团山社区萝卜湖","5月","6月","黄盖镇团山社区","路面砂石硬化、护坡渠道维护、栏筛维护、建设砂石库200平方米",30,20,10,1,15,40,1,3,9,"通过萝卜湖水库维护及应急砂石库建设，为我镇应急水源管理提供保障。","提高村民生活质量，保障安全用水。"]
[81,"产业发展","生产项目","种植业基地","黄盖",null,"临湘市黄盖镇高标准棉油轮作基地建设","新建","黄盖镇广坪村","3月","5月","黄盖镇","棉花基地1000亩，包括沟渠与排灌系统改造、育苗大棚建设等。",360,360,0,1,210,860,1,2,8,"达到年产值300万元，创造利润120万元。改善土塘条件，对区域生态环境修复起到重要作用。改善生产条件，提高现代种植业物质装备水平，为加快现代种植业发展奠定坚实基础","提供农户就业机会，显著改善生产条件，提高棉油轮作综合生产效益、增加职工收入。"]
[82,"就业项目","公益性岗位","公益性岗位","黄盖",null,"黄盖镇公益岗位奖补","新建","黄盖镇","1月","12月","黄盖镇","提供公益性岗位给脱贫户、监测户",3,2,1,4,4,12,4,4,12,"为脱贫户、监测户提供就业机会，稳定增收，减少返贫致贫风险。","提供就业机会，促进农户自主致富，提高经济收入。"]
[83,"产业发展","生产项目","水产养殖业发展","黄盖",null,"黄盖镇产业奖补","新建","黄盖镇","1月","12月","黄盖镇","对积极发展种养殖业的脱贫户及监测户依照标准直接进行奖补",10,10,0,4,31,89,4,31,89,"对全镇31户发展产业的农户按标准直接进行奖补，提高农户种养殖热情，增加经济收入。","以发放奖补的形式鼓励农户们进一步发展产业，解决在产业发展上的问题，达到收入增长的目的。"]
[84,"就业项目","公益性岗位","公益性岗位","白羊田","-","白羊田镇公益岗位奖补","新建","白羊田镇","2023年1月","2023年12月","白羊田镇","奖补脱贫户、监测户公益性岗位",16.5,16.5,0,7,55,202,2,55,202,"帮助脱贫户、监测户就近就地就业，促进受益户稳定增收，防范返贫致贫风险。","提供就业机会，促进农户自主致富，提高经济收入。"]
[85,"产业发展","生产项目","养殖业基地","白羊田","-","白羊田镇产业奖补","新建","白羊田镇","2023年1月","2023年12月","白羊田镇","对有劳动能力，发展意愿的脱贫户、监测户依照标准直接进行奖补",27,27,0,7,165,500,2,165,500,"对全镇422户中符合有劳动能力，发展意愿条件的脱贫户、监测户依照标准直接进行奖补，提高农户种养殖热情，增加经济收入。","以发放奖补的形式鼓励农户们进一步发展产业，解决在产业发展上的问题，达到收入增长的目的。"]
[86,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田","万利村","一至四组道路拓宽硬化","改建","万利村一、二、三、四组","2023年3月","2023年4月","白羊田镇万利村","道路拓宽至4.5米，硬化全长250米",15,10,5,1,302,1478,0,28,73,"完成一至四组公路拓宽硬化全长约250米，为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为出行和农作提供更多便利，提高生活质量，助力乡村振兴。"]
[87,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田","万利村","毛草街至村部道路拓宽硬化","改建","毛草街至万利村部","2023年5月","2023年6月","白羊田镇万利村","道路拓宽1.5米，硬化全长600米",25,7,18,1,728,3015,0,32,82,"完成毛草街至村部道路拓宽硬化全长约600米，改善村民生产生活条件，为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为出行和农作提供更多便利，提高生活质量，助力乡村振兴。"]
[88,"产业发展","生产项目","种植业基地","白羊田","方山村","王竹组油茶种植","新建","方山村王竹组","2023年1月","2023年12月","白羊田镇方山村","发展油茶基地100亩",30,15,15,1,67,268,0,18,41,"提高农户种养殖热情，增加经济收入。","提供就业机会，促进农户自主致富，提高经济收入。"]
[89,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田","方山村","殷家至登东道路硬化","改建","方山村登东组至殷家组","2023年1月","2023年12月","白羊田镇方山村","道路拓宽1.5米，硬化全长650米",28,10,18,1,913,2768,0,68,176,"完成登东至殷家路拓宽650米硬化，改善村民生产生活条件，为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为出行和农作提供更多便利，提高生活质量，助力乡村振兴。"]
[90,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田","西山村","村部至何山组道路升级改造","改建","村部至何山组","2023年3月","2023年9月","白羊田镇西山村","道路拓宽至5米，硬化全长2.5公里",75,30,45,1,560,1640,1,12,38,"完成村部至何山公路拓宽硬化全长约2.5公里，为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为出行和农作提供更多便利，提高生活质量，助力乡村振兴。"]
[91,"乡村建设行动","农村基础设施","农村供水保障设施建设","白羊田","西山村","安全饮水改造","新建","西山村西尧、潘畈、西冲组","2023年3月","2023年6月","白羊田镇西山村","完成三个组的集中供水设施建设",20,10,10,1,482,1890,1,8,32,"完成3个组482户村民生活饮水改善,保障村民饮水安全，进一步巩固脱贫攻坚成果。","改善村民生活饮水,保障村民饮水安全，进一步巩固脱贫攻坚成果。"]
[92,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田","八百村","周后组至高泉组道路硬化","改建","周后组至高泉组","2023年3月","2023年5月","白羊田镇八百村","道路硬化全长1.3公里",30,21,9,1,125,321,0,4,17,"完成周后组至高泉组道路硬化全长约1.3公里，为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为出行和农作提供更多便利，提高生活质量，助力乡村振兴。"]
[93,"乡村建设行动","农村基础设施","农村供水保障设施建设","白羊田","八百村","西干渠改造","改建","四级电站至跃进组","2023年9月","2023年11月","白羊田镇八百村","西干渠改造维修全长1000米",25,20,5,1,112,468,0,13,42,"完成西干渠改造维修，全长约1000米，保障群众农业灌溉，激发群众发展生产的积极性，促进增收。","改善农业生产条件，保障群众农业灌溉，激发群众发展生产的积极性，促进增收。"]
[94,"产业发展","加工物流项目","产地初加工和精深加工","白羊田","八百村","竹木加工","新建","八百村","2023年3月","2023年12月","白羊田镇八百村","建成竹木初加工基地，收购农户竹木，初加工后销售",150,102,48,1,32,89,0,32,89,"完成竹木加工基地建设，包括厂房、设备等，规模化进行初加工后销售。","加强农户自有竹木的销售，同时能为附近群众提供就业机会，促进增收。"]
[95,"产业发展","生产项目","种植业基地","白羊田","双泉村","生姜种植","新建","双泉村新屋组","2023年2月","2023年6月","白羊田镇双泉村","生姜种植50亩",35,30,5,1,7,16,1,7,16,"完成生姜种植50亩，带动脱贫户和监测户发展种植业，激发生产热情，进一步提升农户收入，巩固脱贫攻坚成果。","带动脱贫户和监测户发展种植业，激发生产热情，进一步提升农户收入，巩固脱贫攻坚成果。"]
[96,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田","双泉村","新屋组-左家组道路拓宽","改建","双泉村新屋组-左家组","2023年3月","2023年5月","白羊田镇双泉村","拓宽公路全长1.6公里。",48,40,8,1,420,1260,1,12,28,"完成新屋组-左家组道路拓宽，全长约1.6公里，为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为出行和农作提供更多便利，提高生活质量，助力乡村振兴。"]
[97,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田","双泉村","新屋组-左家组道路硬化","改建","双泉村新屋组-左家组","2023年5月","2023年8月","白羊田镇双泉村","硬化公路全长1.6公里。",91,50,41,1,420,1260,1,12,28,"完成新屋组-左家组道路硬化，全长约1.6公里，为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为出行和农作提供更多便利，提高生活质量，助力乡村振兴。"]
[98,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田","双泉村","左家组道路白改黑","改建","双泉村左家组","2023年9月","2023年11月","白羊田镇双泉村","油化公路全长1.6公里。",58,50,8,1,420,1260,1,12,28,"完成公路油化1.6公里，为村民的出行和农作提供更多的便利。","改善村民生产生活条件，为出行和农作提供更多便利，提高生活质量，助力乡村振兴。"]
[99,"产业发展","生产项目","养殖业基地","白羊田","双泉村","家禽养殖","新建","新屋组","2023年1月","2023年6月","白羊田镇双泉村","养殖3000只鸡",45,40,5,1,20,52,1,3,6,"完成鸡养殖3000只，带动脱贫户和监测户发展养殖业，激发生产热情，进一步提升农户收入，巩固脱贫攻坚成果。","带动脱贫户和监测户发展养殖业，激发生产热情，进一步提升农户收入，巩固脱贫攻坚成果。"]
[100,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","白羊田","白羊田社区","机埠路扩宽硬化","改建","白羊田社区","2023年7月","2023年8月","白羊田镇白羊田社区","机埠路扩宽硬化400米",26,10,16,1,92,340,0,6,13,"完成该机埠路扩宽400米硬化，改善周边群众生产生活条件，方便该路段处种田农户（含脱贫户和检测户）的运输，激发内生动力，进一步提升农户收入，巩固脱贫攻坚成果。","带动脱贫户和监测户就地就近业，改善周边群众生产生活条件，巩固脱贫攻坚成果。"]
[101,"产业发展","产业服务支撑项目","农业社会化服务","坦渡镇",null,"坦渡镇产业帮扶","新建","坦渡镇","2023年3月","2023年6月","坦渡镇人民政府","脱贫户与监测户336户发展产业",18.55,18.55,0,13,336,668,3,336,668,"直接帮扶，提升脱贫户与监测户增加产业收入。","让每户监测户与脱贫户增加产业收入1000元以上，从而巩固脱贫成效。"]
[102,"就业项目","公益性岗位","公益性岗位","坦渡镇",null,"坦渡镇公益性岗位","新建","坦渡镇","2023年1月","2023年12月","坦渡镇人民政府","30个公益性岗位补贴发放",9,9,0,13,30,30,3,13,30,"直接帮扶，提升脱贫户与监测户增加务工收入。","让参加公益性岗位的脱贫户和监测户务工收入增加3000元以上，从而巩固脱贫成效。"]
[103,"产业发展","生产项目","种植业基地","坦渡镇","韩桥村","五德湘菜籽油","新建","韩桥村河田片","2023年1月","2023年4月","韩桥村","丰油789种植600亩",40,10,30,1,380,1420,0,21,53,"引进五德湘菜籽油企业，旱地出租，减少耕地抛荒，增加种植收入。","为脱贫户增收5万元。"]
[104,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","韩桥村","岭上、上屋组渠道疏通","改建","岭上、上屋","2023年1月","2023年4月","韩桥村","渠道疏通500米，宽1米，高1米",33,8,25,1,82,350,0,6,21,"渠道畅通，给群众解决生产难问题。","减少生产成本，从而为脱贫户增收1.5万元。"]
[105,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","万峰村","楠木组公路硬化","新建","楠木组","2023.4.1","2023.9.30","万峰村","组级公路硬化800米",18,10,8,1,24,121,0,7,21,"长800米、宽3.5米、厚20公分","减少农户、脱贫户农产品运输成本，消除道路安全隐患"]
[106,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","万峰村","万峰村山塘整修","改建","万峰村","2023.3.1","2023.6.30","万峰村","山塘整修2座",8,5,3,1,68,280,0,13,46,"2座塘护坡长70米，清淤4600方，底部埋管56米","解决农户、脱贫户农田灌溉，稳产增收。"]
[107,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","农胜村","瑶头组抗旱机埠","新建","农胜村瑶头组","2023年4月25日","2023年5月25日","坦渡镇农胜村","30㎡",24,16,8,1,39,137,0,5,15,"解决农户农业生产灌溉难的问题，从而使脱贫户农业收入增加500元。","脱贫户增加收入500元"]
[108,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","农胜村","三林塘改造","改建","农胜村三林组","2023年6月7日","2023年8月7日","坦渡镇农胜村","清淤1400m³",12,8,4,1,21,69,0,2,4,"完善基础设施，改善农户生产生活条件，增加收入300余元。","脱贫户收入增加300元"]
[109,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","农胜村","畈屋组道路拓宽","扩建","农胜村畈屋组","2023年3月1日","2023年4月1日","坦渡镇农胜村","长1500m宽1.5m",32,22,10,1,516,1966,0,22,57,"解决农户出行难题，并减少农副产品运输成本，增加脱贫户收入500元","脱贫户收入增加500元"]
[110,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","晓阳村","胡家组山塘整修","改建","胡家组","2023年5月1日","2023年7月1日","坦渡镇晓阳村","扩建塘面积18亩，加深度3米。新建排水渠520米",17,5,12,1,73,295,0,10,35,"工程：扩建塘面积18亩，加深度3米。新建排水渠520米。解决村民与脱贫户灌溉难问题，有效提高生产能力","为脱贫户增收400元--600元"]
[111,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","晓阳村","铁路组公路硬化","改建","铁路组","2023年9月1日","2023年10月1日","坦渡镇晓阳村","硬化长625米宽3米厚0.2米",25,10,15,1,28,138,0,10,33,"工程：沙石硬化长1200米宽5米厚0.3米；解决村民与脱贫户出行难问题，方便机耕生产与运输。","为脱贫户增收400元--600元"]
[112,"产业发展","生产项目","油茶产业发展","坦渡镇","晓阳村","临湘市坦渡镇晓阳村油茶基地新建项目","新建油茶基地","坦渡镇晓阳村三组、五组","2023年1月1日","2023年12月1日","坦渡镇晓阳村","新建油茶65亩",23,20,3,1,128,516,0,20,59,"供应油茶原料，解决就业、增加脱贫（监测）户经济收入","企业+村集体+农户，劳务用工和土地流转                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                                  等"]
[113,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","桐梓铺社区","泉井组大塘整修","改建","泉井组","2023年4月1日","2023年12月31日","桐梓铺\n社区","清淤、扩容20亩40000m³、安装40#水泥涵管30米、溢洪道30米",20,15,5,1,112,386,1,14,47,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。","为脱贫户增收400元--600元"]
[114,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","桐梓铺社区","柴家组排洪渠整修","改建","柴家组","2023年4月1日","2023年12月31日","桐梓铺\n社区","清淤、护砌长400米、宽1米、高2.5米",90,80,10,1,149,495,1,15,51,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。","为脱贫户增收400元--600元"]
[115,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","桐梓铺社区","胡家组干垅塘扩建项目","改建","胡家组","2023年4月1日","2023年12月31日","桐梓铺\n社区","清淤5亩约3500m³",5,3,2,1,112,386,1,14,47,"完善基础设施，解决脱贫户水田灌溉困难，增加脱贫户收入，提高经济效益。","为脱贫户增收400元--600元"]
[116,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","大和村","三口塘小型农田水利建设","改建","大和村","2023.1.2","2023.3.30","大和村","三口塘山塘改造",60,40,20,1,65,185,1,20,50,"解决农田灌溉难问题","为脱贫户增收400元--600元"]
[117,"乡村建设行动","农村基础设施","农村道路建设（通户路）","坦渡镇","灯明村","学堂组公路硬化","新建","灯明村学堂组","2023.5.13","2023.5.20","灯明村","长180米、宽3.5米、厚20公分",8.5,3,5.5,1,108,456,0,11,36,"解决灯明村部分群众及脱贫户出行难问题，提高生产生活质量，减少运输成本，增加脱贫户收入，巩固脱贫成效。","为脱贫户增收400元--600元"]
[118,"乡村建设行动","农村基础设施","农村道路建设（通户路）","坦渡镇","灯明村","凉亭组公路硬化","新建","灯明村凉亭组","2023.5.21","2023.5.27","灯明村","长120米、宽3米、厚20 公分",6.5,3,3.5,1,98,397,0,10,33,"解决灯明村部分群众及脱贫户出行难问题，提高生产生活质量，减少运输成本，增加脱贫户收入，巩固脱贫成效。","为脱贫户增收400元--600元"]
[119,"乡村建设行动","农村基础设施","农村供水保障设施建设","坦渡镇","灯明村","自来水管安装","新建","官庄陈家组","2023.4.8","2023.5.10","灯明村","长3050米，63管450米，50管200米，40管600米，32管300米，25管1500米。",10,5,5,1,32,192,0,3,10,"解决官庄陈家组群众及脱贫户用水压力小问题，使得陈家组群众和脱贫户用水更加方便畅通，提高了群众及脱贫户生产生活问题。","解决官庄陈家组群众饮水问题"]
[120,"乡村建设行动","农村基础设施","产业路、资源路、旅游路建设","坦渡镇","定湖村","经果园公路硬化","新建","定湖村周家垄组","2023年4月10日","2023年5月10日","定湖村","公路总长500米，宽4.5米，厚20公分",27,20,7,1,325,1680,0,34,116,"完善基础设施，解决脱贫户和农户出行难的问题，减少农副产品销售的运输成本，使脱贫户增收800元左右，从而巩固脱贫成果。","为脱贫户增收800元"]
[121,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","定湖村","周家垄组公路拓宽","改建","定湖村周家垄组","2023年5月15日","2023年6月15日","定湖村","公路总长1200米，拓宽1.5米，厚20公分",40,10,30,1,360,1820,0,34,116,"完善基础设施，解决脱贫户和农户出行难的问题，减少农副产品销售的运输成本，使脱贫户增收800元左右，从而巩固脱贫成果。","为脱贫户增收800元"]
[122,"产业发展","生产项目","种植业基地","坦渡镇","定湖村","石树咀沃柑园扩建","扩建","定湖村老庄组","2023年3月1日","2023年3月31日","定湖村","扩建面积20亩，混种油茶2000棵",20,12,8,1,296,1580,0,34,116,"完善产业发展项目，解决脱贫户和农户就业问题，增加村集体经济收入，使脱贫户增收1000元左右，从而巩固脱贫成果。","为脱贫户增收1000元"]
[123,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","坦渡村","叶家组公路硬化","新建","叶家组至湾里组","2023.3.1","2023.12.31","坦渡村","组级公路硬化600米、宽4米、厚20公分",16,6,10,1,84,354,0,12,38,"工程：硬化长600米、宽4米、厚20公分，解决村民与脱贫户出行难，方便运输，巩固脱贫成效","为12户脱贫户38人增加收入400-600元"]
[124,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","坦渡村","许阳组山塘整修","改建","许阳组","2023.3.1","2023.12.31","坦渡村","山塘整修1座清淤4亩、安装40#水泥涵管6米、溢洪道3、清淤深度1.5米米",5,4,1,1,36,160,0,5,17,"清淤4亩、安装40#水泥涵管6米、溢洪道3、清淤深度1.5米米，解决水利种植，巩固脱贫成效","为5户脱贫户17人增加收入400-600元"]
[125,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","坦渡村","渠道硬化","改建","湾里组","2023.5.1","2023.12.31","坦渡村","渠道硬化400米渠道硬化长度400米、宽1米、高1.2米、清理宽1米",16,6,10,1,340,1100,0,13,41,"渠道硬化长度400米、宽1米、高1.2米、清理宽1米，解决水利种植，巩固脱贫成效","为13户脱贫户41人增加收入400-600元"]
[126,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","新湖村","赵家组级公路硬化","新建","新湖村赵家组","2023年4月10日","2023年5月10日","新湖村","公路总长420米，宽4米，厚20公分",22,15,7,1,315,1834,0,30,89,"完善基础设施，解决脱贫户和农户出行难的问题，减少农副产品销售的运输成本，使脱贫户增收800元左右，从而巩固脱贫成果。","为脱贫户增收400元--600元"]
[127,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","新湖村","涂四垅组级公路硬化","新建","新湖村涂四垅家组","2023年7月18日","2023年10月10日","新湖村","公路总长560米，宽4.5米，厚20公分",28,20,8,1,330,1972,0,30,89,"完善基础设施，解决脱贫户和农户出行难的问题，减少农副产品销售的运输成本，使脱贫户增收500元左右，从而巩固脱贫成果。","为脱贫户增收400元--600元"]
[128,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","新湖村","石垅山机埠整修","改建","新湖村石垅山组","2023年4月1日","2023年5月1日","新湖村","更换变压器及水泵",6,5,1,1,284,1324,0,30,89,"完善基础设施，解决脱贫户和农户用水的问题，减少农业的生产成本，使脱贫户增收600元左右，从而巩固脱贫成果。","为脱贫户增收400元--600元"]
[129,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","红旗村","燕路坡组公路水泥硬化","新建","燕路坡组","2023年2月1日","2023年4月1日","红旗村","水泥硬化长200米宽3.5米厚0.2米",8,5,3,1,15,60,0,6,16,"解决村民与脱贫户出行难问题，减少运输成本。","为脱贫户增收400元--700元"]
[130,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","红旗村","下螃垄组公路沙石硬化","新建","下螃垄组","2023年2月1日","2023年4月1日","红旗村","沙石硬化长1200米宽5米厚0.3米",12,8,4,1,30,120,0,10,22,"解决村民与脱贫户出行难问题，方便机耕生产与运输。","为脱贫户增收400元--700元"]
[131,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","红旗村","砖冲组山塘护坡、清淤","新建","砖冲组","2023年8月1日","2023年10月1日","红旗村","护坡长80米、清淤3500方",10,6,4,1,14,56,0,8,17,"解决村民与脱贫户灌溉难问题，有效提高生产能力","为脱贫户增收400元--700元"]
[132,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","长岭社区","长岭社区刘家垄组山塘清淤","改建","长岭社区刘家垄组","2023年1月10日","2023年2月10日","长岭社区","20亩",10,8,2,1,1102,3151,0,21,44,"改建基础设施，有效改善脱贫户和居民水体质量，提升山塘的蓄水能力以及河道防洪排涝作用，从而巩固脱贫成果。","为脱贫户增收400元--600元"]
[133,"乡村建设行动","农村基础设施","农村道路建设(通村、通户路)","坦渡镇","长岭社区","长岭社区杨家庄至红旗公路硬化","新建","长岭社区杨家庄组","2023年2月5日","2023年3月5日","长岭社区","公路长500米，宽3.5米，厚20公分",24.5,20,4.5,1,1102,3151,0,21,44,"完善基础设施，解决脱贫户和农户出行难的问题，减少农副产品销售的运输成本，使脱贫户增收800元左右，从而巩固脱贫成果。","为脱贫户增收400元--600元"]
[134,"产业发展","生产项目","种植业基地","坦渡镇","联合村","同心组黄桃园","新建","同心组","2023年2月","2023年11月18日","联合村","50亩",25,10,15,1,85,309,1,17,45,"解决周边部分农户及脱贫户的就业问题，使脱困户及农户收入增加","该项目增加脱贫户集体经济收入问题，受益脱贫户85户309人，现返贫发生率为0"]
[135,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","联合村","百万水库清淤","改建","桥头组",202309,"2023年11月27日","联合村","5000立方米",18,8,10,1,96,345,1,18,55,"完善基础设施，解决脱贫户水田灌溉问题","解决脱贫户共96户345人的水田灌溉问题，增加脱贫户收入600元以上，从而巩固脱贫成果。"]
[136,"产业发展","配套基础设施项目","小型农田水利设施建设","坦渡镇","联合村","百干渠清淤","改建","联合村",202303,"2023年11月20日","联合村","3公里",15,7,8,1,93,326,1,17,47,"完善基础设施，解决脱贫户水田灌溉问题","解决脱贫户共93户326人的水田灌溉问题，增加脱贫户收入600元以上，从而巩固脱贫成果。"]
[137,"农村基础建设","农村道路建设","配套基础设施","五里牌街道","火炬村","公路硬化","改建","火炬村叶家组",2023.08,"2023.10","火炬村","公路硬化1000米",35,20,15,1,33,300,null,2,7,"此项目可以保证300人正常出行。","此路改建好之后可以提高农民的出行质量，达到农民平安出行的满意度，使农民家中的农产品外出销售，从而提高农民收入。"]
[138,"农村基础建设","农村道路建设","配套基础设施","五里牌街道","千针村","公路白改黑","改建","千针村老千组","2023.01.02","2023.01.20","千针村","公路白改黑",12,8,4,1,36,235,null,3,8,"此项目可以保证235人正常出行","此路改建好之后可以提高农民的出行质量，达到农民平安出行的满意度，使农民家中的农产品外出销售，从而提高农民收入。"]
[139,"农村基础建设","农村水利建设","配套基础设施","五里牌街道","千针村","安全饮水","新建","千针村大畈组至方家组","2023.01.01","2023.01.17","千针村","1000米",10,5,5,1,103,580,null,2,5,"此项目实施后可保证103户居民的安全饮水问题。","此项目可保证103户居民的安全饮水问题，提高居民的生活质量，达到居民满意度，提高居民的幸福指数。"]
[140,"农村基础建设","农村道路建设","配套基础设施","五里牌街道","花桥村","路面加宽及桥梁提质改造","改建","花桥村下屋组至刘湾组","2023.01.01","2023.01.20","花桥村","公路硬化460米砌挡土墙111米桥梁加宽2.2米",24,12,12,1,34,212,null,3,5,"此项目可以保证212人正常出行。","此路改建好之后可以提高农民的出行质量，达到农民平安出行的满意度，使农民家中的农产品外出销售，从而提高农民收入。"]
[141,"产业发展","生产项目",null,"五里牌街道","松峰村","松峰村黄精种植集团经济产业园","扩种","松峰村老屋组","2023.01","2023.12","松峰村","70亩",70,30,40,1,903,4500,null,24,60,"此项目可促进农户增收，以及农副产品多样发展。","利用松峰村部分闲置荒山荒地，促进农户增收，以及农副产品多样发展提高农民生活水平。"]
[142,"农村基础建设","农村道路建设","配套基础设施","五里牌街道","松峰村","公路拓宽","改建","下坝组至松峰村部下坝组至上屋组","2023.01","2023.12","松峰村","下坝组至松峰村部下坝组至上屋组公路拓宽4000米",98,20,78,1,903,4500,null,24,60,"此路改建好之后可以提高农民的出行质量，达到农民平安出行的满意度。","此路改建好之后可以提高农民的出行质量，达到农民平安出行的满意度，使农民家中的农产品外出销售，从而提高农民收入。"]
[143,"农村基础建设","农村水利建设","配套基础设施","五里牌街道","松峰村","安全饮水","新建","松峰上铁下铁安坡序阳彭冲井泉小垅周家杨梅兴源新冲豪主旭林宴屋朝阳戴家大咀上屋兴屋斗山丁家张家新屋宋坳苏家赶冲","2023.01","2023.12","松峰村","26个村民小组",200,20,180,1,903,4500,null,24,60,"此项目实施后可保证26个村民小组居民的安全饮水问题","此项目可保证26个居民小组居民的安全饮水问题，提高居民的生活质量，达到居民满意度，提高居民的幸福指数。"]
[144,"农村基础建设","农村道路建设","配套基础设施","五里牌街道","楠木村","桥梁附属工程","新建","楠木村长春组","2023.01.01","2023.01.31","楠木村","桥两边路基提高及硬化",30,15,15,1,789,4162,null,6,13,"此项目实施后可提高居民出行质量","此路改建好之后可以提高农民的出行质量，达到农民平安出行的满意度，使农民家中的农产品外出销售，从而提高农民收入。"]
[145,"农村基础建设","农村水利建设","配套基础设施","五里牌街道","新球社区","山塘整修","改建","新球社区龚家组","2023.10","2023.11","新球社区","清淤护堤塘堤翻修管道道铺设",8,8,null,1,32,128,null,3,9,"山塘通过整修，能保证128人农田能够及时得到灌溉。","山塘通过整修，能保证128人农田能够及时得到灌溉，避免因旱情缺水导致农田减产，从而提高农田产量，增加农户收入。"]
[146,"农村基础建设","农村水利建设","配套基础设施","五里牌街道","新球社区","沟渠整修","改建","新球社区沈家组","2023.10","2023.11","新球社区","清淤疏通整修沟渠",8,8,null,1,48,185,null,4,11,"沟渠通过整修，能保证185人的农田能够及时得到灌溉。","沟渠通过整修，能保证185人的农田能够及时得到灌溉，避免缺水导致农田减产，从而提高农田产量，增加农户收入。"]
[147,"农村基础建设","农村水利建设","配套基础设施","五里牌街道","烟冲村","小港修复工程","改建","烟冲村王洋组","2023.01","2023.02","烟冲村","砌磡180立方桥体加固",12,12,null,1,42,264,null,11,46,"此项目实施后可保证264人的农田灌溉问题","小港通过整修，能保证264人的农田能够及时得到灌溉，避免缺水导致农田减产，从而提高农田产量，增加农户收入。"]
[148,"产业发展","生产项目","配套基础设施","五里牌街道","烟冲村","农田整改农作物种植基地","改建","烟冲村杨畈组","2023.01","2023.03","烟冲村","40亩农田整改",13,13,null,1,23,180,null,14,55,"40亩农田通过整改可提高农民收入。","此项目建设可保障农田种植面积，保障农民生活水平，提高农民收入。"]
[149,"产业发展","生产项目","农村产业发展","五里牌街道","五里牌街道","产业奖补","新建","五里牌街道","2023.01","2023.12",null,"对在家发展种养业的200余户脱贫户进行奖补",30,30,null,10,231,611,null,200,200,"鼓励全街道脱贫户和监测户通过发展种养业，提高收入。","此项目以生产物资或现金奖励的形式，鼓励全街道脱贫户和监测户通过发展种养业，提高经济收入，降低贫困发生率0.5%。"]
[150,"就业项目","公益岗位","公益岗位","五里牌街道","五里牌街道","公益岗位","新建","五里牌街道","2023.01","2023.12",null,"公益岗位",20,20,null,10,231,611,null,50,50,"符合条件的脱贫户和监测户全覆盖。","加快推进巩固脱贫成果与乡村振兴战略的有效衔接，改善农村人居环境，稳定脱贫户及监测户家庭经济收入。"]
[151,"产业发展","生产项目","休闲农业与乡村旅游","詹桥镇","壁山村","壁山村红色文化广场停车站","新建","壁山学校","2022年10月","2022年12月","壁山村","道路硬化3000m²",45,45,null,1,130,620,1,14,40,"推动特色产业发展，打造自主品牌，结合乡村旅游拓展产业链，为居民致富开拓新风向","红色旅游+农户就业相结合"]
[152,"乡村建设行动","农村基础设施","农村供水保障设施建设","詹桥镇","长浩村","长浩村饮水工程","新建","长浩村姚家组至熊畈组","2023年2月","2023年6月","长浩村","等水池、蓄水池、水管连接5000米",30,30,null,1,165,540,1,19,73,"此项目建设保障长浩村村民安全饮水，其中脱贫户19户，从根本上改善村民饮水健康，减少疾病发生","安全饮水+农户保障"]
[153,"产业发展","生产项目","种植业基地","詹桥镇","长浩村","长浩村果园后期工程","新建","长浩村万兴组至万明组","2023年3月","2023年8月","长浩村","果园驳岸、果树抚育设施60亩",13,13,null,1,132,356,1,8,30,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果","种植基地+农户就业相结合"]
[154,"产业发展","生产项目","种植业基地","詹桥镇","水泉村","2023年水泉村杨梅基地建设","新建","水泉村七湾组","2023年3月","2023年5月","水泉村","杨梅种植80亩",10,10,null,1,10,38,1,5,20,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果","种植基地+农户就业相结合"]
[155,"产业发展","生产项目","种植业基地","詹桥镇","印石村","印石村有机蔬菜种植基地","新建","印石村杨家组","7月","10月","印石村","印石村有机蔬菜种植基地70亩",8,5,3,1,32,133,1,3,8,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果","种植基地+农户保障相结合"]
[156,"产业发展","生产项目","种植业基地","詹桥镇","沙团村","沙团村生姜种植基地","新建","沙团村土背组后山","2023年4月","2023年5月","沙团村","生姜种植30亩",20,20,null,1,38,115,1,17,49,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果","种植基地+农户就业相结合"]
[157,"产业发展","生产项目","种植业基地","詹桥镇","分水村","2023年分水村中药材种植基地","新建","分水村各山组","2023年2月","2023年5月","分水村","中药材种植50亩",18,18,null,1,123,356,1,12,37,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果","种植基地+农户就业相结合"]
[158,"产业发展","生产项目","种植业基地","詹桥镇","三界村","2023年三界村香莲种植基地","新建","三界村油铺组","2023年1月","2023年2月","三界村","香莲种植30亩",12,12,null,1,125,786,1,7,27,"发展集体经济，带动群众发展产业，增加群众及贫困户收入，巩固脱贫成果","种植基地+农户就业相结合"]
[159,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","云山村","2023年云山村村级公路维修","新建","云山村坳上组至坳背组","2023年2月","2023年5月","云山村","公路拓宽及硬化长1000米拓宽至4.5米",45,45,null,1,251,498,1,11,31,"为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[160,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","贺畈社区","2023年贺畈社区组级公路拓宽硬化","新建","鸦山水库至山上组、胡岭组","2023年2月","2023年11月","贺畈社区","公路拓宽及硬化长2.2公里拓宽至5米",65,65,null,1,60,250,1,4,13,"为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[161,"乡村建设行动","农村基础设施","农村道路建设","詹桥镇","贺畈社区","2023年贺畈社区谭冲组公路拓宽硬化","新建","谭冲组","2023年2月","2023年11月","贺畈社区","公路拓宽及硬化长450米拓宽至5米",25,25,null,1,58,210,1,4,16,"为了群众出行和安全，基础设施改造，提高脱贫户和其他群众生产生活条件","基础设施+农户保障相结合"]
[162,"产业发展","产业服务支撑项目","其他","詹桥镇",null,"2023年詹桥镇产业奖补","新建","詹桥镇","2023年1月","2023年12月","詹桥镇","带动全镇脱贫人口发展产业，提高脱贫人口收入",70,70,null,14,657,2019,4,657,2019,"带动全镇脱贫人口发展产业，提高脱贫人口收入，受益贫困人口657户2019人","种植基地+农户就业相结合"]
[163,"就业项目","公益性岗位","公益性岗位","詹桥镇",null,"2023年詹桥镇公益岗位","新建","詹桥镇","2023年1月","2023年12月","詹桥镇","鼓励聘用脱贫户务工",13.5,13.5,null,14,45,45,4,45,45,"为群众及脱贫户提供就业机会，带动增收致富","公益岗位+农户就业相结合"]
[164,"乡村建设行动","农村基础设施","其他","詹桥镇",null,"2023年詹桥镇易地搬迁安置点基础设施建设","新建","詹桥镇易地搬迁安置点","2023年1月","2023年12月","詹桥镇易地搬迁安置点","安置点80户居民",10,10,null,12,80,274,4,80,274,"此项目实施，通过安置点基础设施建设，提高住户生活质量，提升脱贫户脱贫质量，进一步巩固脱贫成果","基础设施+农户保障相结合"]
[165,"产业发展","生产项目","种植业基地","詹桥镇",null,"2023年詹桥镇易地搬迁安置点产业发展","新建","詹桥镇易地搬迁安置点","2023年1月","2023年12月","詹桥镇易地搬迁安置点","扶贫车间产业配套，安置点80户居民",25,25,null,12,80,274,4,80,274,"此项目实施，通过帮助发展产业，改变住户生活质量，提升脱贫户脱贫质量，进一步巩固脱贫成果","种植基地+农户就业相结合"]
[166,"产业发展","生产项目","种植业基地","忠防","响山村","响山村扩大油茶基地种植规模","新建","响山村",1,3,"响山村","200亩",40,20,20,1,10,27,0,6,11,"完成扩大油茶基地种植规模200亩，增加脱贫户和周边群众的生活收入。","增加脱贫户和周边群众的生活收入，群众满意度100%"]
[167,"乡村建设行动","农村基础设施","农村供水保障设施建设","忠防","双港村","四屋组灌溉水渠","新建","四屋组",2023.3,2023.11,"双港村","1.2KM",30,20,10,1,120,520,0,15,5,"完成水渠灌溉，增加脱贫户和周边群众的生活收入","增加脱贫户和周边群众的生活收入，群众满意度100%"]
[168,"产业发展","生产项目","种植业基地","忠防","双港村","双港杨里组、陈家组、四屋组油茶基地","新建","杨里组、陈家组、四屋组",2023.3,2023.7,"双港村","230亩",45,30,15,1,12,34,0,3,8,"完成油茶基地建设，增加脱贫户和周边群众的生活收入","增加脱贫户和周边群众的生活收入，群众满意度100%"]
[169,"乡村建设行动","农村基础设施","农村供水保障设施建设","忠防","沙坪村","沙坪        村大山水渠整修硬化","整修","官山组","2月","11月","沙坪村","全长1000米\n",30,22,8,1,60,450,0,6,12,"构建美丽宜居新农村，提高农户幸福感。利于脱贫户和周边群众生产用水。","利于脱贫户和周边群众生产用水，群众满意度100%"]
[170,"产业发展","生产项目","光伏电站建设","忠防","汀畈社区","汀畈社区集体经济光伏发电","新建","元冲组",2023.1,2023.11,"汀畈社区","光伏发电100KW",50,25,25,1,12,34,0,3,8,"完成一个100KW的光伏发电站，增加脱贫户和周边群众的生活收入","增加脱贫户和周边群众的生活收入，群众满意度100%"]
[171,"乡村建设行动","农村基础设施","农村供水保障设施建设","忠防","木形村","木形村堤湾组港堤维修加固","维修","堤湾组","2月","6月","木形村","150米港堤维修，一座堰坝加固",15,10,5,1,300,1080,0,2,10,"解决我村村民灌溉用水","利于脱贫户和周边群众发展多种产业经济，增产增收.群众满意度100%"]
[172,"产业发展","生产项目","种植业基地","忠防","忠防社区","忠防镇忠防社区咀上组猕猴桃种植基地","新建","咀上组","3月","9月","忠防社区","垦荒及土地整36 亩，购栽种苗4300 根，施肥抚育76 亩，",15,9,6,1,5,20,0,2,4,"充分利用了现有土地资源，引导了群众发展多种产业经济，为脱贫户监测户提供临时就业岗位，增产增收.","利于脱贫户和周边群众发展多种产业经济，增产增收.群众满意度100%"]
[173,"乡村建设行动","农村基础设施","农村供水保障设施建设","忠防","邱坪社区","忠防镇邱坪社区张坪组安全饮水","新建","邱坪社区","1月","3月","邱坪社区","全长1500米",11,0,11,0,28,118,0,2,2,"完成管道1500米，利于脱贫户和周边群众生产用水。","利于脱贫户和周边群众生产用水，群众满意度100%"]
[174,"产业发展","生产项目","种植业基地","忠防","马家洞村","忠防镇马家洞村黄土组药材基地","扩建","黄土组",2023.1,2023.12,"马家洞村","维护12亩",15,10,5,1,30,115,1,10,30,"为脱贫户提供零时就业岗位，增加村集体经济收入，用于村集体建设","利于部分脱贫户增收，利于村集体经济发展，群众满意度100%"]
[175,"乡村建设行动","农村基础设施","农村供水保障设施建设","忠防","马家洞村","忠防镇马家洞村谢垅组河港治理","新建","谢垅组",2023.4,2023.8,"马家洞村","500米河港清淤护坡",10,10,0,1,40,165,1,20,58,"完成河道治理100，含河道清淤，砌墈。","利于脱贫户和周边群众生产生活用水安全，群众满意度100%"]
[176,"乡村建设行动","农村基础设施","农村道路建设","忠防","新田村","忠防镇新田村村部公路建设","改建","新田村",11,"2023年5","新田组","全长85 米，宽 3.5米",15,10,5,1,48,296,0,5,13,"全长 85米，宽3.5 米，利于脱贫户出行困难","得于脱贫户出行困难，群众满意度100%"]
[177,"产业发展","生产项目","种植业基地","忠防","雁峰村","雁峰村晓丰片茶油树基地","新建","元咀组",6,11,"雁峰村","300亩山林整改，种植300亩茶油树",30,20,10,1,35,75,0,4,11,"完成300亩山林整改，种植300亩茶油树。利于脱贫户和周边群众生产生活","利于脱贫户和周边群众生产生活，群众满意度100%"]
[178,"乡村建设行动","农村基础设施","农村供水保障设施建设","忠防","雁峰村","雁峰村中雁片灌溉水渠修整","改建","坳背组、港背组",9,11,"雁峰村","改建修整1600米灌溉水渠",25,20,5,1,169,762,0,7,14,"改建修整1600米农田灌溉水渠，利于脱贫户和周边群众生产生活","利于脱贫户和周边群众生产生活，群众满意度100%"]
[179,"乡村建设行动","农村基础设施","农村道路建设","忠防","渔潭村","猫行组公路连接线硬化","新建","猫形组",2023.3,2023.11,"渔潭村","1KM",30,0,30,1,120,360,0,3,6,"完成公路硬化，增加脱贫户和周边群众的生活收入","增加脱贫户和周边群众的生活收入，群众满意度100%"]
[180,"乡村建设行动","农村基础设施","农村供水保障设施建设","忠防","渔潭村","王家组烂上组安全饮水工程","新建","王家组，烂上组",2023.3,2023.7,"渔潭村","主管2KM",35,0,35,1,130,370,0,3,5,"完成安全饮水工程建设，保证饮水安全。","增加脱贫户和周边群众的生活收入，群众满意度100%"]
[181,"就业项目","公益性岗位奖补","公益性岗位奖补","忠防","忠防镇","忠防镇2023年公益岗位","新建","忠防镇",2023.1,2023.12,"忠防镇","公益性岗位奖补",9.6,9.6,0,11,32,32,1,32,32,"用于鼓励脱贫户监测户自力更生，做保洁员等公益性岗位奖补，保证收入问题。","用于鼓励脱贫户监测户自力更生，做保洁员等公益性岗位奖补，保证收入问题。"]
[182,"产业发展","生产项目","种植业基地","忠防","忠防镇","忠防镇2023年产业奖补","新建","忠防镇",2023.01,2023.12,"忠防镇","产业奖补",17,17,0,11,160,160,1,160,160,"利于脱贫户自力更生，利用鼓励种养增加收入保障脱贫成效，奖补金额补贴种养支出10%左右。","利于脱贫户自力更生，利用鼓励种养增加收入保障脱贫成效，奖补金额补贴种养支出10%左右。"]
[183,"产业发展","生产项目","种植业 基地","聂市镇","权桥村","权家西陇组茶油种植基地","新建","权家西陇组","2022年10 月","2023年4 月","权桥村","茶油种植100亩",30,20,10,1,312,836,null,4,10,"权家西陇谢家马安严家杉木种植油茶100亩。","带动脱贫户及农户发展产业"]
[184,"乡村建设行动","农村基础设施","小型农田水利设施建设","聂市镇","权桥村","权家组梨树冲山塘、杉木组新屋冲山塘","新建","权家组、杉木组","2023年2 月","2023年4 月","权桥村","权家组、杉木组山塘整修",8,6,2,9,126,378,null,13,29,"山塘维修有效提供9个组的稻田灌溉，提高贫困户增产增收。","带动农户及脱贫户稻田灌溉及增产增收。"]
[185,"产业发展","加工物流项目","产地初加工及精深加工","聂市镇","乘岭社区","湘莲厂二期建设","2022年转2023年","乘岭社区","2023年6月1日","2023年9月31日","乘岭社区","700㎡湘莲加工厂二期建设",60,50,10,1,522,1804,null,32,88,"发展集体经济，带动群众发展产业，增加群众及脱贫户收入，巩固脱贫成果。","带动农户及脱贫户发展产业增产增收。"]
[186,"产业发展","生产项目","种植业基地","聂市镇","凤形村","黄金种植","新建","军畈组，龙斗组，乔山组","2023年01 月","2023年12 月","凤形村","新增中药材黄精种植面积100亩",50,40,10,1,7,23,null,7,23,"从2023年至2026年增加中药材黄精种植面积100亩，带动群众发展产业，提高群众收入，巩固脱贫成果。","解决脱贫户及农户就业"]
[187,"乡村建设行动","农村基础设施","小型农田水利设施建设","聂市镇","凤形村","山塘整修","新建","塘湾、方湾、芹冲、沈家四座山塘整修","2023年","2023年","凤形村","山塘维修",10,8,2,1,160,358,null,11,22,"山塘维修（群众用水），稳固脱贫成效。该项目涉及农户160户358人，其中脱贫户11户22人","水利设施维修，方便群众发展生产"]
[188,"产业发展","生产项目","种植业基地","聂市镇","马垅村","湘莲栽种","新建","何桥组、香花组等6个组","2023年04 月","2023年10 月","马垅村","湘莲栽种300亩",28,22,6,1,110,589,1,13,26,"巩固脱贫成效，壮大集体经济","解决脱贫户及农户就业"]
[189,"产业发展","生产项目","养殖业基地","聂市镇","马垅村","稻田养虾","新建","庙下组","2023年02 月","2023年10 月","马垅村","稻田养虾110亩",35,27,8,1,78,330,1,5,7,"巩固脱贫成效，壮大集体经济","解决脱贫户及农户就业"]
[190,"产业发展","生产项目","种植业基地","聂市镇","三和村","鸿鸣花卉基地整改","新建","廖家组","2023年03 月","2023年04 月","三和村","整改10亩",40,30,10,1,50,160,null,14,37,"改善产业发展条件增加农民收入","解决脱贫户及农户就业"]
[191,"乡村建设行动","农村基础设施","农村道路建设","聂市镇","朱圣村","朱圣村四海组公路驳岸","新建","朱圣村四海组","2022年11 月","2023年2  月","朱圣村","朱圣村四海组公路驳岸",5,5,0,1,50,268,null,4,10,"公路驳岸防止公路塌陷，稳固脱贫成效。该项目涉及农户50户268人，其中脱贫户4户10人。","公路驳岸防止公路塌陷，稳固脱贫成效。"]
[192,"产业发展","生产项目","种植业基地","聂市镇","汤畈村","拾房组经果林基地","新建","拾房组","2023年03 月","2023年05 月","汤畈村","经果林基地40亩",15,10,5,1,48,156,null,3,7,"带动群众大力发展产业，提高脱贫户人口收入，巩固脱贫成果。","解决脱贫户及农户就业"]
[193,"乡村建设行动","农村基础设施","小型农田水利设施建设","聂市镇","汤畈村","带冲组山塘驳岸","新建","带冲组","2023年02 月","2023年03 月","汤畈村","山塘驳岸100米",8,5,3,1,30,145,null,1,2,"加强基础建设，为产业发展提供条件，增加群众收入。","加强基础建设，为产业发展提供条件，增加群众收入。"]
[194,"乡村建设行动","农村基础设施","农村道路建设","聂市镇","汤畈村","白果组公路白改黑","新建","白果组","2023年04 月","2023年06 月","汤畈村","公路白改黑长600米，宽3.5米厚0.03米",40,30,10,1,28,126,null,3,8,"加强乡村建设，改变村容村貌，为民提供优越生活条件。","加强基础建设，改变村容村貌，为民提供优越生活条件，巩固脱贫成果。"]
[195,"乡村建设行动","农村基础设施","农村道路建设","聂市镇","源潭社区","源潭社区刘家坡道路硬化","新建","源潭社区底塘组","2023年06 月","2023年07 月","源潭社区","硬化道路长228米，宽3.5米",13.6,5,8.6,1,40,192,null,6,15,"改善了脱贫户与居民周边环境，防止返贫","加强基础建设，改变村容村貌，巩固脱贫成果。"]
[196,"乡村建设行动","农村基础设施","小型农田水利设施建设","聂市镇","红士村","红士村十一座山塘整修","新建","红士村","2022年11 月","2023年1  月","红士村","红士村十一座山塘整修（新屋山塘、王咀山塘、大坡山塘、赵家垅山塘、新屋冲山塘、大屋山塘、后垅山塘、梨树山塘、上王山塘、塘门山塘、峡冲山塘）",30,25,5,1,370,1800,1,18,55,"山塘整险可有效灌溉农田作物增加脱贫户及农户农业生产收入.","加强基础建设，为产业发展提供条件，巩固脱贫成果。"]
[197,"乡村建设行动","农村基础设施","小型农田水利设施建设","聂市镇","沿河社区","山塘整修","山塘整修","树湾组","2023年","2023年","沿河社区","山塘整修",5,3,2,1,93,348,null,3,6,"山塘整修（群众用水），巩固脱贫成果。该项目涉及93户348人，其中脱贫户及监测户3户6人。","解决农户农田灌溉"]
[198,"产业发展","生产项目","养殖业基地","聂市镇","同德村","聂市镇同德村同德垸500亩水面生态养殖项目建设工程","转2022年入库","同德垸","2023年3  月","2023年8 月","同德村","聂市镇同德村同德垸500亩水面生态养殖，由村集体统一实行人放天养，养殖草鱼、白鲢、桂花鱼、鲫鱼等四大家鱼常规渔业养殖。",55,25,30,1,1213,5119,null,4,185,"巩固脱贫成效，壮大集体经济，吸收脱贫劳动力就业，该项目涉及农户1213户5119人，其中脱贫户52户185人。","解决脱贫户及农户就业"]
[199,"产业发展","生产项目","种植业基地","聂市镇","同合村","洞庭茶园基地","转2022年入库","洞庭组钱家组晏明组吴家组","2022年11 月","2023年4 月","同合村","新建油茶种植400亩",80,60,20,1,938,3846,1,65,227,"巩固脱贫成效，壮大集体经济，吸收脱贫劳动力就业，该项目涉及农户938户3846人，其中脱贫户65户227人。","解决脱贫户及农户就业"]
[200,"产业发展","生产项目","养殖业基地","聂市镇","同合村","临湘市中欣养殖专业合作社","新建","余家组","2022年10  月","2023年5 月","同合村","西门塔尔肉牛100头",160,100,60,1,938,3846,1,65,227,"巩固脱贫成效，壮大集体经济，吸收脱贫劳动力就业，该项目涉及农户938户3846人，其中脱贫户65户227人。","解决脱贫户及农户就业"]
[201,"产业发展","生产项目","种植业 基地","聂市镇","乘风村","湘莲种植500亩","新建","群英友爱团结组","2023年3  月","2023年10  月","乘风村","湘莲种植500亩",30,24,6,1,110,485,null,9,30,"巩固脱贫成效，壮大集体经济该项目涉及农户110户485人，其中脱贫户9户30人。","解决脱贫户及农户就业"]
[202,"产业发展","生产项目","种植业 基地","聂市镇","官田村","桥畈组茶油种植基地","新建","乌炮组和桥畈组","2022年10 月","2023月4 月","官田村","茶油种植60亩",20,12,8,1,288,650,1,3,8,"乌炮组、桥畈组杉木种植油茶60亩。该项目涉及农户288户650人，其中脱贫户3户8人。","带动脱贫户及农户发展产业"]
[203,"乡村建设行动","农村基础设施","小型农田水利设施建设","聂市镇","官田村","引水河港护砌建设","新建","引水组、燕屋组、桥畈组、凤形组、麻阳组、","2023年 ","2023年","官田村","引水河港护砌工程",50,40,10,1,100,500,1,22,70,"改善农村产业发展条件增加农民收入.该项目涉及农户100户500人，其中脱贫户22户70人。","加强基础建设，为产业发展提供条件，巩固脱贫成果。"]
[204,"乡村建设行动","农村基础设施","小型农田水利设施建设","聂市镇","官田村","山塘整修","新建","注冲组、廖冲组四座山塘整修","2023年","2023年","官田村","山塘维修",12,9,3,1,150,322,1,10,26,"山塘维修（群众用水），稳固脱贫成效。该项目涉及农户150户322人，其中脱贫户10户26人","加强基础建设，为产业发展提供条件，巩固脱贫成果。"]
[205,"产业发展","生产项目",null,"聂市镇",null,"聂市镇产业奖补","新建","聂市镇","2023年","2023年","聂市镇","聂市镇产业奖补",80,80,null,17,632,1869,4,245,764,"全镇范围内实施产业奖补，受益脱贫户及监测户脱贫户632户1869人","全镇范围内实施产业奖补，支持鼓励产业发展，提高脱贫人口及监测户收入，巩固脱贫成果。"]
[206,"就业项目","公益性岗位","公益性岗位","聂市镇",null,"聂市镇公益性岗位","新建","聂市镇","2023年","2023年","聂市镇","聂市镇公益性岗位",33,33,null,17,632,1869,4,245,764,"全镇范围内实施公益性岗位，受益脱贫户及监测户脱贫户632户1869人","全镇范围内实施公益性岗位，解决脱贫人口及监测户就业难问题，巩固脱贫成果。"]
[207,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","长塘镇","柳厂村","柳厂桥往南道路拓宽","新建","李家组","2023.1.15.","2023.8.15","柳厂村委会","长800米，宽6米，厚0.2米，驳岸300米",45,35,10,1,420,1860,1,11,38,"完善道路拓宽硬化，可改善一般群众与脱贫户的运输与出行，生产耕种，提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%","改善一般群众与脱贫户的运输与出行，生产耕种，提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
[208,"产业发展","生产项目","养殖业基地","长塘镇","柳厂村","梅花鹿养殖基地","扩建","段头组","2023.3.15","2023.9.15","柳厂村委会","养殖区：100平方米，养殖鹿：30头",53,45,8,1,860,3650,1,21,80,"产业发展，能让周边的困难群众及脱贫户就近就地就业，能增加老百姓收入，改变生活质量，提升脱贫户脱贫质量，进一步巩固成果，长久受益群众满意度100%","带动困难群众及脱贫户30人就近就地就业","2022年转"]
[209,"产业发展","配套基础设施项目","小型农田水利设施建设","长塘镇","柳厂村","李家组水渠维修","维修","李家组","2023.3.15","2023.8.15","柳厂村委会","长：450米，宽：1米，高：1.2米，混泥土厚度：0.3米",21,15,6,1,48,127,1,2,12,"完善水渠维修，可改善一般群众与脱贫户的生产生活用水，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%","改善一般群众与脱贫户的生产生活用水，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
[210,"产业发展","配套基础设施项目","小型农田水利设施建设","长塘镇","古洞村","沙家塘维修驳岸","新建","中屋组","2023.6.30","2023.8.30","古洞村","驳岸全长40米，高2米",17,10,7,1,126,680,1,5,17,"通过水利维修，解决脱贫户及广大群众的灌溉用水，促进农业增产增收，群众满意度100%","改善一般群众与脱贫户的生产生活用水，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
[211,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","长塘镇","古洞村","道路驳岸","新建","陈段组","2023.4.3","2023.5.3","古洞村","道路驳岸全长30米",15,8,7,1,131,680,1,3,5,"改善一般群众与脱贫户的运输与出行，生产耕种，提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%","改善一般群众与脱贫户的生产生活用水，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
[212,"产业发展","配套基础设施项目","小型农田水利设施建设","长塘镇","古洞村","芦塘维修驳岸","新建","曹田组","2023.5.3","2023.7.3","古洞村","驳岸全长30米，高1.5米",16,10,6,1,163,890,1,3,5,"通过水利维修，解决脱贫户及广大群众的灌溉用水，促进农业增产增收，群众满意度100%","改善一般群众与脱贫户的生产生活用水，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
[213,"产业发展","生产项目","种植业基地","长塘镇","古洞村","种植药材吴茱萸","恢复","邹家组","2023.3.15","2023.5.15","古洞村","30万株",12,10,2,1,163,890,1,5,17,"改善村集体经济、稳固脱贫成效、长久受益群众满意度100%","带动20人就业"]
[214,"产业发展","配套基础设施项目","小型农田水利设施建设","长塘镇","马安村","水渠建设","新建","狮子组、太山组","2023.1.10","2023.11.10","马安村","800米水渠、水井一口",30,15,15,1,200,780,1,4,11,"解决了老百姓及脱贫户的农田灌溉，提升了脱贫户自身发展能力，有利于促进群众及脱贫户增产增收，巩固脱贫成果","改善一般群众与脱贫户的生产生活用水，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
[215,"产业发展","配套基础设施项目","小型农田水利设施建设","长塘镇","马安村","水库建设","改建","四屋组","2023.1.20","2023.10.15","马安村","取淤5000方、埋泄洪管、护坡",38,18,20,1,620,2480,1,17,50,"解决了老百姓及脱贫户的农田灌溉，提升了脱贫户自身发展能力，有利于促进群众及脱贫户增产增收，巩固脱贫成果","改善一般群众与脱贫户的生产生活用水，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
[216,"产业发展","配套基础设施项目","小型农田水利设施建设","长塘镇","水圳村","蓄水塘建设","新建","四合组","2023.1.1","2023.10.1 ","水圳村","驳岸60米、水沟40米",15,10,5,1,220,980,1,3,11,"解决了老百姓及脱贫户的农田灌溉，提升了脱贫户自身发展能力，有利于促进群众及脱贫户增产增收，巩固脱贫成果","改善一般群众与脱贫户的生产生活用水，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
[217,"产业发展","配套基础设施项目","小型农田水利设施建设","长塘镇","水圳村","池塘清淤驳岸","新建","细黄片","2023.10.1","2023.11.1 ","水圳村","240米*2米",15,10,5,1,98,42,1,2,8,"解决了老百姓及脱贫户的农田灌溉，提升了脱贫户自身发展能力，有利于促进群众及脱贫户增产增收，巩固脱贫成果","改善一般群众与脱贫户的生产生活用水，有利于农田灌溉，粮食种植提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
[218,"乡村建设行动","农村基础设施","农村道路建设（通村、通户路）","长塘镇","水圳村","机耕路硬化","新建","边坎组","2023.4.1","2023.5.1","水圳村","400米*3米*0.2米",18,10,8,1,104,480,1,3,11,"改善一般群众与脱贫户的运输与出行，生产耕种，提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%","改善一般群众与脱贫户的运输与出行，生产耕种，提升经济效益，促进巩固脱贫成效，长久受益群众满意度100%"]
[219,"产业发展","生产项目","种植业基地","长塘镇","长塘社区","马蒂种植","新建","长塘社区辖区范围内","2023.7.15","2024.2.28","长塘社区","马蒂种植100亩",7,5,2,1,18,72,1,4,8,"完成我社区马蒂种植100亩，带动增加产值30万，带动群众18人就业，其中贫困劳动力3人。受益建档脱贫户4户8人，群众满意度99%","带动18人就业"]
[220,"产业发展","配套基础设施项目","小型农田水利设施建设","长塘镇","长塘社区","水渠建设","新建","汪家组-邓家岭","2023.1.20","2023.8.30","长塘社区","新建水渠1500米*0.6米*0.5米",35,20,15,1,192,768,1,7,17,"通过水利维修，解决脱贫户及广大群众的灌溉用水，促进农业增产增收，同时可安排部份脱贫户参与修建，增加收入。","带动26人就业"]
[221,"乡村建设行动","农村基础设施","农村供水保障","长塘镇","长塘社区","邓家片自来水安装","新建","邓家片","2023.1.15 ","2023.12.30","长塘社区","自来水安装85户",20,20,0,1,85,362,1,5,13,"完成我社区邓家片自来水安装，完善社区基础设施 ，改善一般群众与贫困户的饮水安全问题，提升贫困户幸福感安全感。安装自来水设施，贫困劳动力可以参与其中务工，提高脱贫户收入。建设此项目，群众满意度99％.","带动8人就业"]
[222,"产业发展","生产项目","种植业基地","长塘镇","何洞村","油茶基地","新建","段家组/沈家组/艾家组","2023.1.1","2023.7.1","何洞村","新建油茶基地160亩",80,60,20,1,39,169,"\t1",2,6,"有利于夯实村域集体经济基础壮大集体经济改善环境帮助脱贫户解决就业，增加收入","按照公司加集体加农户的模式联动开发"]
[223,"产业发展","生产项目","种植业基地","长塘镇","何洞村","油茶基地","新建","陆家组/周家组/新屋一组","2023.7..2","2023.12.1","何洞村","新建油茶基地150亩",75,60,15,1,103,478,null,3,9,"有利于夯实村域集体经济基础壮大集体经济改善环境帮助脱贫户解决就业，增加收入","按照公司加集体加农户的模式联动开发"]
[224,"产业发展","生产项目","养殖业基地","长塘镇","何洞村","养鸡场","\t改建","沈一组","2023.1.1","2023.5.1","何洞村","改建2万羽养鸡场一个",80,20,60,1,10,50,1,4,6,"有利于夯实村域集体经济基础壮大集体经济改善环境帮助脱贫户解决就业，增加收入","按照公司加集体加农户的模式联动开发"]
[225,"乡村建设行动","人居环境整治","农村基础设施","长塘镇","托坝社区","中屋组水沟及驳岸","新建","中屋组","2023.5.1","2023.10.30","托坝社区","水沟：长520米 高0.8米 底宽0.5米 口宽0.8米  厚0.2米                     盖板：1050片*120元/片",40,20,20,1,640,2200,1,10,31,"集中办事场所的修建，为社区贫困户以及广大群众创造了更好、更便利的生活条件，群众满意度100%","集中办事场所的修建，为社区贫困户以及广大群众创造了更好、更便利的生活条件，群众满意度100%","2022年转"]
[226,"乡村建设行动","人居环境整治","农村污水治理","长塘镇","托坝社区","托坝西街污水治理","新建","托坝西街","2023.7.1","2023.9.30","托坝社区","长1200米 高0.6米 底宽0.4米 口宽0.7米 厚0.2米",30,10,20,1,320,800,1,4,14,"完善社区基础设施，改善人居环境，水沟建设给社区脱贫户和广大群众的生活带来了极大的方便，提高了生活质量。","完善社区基础设施，改善人居环境，水沟建设给社区脱贫户和广大群众的生活带来了极大的方便，提高了生活质量。"]
[227,"产业发展","生产项目","种植业基地、产地初加工和精深加工","长塘镇","托坝社区","红薯种植及加工基地","新建","游港河内港、集中建房点","2023.3.1","2023.11.30","托坝社区","200亩（购红薯种子 育秧苗 栽种秧苗 收获）   加工设备4套 2个厂房共260平（长13米 宽10米 高4.5米）",47,20,27,1,800,2000,1,6,19,"完成我社区红薯种植200亩，带动增加产值6万，带动群众14人就业 购置完整红薯加工设备，增加集体经济收入，带动脱贫户和社区群众就业","完成我社区红薯种植200亩，带动增加产值6万，带动群众15人就业 购置完整红薯加工设备，增加集体经济收入，带动脱贫户和社区群众就业"]
[228,"乡村建设行动","农村基础设施","产业路建设","长塘镇","石田村","上铺组水渠至李家桥驳岸","新建","上铺组","2023.4.1","2023.5.1","石田村","长260米、上宽0.5米、下宽1.2米，高1.7米，脚长260米、宽1.2米、高１米共计６８８立方米",30,10,20,1,50,400,0,7,17,"完善水利建设，改善灌溉条件，增加群众收入。","改善人居环境，完善水利建设，灌溉条件，增加群众收入。。","2022年转"]
[229,"乡村建设行动","农村基础设施","产业路建设","长塘镇","石田村","周家组至上铺组驳岸","新建","周家组","2023.4.1","2023.5.1","石田村","长160米、上宽0.5米、下宽1.2米，高1.7米，脚长260米、宽1.2米、高１米共计423.2立方米",20,10,10,1,50,400,0,7,17,"完善水利建设，改善灌溉条件，增加群众收入。","改善人居环境，完善水利建设，灌溉条件，增加群众收入。","2022年转"]
[230,"乡村建设行动","人居环境整治","农村基础设施","长塘镇","石田村","工农片水沟及驳岸","新建","工农片","2023.1.1","2023.10.30","石田村","水沟：长600米 高1米  厚0.2米                     盖板：1200片*120元/片",40,20,20,1,300,1500,1,8,22,"集中办事场所的修建，为村贫困户以及广大群众创造了更好、更便利的生活条件，群众满意度100%","集中办事场所的修建，为村贫困户以及广大群众创造了更好、更便利的生活条件，群众满意度100%"]
[231,"就业项目","公益性岗位","公益性岗位","长塘镇","长塘镇","长塘镇","新建","长塘镇","2023.1.1","2023.12.31","长塘镇人民政府","32人",9.6,9.6,0,8,29,32,8,29,32,"提升脱贫户生活质量，巩固脱贫攻坚成果，提高脱贫户收入","带动脱贫户32人就业"]
[232,"产业发展","生产项目","产业奖补","长塘镇","长塘镇","长塘镇2023年养猪养鸡","新建","长塘镇","2023.2.1","2023.10.1","长塘镇人民政府","猪仔90头，鸡2000只",15,15,0,8,100,380,8,100,380,"提升脱贫户生活质量，巩固脱贫攻坚成果，提高脱贫户收入","带动脱贫户100人发展产业，增加收入"]
[233,"乡村建设行动","农村基础设施","农村供水保障","长塘镇","长塘镇","长塘镇自来水厂提质改造","新建","长塘镇","2023.1.1","2023.12.31","长塘镇","抽水设备一套；清水池800立方；过滤池管道2000米",80,60,20,8,8792,28592,8,191,548,"用于改善群众用水质量，保障群众健康","用于改善群众用水质量，保障群众健康"]
[234,"乡村建设行动","人居环境整治","农村垃圾治理","长塘镇","长塘镇","长塘镇农村垃圾治理","新建","长塘镇","2023.1.1","2023.12.31","长塘镇","新增垃圾清运车16台",60,50,10,8,8792,28592,8,191,548,"提升村容村貌，提升群众生活幸福感","提升村容村貌，提升群众生活幸福感"]
[235,"乡村建设行动","农村基础设施","产业路、资路、资源路、旅游路建设","长塘镇","长塘镇","长塘镇游港河沿路提质改造","新建","长塘镇马安村狮子组、元门组","2023.1.1","2023.12.31","长塘镇","长1500米，宽6米，厚0.25米",200,150,50,8,8792,28592,8,191,548,"改善人居环境，方便居民出行和种植运输，提高出行安全性","改善人居环境，方便居民出行和种植运输，提高出行安全性"]
[236,"产业发展","生产项目","养殖业基地","云湖街道办事处","云湖街道办事处","云湖街道2023年产业奖补","新建","云湖各村（社区）",2023.1,2023.12,"云湖街道办事处","5个村（社区）100户348人",20,20,null,5,100,348,5,87,301,"给大约100户、348人提供产业奖补","促进脱贫户、监测户产业增收，巩固脱贫成果。"]
[237,"就业项目","公益性岗位","公益性岗位","云湖街道办事处","云湖街道办事处","云湖街道2023年公益性岗位","新建","云湖各村（社区）",2023.1,2023.12,"云湖街道办事处","5个村（社区）40户129人",15,15,null,5,40,129,5,40,129,"给5个村社区提供公益性岗位40个受益120人以上","促进脱贫户监测户稳定就业，提供收入，巩固脱贫成果。"]
[238,"产业发展","生产项目","种植业基地","云湖街道办事处","板桥村","油茶基地","扩建","白鹤组、港贝组",2023.2,2023.6,"板桥村","抚育茶树150亩",6,6,null,1,550,1760,1,10,32,"油茶苗完成抚育150亩以上，受益1760人以上","提高茶株品质，延长植株效益时长；带动脱贫户监测户就业创收，巩固脱贫攻坚成果"]
[239,"乡村建设行动","农村基础设施","农村道路建设","云湖街道办事处","板桥村","村级主公路整修","整修","全村范围",2023.3,2023.11,"板桥村","道路整修800米",64,20,44,1,840,4500,1,55,206,"道路整修800米，受益4500人以上","修整损坏路面，方便脱贫户及村民出行，为乡村振兴提供交通便利，打下基础。"]
[240,"乡村建设行动","农村基础设施","农村道路建设","云湖街道办事处","三联村","道路建设","扩建","苦竹入组道路拓宽",2023.03,2023.04,"三联村","2.3公里道路拓宽1米",25,10,15,1,15,72,1,3,12,"2.3公里道路拓宽1米，受益70人以上","解决农户交通出行\n问题"]
[241,"乡村建设行动","农村基础设施","新\n建\n通\n组\n公\n路","云湖街道办事处","三联村","接长忠公路通划船蒋家两组","新建","划船蒋家两组",2022.11,2023.01,"三联村","1.2公里长，6米宽，20公分厚",45,10,35,1,45,187,1,5,28,"新建1.2公里路，受益180人以上","解决农户交通出行\n问题"]
[242,"乡村建设行动","农村基础设施","农村道路建设","云湖街道办事处","王禾社区","组级公路连接","新建","新建组至杜家组",2023.3,2023.12,"王禾社区","全长350米宽5米水泥厚20厘米",23,10,13,1,770,3108,1,35,105,"新建350米组级公里，受益3000人以上","方便全社区人员出行高标准农田建设收益"]
[243,"乡村建设行动","农村基础设施","农村水渠建设","云湖街道办事处","王禾社区","灌排渠整修","新建","蒋一组蒋二组","2022.11.",2023.12,"王禾社区","全长200米宽1米高1米驳岸",32,15,17,1,770,3108,1,35,105,"整修渠道200米，受益3000人以上","600多亩农田灌排安全"]
[244,"乡村建设行动","农村基础设施","农村道路建设","云湖街道办事处","飞跃社区","李冲桥梁拓宽及整改","整改","栗埜片区",2023.3,2023.11,"飞跃社区","李冲桥梁拓宽及整改宽2米、长5米",15,10,5,1,130,1260,1,19,56,"桥梁拓宽整改5米，受益1200人以上","加宽桥梁及整改桥梁面，方便农户出行，为乡村振兴提供交通便利，打下基础。"]
[245,"产业发展","生产项目","种植业基地","云湖街道办事处","云湖集中安置小区","粮油生产基地","新建","王禾社区",2023.4,"2023.10","云湖集中安置小区","70.1亩水田种植",19,10,9,1,167,654,1,167,654,"种植水田70.1亩，受益600人以上","巩固脱贫成果，减少小区住户生活成本，降低返贫几率。"]
[246,"产业发展","生产项目","种植业基地","云湖街道办事处","云湖集中安置小区","蔬菜种植基地","新建","飞跃社区",2023.1,2023.12,"云湖集中安置小区","30亩菜地种植",6,6,null,1,167,654,1,167,654,"种植菜地30亩，受益600人以上","巩固脱贫成果，减少小区住户生活成本，降低返贫几率。"]
[247,"产业发展","配套基础设施项目","小型农田水利设施建设","云湖街道办事处","云湖集中安置小区","粮油生产基地附属路面及水渠灌溉设施","新建","王禾社区",2023.3,"2023.9","云湖集中安置小区","4米*500米路面拓宽及疏通2米*800米水渠",8,8,null,1,167,654,1,167,654,"4米*500米路面拓宽及疏通2米*800米水渠，受益600人以上","提高粮油生产基地生产效率及产量。"]
[248,"产业发展","生产项目","种植基地","白石园国有林场","建兴庵分场","临湘市欠发达白石园国有林场黄精产业发展示范基地建设项目","种植","白石园国有林场建兴庵分场菜坡","2023/1/1","2023/12/31","白石园国有林场","黄精种植50亩",57.3,40,17.3,null,null,89,{"$nulls":3},"通过项目实施，项目区林分结构将得到进一步的优化，有利于黄精的稳产、高产，对发展和保护森林资源，维护生态平衡.","可借鉴的生产经营模式，辐射周边，提高林农对科学经营的认识，促进周边林农增收增效，为衔接推进乡村振兴发挥重要的社会效益。"]
[249,"产业发展","生产项目","种植业基地","药菇山国有林场",null,"临湘市药菇山欠发达国有林场中药材培育示范基地中药材培育项目","种植","临湘市药菇山国有林场","2023年1月","2023年11月","临湘市药菇山国有林场","临湘市药菇山国有林场黄家、横山、杨树坪等林班内培育白芨、丹参、杜仲等名贵药材65亩",100.05,80,20.05,null,null,118,{"$nulls":3},"促进林场经济发展，提高林场林地资源利用率；有效地保护了林场的生态环境，建成具有区域特色的种植基地；形成现代药材生产集约化产业体系，推进乡村振兴发挥重要的社会效益。","雇用林场周边部分社会劳动力清理林地、挖坑等工序。"]
[250,"乡村建设行动","农村基础设施","农村道路建设","荆竹山国有林场","荆竹山国有林场","临湘市荆竹山欠发达国有林场林区道路硬化及集材场建设项目","新建","临湘市荆竹山国有林场","2023年4月","2023年10月","临湘市荆竹山国有林场","林区生产道路路面硬化130米、集材场建设一个（1600平方米）及附属设施建设",57.876,50,7.876,null,null,102,{"$nulls":3},"提高道路防火森林灾功能、提升公路通行能力，满足林场职工及周边居民对美好生活的需求。","改善林场职工及周边群众交通、生产生活条件等，加强林场基础设施建设，促进秀美林场建设。"]
[251,"其他","其他","少数民族发展","各乡镇","各乡镇","临湘市茶园低氟改造改造边销茶原料降氟项目","新建、改建",null,"2023年1月","2023年12月","建设相关村、社区","新建、改建低氟茶园900亩",500,340,160,18,939,2861,13,240,753,"带动周边群众就业，保障低氟黑毛茶原料供应稳定","种植基地+农户，劳务用工、保底收购、茶产业和旅游相结合"]
[252,"产业发展","小额信贷贴息","扶贫小额信贷贴息","临湘市","临湘市","扶贫小额信贷贴息","续建","各乡镇","2023年1月","2023年12月","农业银行、农商行","脱贫户（包括监测户）小额信贷贴息",200,200,null,null,650,650,null,650,650,"脱贫户（包括监测户）小额信贷贴息","鼓励群众发展产业，增加收入"]
[253,"巩固三保障成果","教育","享受 “雨露计划”职业教育补助","临湘市","临湘市","享受 “雨露计划”职业教育补助","续建","各乡镇","2023年1月","2023年12月","乡村振兴局","脱贫户（包括监测户）的子女就读职业高等学院补助1500/学期",150,150,{"$nulls":3},1000,null,1000,1000,"补助1500/学期","为脱贫户学生读书提供保障"]
[254,"乡村建设行动","人居环境整治","农村卫生厕所改造(户用、公共厕所)","临湘市","临湘市","农村卫生厕所改造(户用、公共厕所)","新建、改建","各乡镇","2023年1月","2023年12月","乡村振兴局","全市3506个厕所建设",350,350,{"$nulls":3},4000,null,4000,4000,"全市3506个厕所建设任务奖补","改善群众生活环境"]
[255,"产业发展","生产项目","支持粮食生产发展","临湘市","临湘市",null,"新建","各乡镇","2023年1月","2023年12月","农业农村局","全市双季稻种奖补",2000,2000,{"$nulls":3},300,null,300,300,"对全市双季稻种植户、粮食监测调查点、种粮大户、龙头企业、农民专业合作社、病虫害防止服务组织等进行奖补","稳定和增加粮食生产面积，增加粮食产量，鼓励、促进脱贫户种植粮食积极性，增加脱贫户种植收益。"]
[256,"就业项目","务工补助","一次性交通补贴，扶贫车间补助","临湘市","临湘市","一次性交通补贴，扶贫车间补助","新建","各乡镇","2023年1月","2023年12月","就业局","在外务工脱贫户一次性交通补贴，提供就业的扶贫车间补助",100,100,{"$nulls":3},450,null,450,450,"在外务工脱贫户一次性交通补贴，提供就业的扶贫车间补助","鼓励群众在外务工，自力更生"]
["合    计",{"$nulls":12},{"$f":"SUM(N6:N261)","v":11123.996},{"$f":"SUM(O6:O261)","v":8220.75},2903.246,146,83076,310456,26,13783,28218]